## Compliance Matrix
ID | Requirement | Page | Section | Category | Required action | Verified? | Compliant? | Owner | Notes | Source quote
R-011 | The regulatory framework for the BSL-3 lab must comply with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024 (as updated from time to time). | 2 |  | Mandatory | Comply with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024 (as updated from time to time). | Yes |  |  |  | Regulatory framework (Mandatory) DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024 (as updated from time to time)
R-041 | The consultant/selected bidder shall remain fully and exclusively responsible and accountable for the accuracy, completeness, technical soundness, regulatory compliance (including but not limited to DBT-ICMR National Guidelines, 2024 and any amendment thereon), biosafety/biosecurity integrity, and overall fitness-for-purpose of all services and deliverables provided under this engagement. | 5 |  | Mandatory | Ensure full and exclusive responsibility and accountability for accuracy, completeness, technical soundness, regulatory compliance (including DBT-ICMR National Guidelines, 2024), biosafety/biosecurity integrity, and overall fitness-for-purpose of all services and deliverables. | Yes |  |  |  | Notwithstanding any review, approval, consent, or acceptance provided by AIIMS Patna or its authorized representatives at any stage of the project—whether in respect of designs, drawings, technical specifications, reports, equipment selection, validation protocols, construction-stage technical support and design-intent compliance review, or any other deliverable or process—the consultant/selected bidder shall remain fully and exclusively responsible and accountable for the accuracy, completeness, technical soundness, regulatory compliance (including but not limited to DBT-ICMR National Guidelines, 2024 and any amendment thereon), biosafety/biosecurity integrity, and overall fitness-for-purpose of all services and deliverables provided under this engagement.
R-042 | The consultant/selected bidder must carry out all necessary corrections, revisions, revalidation, or remedial measures at their own cost, without any additional financial liability to AIIMS Patna, if any deliverable is found to be non-compliant or deficient prior to (during) final operational handover/certification process, even if previously approved. | 5 |  | Mandatory | Perform all necessary corrections, revisions, revalidation, or remedial measures at own cost for non-compliant or deficient deliverables prior to final operational handover/certification. | Yes |  |  |  | The consultant/selected bidder further undertakes to carry out all necessary corrections, revisions, revalidation, or remedial measures at their own cost, without any additional financial liability to AIIMS Patna, in the event that any deliverable, even if previously approved, is found to be non-compliant or deficient at any point prior to (during) final operational handover/certification process.
R-054 | The establishment, design, construction, commissioning, validation, certification support, and operational-readiness planning of the proposed facility shall be governed primarily by the DBT-ICMR National Guidelines for Biosafety Level-3 Laboratory, 2024, as amended or updated from time to time. | 16 | 1.1 (iv) | Mandatory | The selected A&E Consultant must ensure that the project adheres to the DBT-ICMR National Guidelines for Biosafety Level-3 Laboratory, 2024, and any subsequent amendments or updates. | Yes |  |  |  | The establishment, design, construction, commissioning, validation, certification support, and operational-readiness planning of the proposed facility shall be governed primarily by the DBT-ICMR National Guidelines for Biosafety Level-3 Laboratory, 2024, as amended or updated from time to time.
R-055 | The facility shall also be planned in alignment with applicable statutory, regulatory, biosafety, biosecurity, environmental, biomedical waste, building, fire safety, engineering, and institutional requirements, including the Environment (Protection) Act, 1986, Rules relating to hazardous microorganisms/genetically engineered organisms or cells, applicable IBSC/RCGM requirements, National Building Code, relevant BIS/IS codes, CPCB/BPCB requirements, CPWD guidelines and other applicable national and international best practices/guidelines (latest), wherever relevant. | 16 | 1.1 (iv) | Mandatory | The selected A&E Consultant must plan the facility in alignment with all specified statutory, regulatory, and institutional requirements, including but not limited to the Environment (Protection) Act, 1986, IBSC/RCGM requirements, National Building Code, BIS/IS codes, CPCB/BPCB requirements, and CPWD guidelines. | Yes |  |  |  | The facility shall also be planned in alignment with applicable statutory, regulatory, biosafety, biosecurity, environmental, biomedical waste, building, fire safety, engineering, and institutional requirements, including the Environment (Protection) Act, 1986, Rules relating to hazardous microorganisms/genetically engineered organisms or cells, applicable IBSC/RCGM requirements, National Building Code, relevant BIS/IS codes, CPCB/BPCB requirements, CPWD guidelines and other applicable national and international best practices/guidelines (latest), wherever relevant.
R-056 | The selected A&E Consultant shall be responsible for providing integrated professional services covering site verification, existing facility assessment, retrofitting assessment, biosafety risk assessment, laboratory workflow planning, containment zoning, architectural planning, engineering design, HVAC and containment engineering, MEP and utility design, building automation and monitoring systems, BIM, CFD analysis, equipment planning, technical specifications, DPR, cost estimates, BOQ, subsequent tender document, pre-bid & | 16 | 1.1 (v) | Mandatory | The selected A&E Consultant must provide integrated professional services including site verification, facility assessment, retrofitting assessment, biosafety risk assessment, laboratory workflow planning, containment zoning, architectural planning, engineering design, HVAC and containment engineering, MEP and utility design, building automation and monitoring systems, BIM, CFD analysis, equipment planning, technical specifications, DPR, cost estimates, BOQ, and subsequent tender documents. | Yes |  |  |  | The selected A&E Consultant shall be responsible for providing integrated professional services covering site verification, existing facility assessment, retrofitting assessment, biosafety risk assessment, laboratory workflow planning, containment zoning, architectural planning, engineering design, HVAC and containment engineering, MEP and utility design, building automation and monitoring systems, BIM, CFD analysis, equipment planning, technical specifications, DPR, cost estimates, BOQ, subsequent tender document, pre-bid &
R-057 | The proposed facility is required to function as a safe, compliant, maintainable, certifiable, and operationally efficient BSL-3 laboratory with associated BSL-2/support areas, proper personnel/material/sample/waste flow, controlled access, negative pressure containment, HEPA filtration, decontamination systems, emergency provisions, monitoring and alarm systems, and appropriate redundancy for critical systems. | 17 |  | Mandatory | Design the facility to function as specified. | Yes |  |  |  | (vi) The proposed facility is required to function as a safe, compliant, maintainable, certifiable, and operationally efficient BSL-3 laboratory with associated BSL-2/support areas, proper personnel/material/sample/waste flow, controlled access, negative pressure containment, HEPA filtration, decontamination systems, emergency provisions, monitoring and alarm systems, and appropriate redundancy for critical systems.
R-058 | The design shall not be limited to indicative inputs provided by AIIMS Patna; rather, the A&E Consultant shall apply its professional expertise, independent assessment, domain knowledge, biosafety expertise & understanding, compliance, engineering competence, and regulatory experience to develop a complete, coordinated, fit-for-purpose, and certification-ready design solution duly executable at construction and certification level. | 17 |  | Mandatory | Apply professional expertise and experience to develop a complete, coordinated, fit-for-purpose, and certification-ready design solution. | Yes |  |  |  | The design shall not be limited to indicative inputs provided by AIIMS Patna; rather, the A&E Consultant shall apply its professional expertise, independent assessment, domain knowledge, biosafety expertise & understanding, compliance, engineering competence, and regulatory experience to develop a complete, coordinated, fit-for-purpose, and certification-ready design solution duly executable at construction and certification level.
R-059 | This RFP is therefore issued for selection of a competent A&E Consultant capable of delivering the technical foundation for subsequent execution, commissioning, validation, certification, and operational readiness of the proposed BSL-3 laboratory at AIIMS Patna. | 17 |  | Eligibility criteria | Be a competent A&E Consultant capable of delivering the technical foundation for subsequent execution, commissioning, validation, certification, and operational readiness. | Yes |  |  |  | (vii) This RFP is therefore issued for selection of a competent A&E Consultant capable of delivering the technical foundation for subsequent execution, commissioning, validation, certification, and operational readiness of the proposed BSL-3 laboratory at AIIMS Patna.
R-060 | The A&E Consultant shall be responsible for assessing the existing facility/infrastructure, identifying required retrofitting and engineering interventions, developing the master plan, preparing biosafety risk assessment and workflow planning, designing containment and engineering systems, integrating architectural, MEP, HVAC, utility, automation, monitoring, laboratory equipment, BIM and CFD requirements, and preparing all technical documentation required for mandatory clearances (such as fire safety/environmental clearance etc.), procurement, construction, commissioning, validation and certification. | 18 | 2.1 (ii) | Mandatory | Perform the specified tasks including assessment, planning, design, integration, and documentation. | Yes |  |  |  | The A&E Consultant shall be responsible for assessing the existing facility/infrastructure, identifying required retrofitting and engineering interventions, developing the master plan, preparing biosafety risk assessment and workflow planning, designing containment and engineering systems, integrating architectural, MEP, HVAC, utility, automation, monitoring, laboratory equipment, BIM and CFD requirements, and preparing all technical documentation required for mandatory clearances (such as fire safety/environmental clearance etc.), procurement, construction, commissioning, validation and certification.
R-061 | The A&E Consultant shall ensure that the proposed solution is practical for execution, suitable for tendering, verifiable during construction, and capable of supporting successful commissioning, validation, biosafety validation and certification processes. | 18 | 2.1 (iii) | Mandatory | Ensure the proposed solution meets the specified criteria for execution, tendering, verification, and support for commissioning, validation, and certification. | Yes |  |  |  | The A&E Consultant shall ensure that the proposed solution is practical for execution, suitable for tendering, verifiable during construction, and capable of supporting successful commissioning, validation, biosafety validation and certification processes.
R-062 | The consultancy services shall result in a complete package of deliverables, including site assessment, design basis documents, master plan, containment zoning strategy, workflow plans, coordinated drawings, engineering calculations, BIM outputs, CFD analysis, technical specifications, equipment utility requirements, cost estimates, DPR, BOQ, tender documents, construction-stage technical review inputs, commissioning and validation support documents, certification-support documentation, and as-built / handover records etc., as required under this RFP. | 18 | 2.1 (iv) | Mandatory | Provide a complete package of deliverables as listed. | Yes |  |  |  | (iv) The consultancy services shall result in a complete package of deliverables, including site assessment, design basis documents, master plan, containment zoning strategy, workflow plans, coordinated drawings, engineering calculations, BIM outputs, CFD analysis, technical specifications, equipment utility requirements, cost estimates, DPR, BOQ, tender documents, construction-stage technical review inputs, commissioning and validation support documents, certification-support documentation, and as-built / handover records etc., as required under this RFP.
R-063 | The A&E Consultant shall not merely reproduce the indicative requirements provided by AIIMS Patna, but shall apply its professional expertise, independent assessment, biosafety knowledge, engineering judgment and regulatory understanding to develop a complete, coordinated and fit-for-purpose solution. | 18 | 2.1 (v) | Mandatory | Apply professional expertise, independent assessment, biosafety knowledge, engineering judgment and regulatory understanding to develop a complete, coordinated and fit-for-purpose solution. | Yes |  |  |  | (v) The A&E Consultant shall not merely reproduce the indicative requirements provided by AIIMS Patna, but shall apply its professional expertise, independent assessment, biosafety knowledge, engineering judgment and regulatory understanding to develop a complete, coordinated and fit-for-purpose solution.
R-064 | The Bidder shall submit, as part of its Technical Bid, a preliminary Need Assessment Note for the proposed BSL-3 Laboratory at AIIMS Patna, based on the information provided in this RFP, the existing building details, indicative laboratory activities, proposed equipment profile, applicable biosafety requirements, and the Bidder’s professional understanding of similar high-containment laboratory facilities. | 19 | 2.2 (i) | Submission logistics | Submit a preliminary Need Assessment Note as part of the Technical Bid. | Yes |  |  |  | (i) The Bidder shall submit, as part of its Technical Bid, a preliminary Need Assessment Note for the proposed BSL-3 Laboratory at AIIMS Patna, based on the information provided in this RFP, the existing building details, indicative laboratory activities, proposed equipment profile, applicable biosafety requirements, and the Bidder’s professional understanding of similar high-containment laboratory facilities.
R-065 | The Need Assessment shall not be a mere reproduction of the RFP provisions. It shall reflect the Bidder’s independent professional assessment of what is required to convert the identified existing building space into a safe, compliant, functional, maintainable, and certification-oriented BSL-3 laboratory facility. | 19 | 2.2 (ii) | Mandatory | Ensure the Need Assessment reflects an independent professional assessment and is not a mere reproduction of RFP provisions. | Yes |  |  |  | The Need Assessment shall not be a mere reproduction of the RFP provisions. It shall reflect the Bidder’s independent professional assessment of what is required to convert the identified existing building space into a safe, compliant, functional, maintainable, and certification-oriented BSL-3 laboratory facility.
R-066 | The Need Assessment Note shall, at minimum, cover the Bidder’s assessment of functional laboratory requirements, BSL-3 and associated BSL-2/support area requirements, personnel/material/sample/waste workflow, containment zoning, pressure cascade requirements, HVAC and HEPA filtration needs, utility and power redundancy requirements, decontamination and waste management needs, equipment integration requirements, access control and security needs, emergency and safety provisions, validation and certification requirements, and key risks requiring attention during design and execution. | 19 | 2.2 (iii) | Mandatory | Include the specified minimum content in the Need Assessment Note. | Yes |  |  |  | (iii) The Need Assessment Note shall, at minimum, cover the Bidder’s assessment of functional laboratory requirements, BSL-3 and associated BSL-2/support area requirements, personnel/material/sample/waste workflow, containment zoning, pressure cascade requirements, HVAC and HEPA filtration needs, utility and power redundancy requirements, decontamination and waste management needs, equipment integration requirements, access control and security needs, emergency and safety provisions, validation and certification requirements, and key risks requiring attention during design and execution.
R-067 | The Bidder shall also identify any additional requirement, gap, constraint, assumption, interface issue, or clarification which, in its professional opinion, may affect design development, tender preparation, construction execution, commissioning, validation, certification, operation, maintenance, or long-term compliance of the facility. | 19 | 2.2 (iv) | Mandatory | Identify and mention any additional requirements, gaps, constraints, assumptions, interface issues, or clarifications in the Need Assessment Note. | Yes |  |  |  | (iv) The Bidder shall also identify any additional requirement, gap, constraint, assumption, interface issue, or clarification which, in its professional opinion, may affect design development, tender preparation, construction execution, commissioning, validation, certification, operation, maintenance, or long-term compliance of the facility.
R-068 | Where any information provided by AIIMS Patna is considered indicative, insufficient, inconsistent, or requiring verification, the Bidder shall clearly mention the same in the Need Assessment Note. | 19 | 2.2 (iv) | Mandatory | Clearly mention in the Need Assessment Note any AIIMS Patna information considered indicative, insufficient, inconsistent, or requiring verification. | Yes |  |  |  | Where any information provided by AIIMS Patna is considered indicative, insufficient, inconsistent, or requiring verification, the Bidder shall clearly mention the same in the Need Assessment Note.
R-069 | The fundamental philosophy underlying the design of the BSL-3 Laboratory at AIIMS Patna shall be to create a safe, compliant, functional, maintainable, validation-supportive and certification-ready high-containment laboratory facility that provides comprehensive, multi-layered protection to laboratory personnel, support staff, the institution, the community and the environment from exposure to high risk biological agents handled within the facility. | 19 | 2.3 (i) | Mandatory | Design the BSL-3 Laboratory based on the specified fundamental philosophy. | Yes |  |  |  | (i) The fundamental philosophy underlying the design of the BSL-3 Laboratory at AIIMS Patna shall be to create a safe, compliant, functional, maintainable, validation-supportive and certification-ready high-containment laboratory facility that provides comprehensive, multi-layered protection to laboratory personnel, support staff, the institution, the community and the environment from exposure to high risk biological agents handled within the facility.
R-070 | The A&E Consultant shall therefore develop the design after proper assessment of the existing building, available space, structural and service constraints, utility interfaces, equipment movement requirements, access conditions, maintainability requirements and regulatory compliance obligations. | 20 | 2.3 (ii) | Mandatory | Develop the design after proper assessment of the existing building and other specified factors. | Yes |  |  |  | The A&E Consultant shall therefore develop the design after proper assessment of the existing building, available space, structural and service constraints, utility interfaces, equipment movement requirements, access conditions, maintainability requirements and regulatory compliance obligations.
R-071 | The design shall not be treated merely as an interior fit-out, but as an integrated high-containment laboratory system. | 20 | 2.3 (ii) | Mandatory | Treat the design as an integrated high-containment laboratory system, not merely an interior fit-out. | Yes |  |  |  | The design shall not be treated merely as an interior fit-out, but as an integrated high-containment laboratory system.
R-072 | The design shall incorporate reliable, testable and maintainable containment measures proportionate to the nature and level of risk. | 20 | 2.4 | Mandatory | Incorporate reliable, testable, and maintainable containment measures proportionate to risk. | Yes |  |  |  | The design shall incorporate reliable, testable and maintainable containment measures proportionate to the nature and level of risk.
R-073 | The design shall ensure that: All work involving biological agents is carried out within appropriately selected, located, installed and certified biological safety cabinets or other containment equipment, as required by risk assessment and applicable guidelines. | 20 | 2.4 (a) (i) | Mandatory | Ensure all work involving biological agents is carried out within appropriately selected, located, installed, and certified biological safety cabinets or other containment equipment. | Yes |  |  |  | (i) All work involving biological agents is carried out within appropriately selected, located, installed and certified biological safety cabinets or other containment equipment, as required by risk assessment and applicable guidelines;
R-074 | The design shall ensure that: The laboratory environment itself maintains appropriate negative pressure relationship with respect to adjacent non-containment areas, thereby creating inward airflow and preventing escape of potentially contaminated air. | 20 | 2.4 (a) (ii) | Mandatory | Ensure the laboratory environment maintains appropriate negative pressure relative to adjacent non-containment areas. | Yes |  |  |  | (ii) The laboratory environment itself maintains appropriate negative pressure relationship with respect to adjacent non-containment areas, thereby creating inward airflow and preventing escape of potentially contaminated air;
R-075 | The design shall ensure that: Air movement, pressure cascade, door interlocks, airflow paths and room relationships are must be planned to support containment and minimize cross-contamination risk. | 20 | 2.4 (a) (iii) | Mandatory | Plan air movement, pressure cascade, door interlocks, airflow paths, and room relationships to support containment and minimize cross-contamination risk. | Yes |  |  |  | (iii) Air movement, pressure cascade, door interlocks, airflow paths and room relationships are must be planned to support containment and minimize cross-contamination risk;
R-076 | The design shall ensure that: All exhaust air and other relevant air streams shall be treated through suitable HEPA filtration and containment-oriented engineering systems, as applicable. | 20 | 2.4 (a) (iv) | Mandatory | Treat all exhaust air and relevant air streams through suitable HEPA filtration and containment-oriented engineering systems. | Yes |  |  |  | (iv) All exhaust air and other relevant air streams shall be treated through suitable HEPA filtration and containment-oriented engineering systems, as applicable.
R-077 | UVGI may also be considered as a supplementary disinfection provision in HVAC/exhaust/air-treatment systems, wherever justified by biosafety expert & biosafety risk assessment and approved design philosophy; however, UVGI shall not be treated as a substitute for HEPA filtration, validated decontamination, cleaning, disinfection, commissioning or certification requirements. | 20 | 2.4 (a) (iv) | Desirable | Consider UVGI as a supplementary disinfection provision if justified by biosafety expert & risk assessment and approved design philosophy, but not as a substitute for other requirements. | Yes |  |  |  | UVGI may also be considered as a supplementary disinfection provision in HVAC/exhaust/air-treatment systems, wherever justified by biosafety expert & biosafety risk assessment and approved design philosophy; however, UVGI shall not be treated as a substitute for HEPA filtration, validated decontamination, cleaning, disinfection, commissioning or certification requirements.
R-078 | The design shall ensure that: The layout must support correct use of PPE, controlled entry and exit, donning and doffing, shower / change procedures, emergency response and decontamination processes. | 20 | 2.4 (a) (v) | Mandatory | Design the layout to support correct use of PPE, controlled entry/exit, donning/doffing, shower/change procedures, emergency response, and decontamination processes. | Yes |  |  |  | (v) The layout must support correct use of PPE, controlled entry and exit, donning and doffing, shower / change procedures, emergency response and decontamination processes;
R-079 | The design shall ensure that: Emergency systems, alarms, communication systems, eyewash / safety shower provisions, spill response provisions and escape routes are appropriately planned and accessible. | 21 | 2.4 (a) (vi) | Mandatory | Plan and make accessible emergency systems, alarms, communication systems, eyewash/safety shower provisions, spill response provisions, and escape routes. | Yes |  |  |  | (vi) Emergency systems, alarms, communication systems, eyewash / safety shower provisions, spill response provisions and escape routes are appropriately planned and accessible; and
R-080 | The design shall ensure that: The design supports occupational health, incident response and laboratory-acquired infection prevention measures through appropriate infrastructure, documentation interfaces and operational planning inputs. | 21 | 2.4 (a) (vii) | Mandatory | Design to support occupational health, incident response, and laboratory-acquired infection prevention measures. | Yes |  |  |  | (vii) The design supports occupational health, incident response and laboratory-acquired infection prevention measures through appropriate infrastructure, documentation interfaces and operational planning inputs.
R-081 | The design shall ensure that: The BSL-3 containment zone functions as a secondary containment barrier through sealed, cleanable and maintainable construction. | 21 | 2.4 (b) (i) | Mandatory | Ensure the BSL-3 containment zone functions as a secondary containment barrier through sealed, cleanable, and maintainable construction. | Yes |  |  |  | (i) The BSL-3 containment zone functions as a secondary containment barrier through sealed, cleanable and maintainable construction;
R-082 | The design shall ensure that: Penetrations, service entries, ducts, conduits and interfaces are properly sealed, coordinated and suitable for containment requirements. | 21 | 2.4 (b) (ii) | Mandatory | Ensure penetrations, service entries, ducts, conduits, and interfaces are properly sealed, coordinated, and suitable for containment. | Yes |  |  |  | (ii) Penetrations, service entries, ducts, conduits and interfaces are properly sealed, coordinated and suitable for containment requirements;
R-083 | The design shall ensure that: All materials leaving the containment area, including solid waste, liquid waste, reusable materials, equipment and samples, are routed through defined and appropriate decontamination / transfer processes. | 21 | 2.4 (b) (iii) | Mandatory | Route all materials leaving the containment area through defined and appropriate decontamination/transfer processes. | Yes |  |  |  | (iii) All materials leaving the containment area, including solid waste, liquid waste, reusable materials, equipment and samples, are routed through defined and appropriate decontamination / transfer processes;
R-084 | The design shall ensure that: Airflow, exhaust, effluent, waste and decontamination systems are planned to prevent uncontrolled release to non-containment areas or the environment. | 21 | 2.4 (b) (iv) | Mandatory | Plan airflow, exhaust, effluent, waste, and decontamination systems to prevent uncontrolled release. | Yes |  |  |  | (iv) Airflow, exhaust, effluent, waste and decontamination systems are planned to prevent uncontrolled release to non-containment areas or the environment;
R-085 | The design shall ensure that: Access to the BSL-3 zone is restricted, controlled, monitored and supported by suitable biosecurity provisions. | 21 | 2.4 (b) (v) | Mandatory | Ensure access to the BSL-3 zone is restricted, controlled, monitored, and supported by suitable biosecurity provisions. | Yes |  |  |  | (v) Access to the BSL-3 zone is restricted, controlled, monitored and supported by suitable biosecurity provisions;
R-086 | The design shall ensure that: Fail-safe and redundancy considerations are incorporated for critical containment systems, wherever required. | 21 | 2.4 (b) (vi) | Mandatory | Incorporate fail-safe and redundancy considerations for critical containment systems wherever required. | Yes |  |  |  | (vi) Fail-safe and redundancy considerations are incorporated for critical containment systems, wherever required; and
R-087 | The design shall ensure that: Monitoring and alarm systems are integrated to enable early detection of containment breaches, pressure deviation, equipment failure or operational anomalies. | 21 | 2.4 (b) (vii) | Mandatory | Integrate monitoring and alarm systems to enable early detection of containment breaches, pressure deviation, equipment failure, or operational anomalies. | Yes |  |  |  | (vii) Monitoring and alarm systems are integrated to enable early detection of containment breaches, pressure deviation, equipment failure or operational anomalies.
R-088 | The A&E Consultant shall develop the design based on the following containment pillars: Physical and engineering containment, Safety equipment and primary containment, Facility design and secondary containment, Procedural support through design, Workflow-based design philosophy, Biosafety risk assessment as basis of design, Integration of engineering systems, Redundancy, reliability and fail-safe design, Maintainability and operational sustainability, Biosafety culture and design philosophy, Compliance, validation and certification readiness, and Deliverable-oriented design philosophy. | 21 | 2.5 | Mandatory | Develop the design based on the specified integrated containment pillars. | Yes |  |  |  | The A&E Consultant shall develop the design based on the following containment pillars:
R-089 | The design shall ensure that the layout, materials, doors, services, utilities and equipment interfaces support containment, cleaning, disinfection, fumigation / decontamination, maintenance and validation. | 21 | 2.5 (a) | Mandatory | Ensure the layout, materials, doors, services, utilities, and equipment interfaces support containment, cleaning, disinfection, fumigation/decontamination, maintenance, and validation. | No — check |  |  |  | The design shall ensure that the layout, materials, doors, services, utilities and equipment interfaces support containment, cleaning, disinfection, fumigation / decontamination, maintenance and validation.
R-090 | The design shall accommodate appropriate biological safety cabinets, containment devices, autoclaves, pass-through systems, decontamination equipment, emergency equipment and other safety systems required for the intended BSL-3 laboratory activities. | 22 | 2.5 (b) | Mandatory | Accommodate appropriate safety equipment and systems as listed. | Yes |  |  |  | The design shall accommodate appropriate biological safety cabinets, containment devices, autoclaves, pass-through systems, decontamination equipment, emergency equipment and other safety systems required for the intended BSL-3 laboratory activities.
R-091 | The selection, placement and utility integration of such equipment shall be coordinated with room layout, airflow pattern, user workflow, maintenance access, certification requirements and operational safety. | 22 | 2.5 (b) | Mandatory | Coordinate the selection, placement, and utility integration of equipment with room layout, airflow pattern, user workflow, maintenance access, certification requirements, and operational safety. | Yes |  |  |  | The selection, placement and utility integration of such equipment shall be coordinated with room layout, airflow pattern, user workflow, maintenance access, certification requirements and operational safety.
R-092 | The facility design shall provide the secondary containment layer required to protect non-containment areas, the institution, the public and the environment. This shall include sealed and cleanable construction, controlled access, negative pressure gradients, suitable HVAC zoning, HEPA-filtered exhaust with suitable supplementary UVGI, waste and effluent treatment provisions, decontamination systems, restricted movement routes, emergency response infrastructure, BMS / EMS monitoring, alarms and validated performance parameters. | 22 | 2.5 (c) | Mandatory | Design the facility to provide the secondary containment layer, including the specified features. | Yes |  |  |  | The facility design shall provide the secondary containment layer required to protect non-containment areas, the institution, the public and the environment. This shall include sealed and cleanable construction, controlled access, negative pressure gradients, suitable HVAC zoning, HEPA-filtered exhaust with suitable supplementary UVGI, waste and effluent treatment provisions, decontamination systems, restricted movement routes, emergency response infrastructure, BMS / EMS monitoring, alarms and validated performance parameters.
R-093 | The facility design shall support such procedures by ensuring logical workflow, minimized cross-traffic, proper entry and exit sequence, clean-to-dirty movement, defined sample movement, defined waste movement, accessible decontamination systems, adequate storage, clear signage, communication systems, data management support, asset / inventory interface, and suitable provisions for training, maintenance and emergency response. | 22 | 2.5 (d) | Mandatory | Design the facility to support procedural containment by ensuring the listed features. | Yes |  |  |  | The facility design shall support such procedures by ensuring logical workflow, minimized cross-traffic, proper entry and exit sequence, clean-to-dirty movement, defined sample movement, defined waste movement, accessible decontamination systems, adequate storage, clear signage, communication systems, data management support, asset / inventory interface, and suitable provisions for training, maintenance and emergency response.
R-094 | The A&E Consultant shall design the BSL-3 facility on the basis of clearly defined and approved workflows. | 22 | 2.5 (e) | Mandatory | Design the BSL-3 facility based on clearly defined and approved workflows. | Yes |  |  |  | The A&E Consultant shall design the BSL-3 facility on the basis of clearly defined and approved workflows.
R-095 | At minimum, the design shall address: Personnel entry, gowning, working, shower / exit and emergency exit flow; Sample receipt, movement, processing, storage, rejection and disposal flow, sterilizable materials flow; Sample identification, traceability, movement, segregation, testing, reporting of results, retention, storage and final disposal, with appropriate measures to prevent mix-up, cross-contamination and loss of sample integrity; Material entry, consumable movement, equipment movement and decontamination flow; Biomedical waste, solid waste, liquid waste and reusable item movement; Clean and contaminated route separation, wherever applicable; Repair & maintenance access without compromising containment; and Emergency response and evacuation routes. | 22 | 2.5 (e) (i)-(viii) | Mandatory | Address the listed workflow aspects in the design. | Yes |  |  |  | At minimum, the design shall address: (i) Personnel entry, gowning, working, shower / exit and emergency exit flow; (ii) Sample receipt, movement, processing, storage, rejection and disposal flow, sterilizable materials flow; (iii) Sample identification, traceability, movement, segregation, testing, reporting of results, retention, storage and final disposal, with appropriate measures to prevent mix-up, cross-contamination and loss of sample integrity. (iv) Material entry, consumable movement, equipment movement and decontamination flow; (v) Biomedical waste, solid waste, liquid waste and reusable item movement; (vi) Clean and contaminated route separation, wherever applicable; (vii) Repair & maintenance access without compromising containment; and (viii) Emergency response and evacuation routes.
R-096 | The design shall demonstrate that workflows are coordinated with room zoning, pressure cascade, access control, BMS / EMS, HVAC zoning, decontamination systems, sample handling, waste management and validation & certification requirements. | 23 | 2.5 (e) (ix) | Mandatory | Demonstrate that workflows are coordinated with the listed systems and requirements. | Yes |  |  |  | (ix) The design shall demonstrate that workflows are coordinated with room zoning, pressure cascade, access control, BMS / EMS, HVAC zoning, decontamination systems, sample handling, waste management and validation & certification requirements.
R-097 | The A&E Consultant shall ensure that the design is driven by biosafety risk assessment and not merely by spatial arrangement. | 23 | 2.5 (f) | Mandatory | Ensure the design is driven by biosafety risk assessment. | Yes |  |  |  | The A&E Consultant shall ensure that the design is driven by biosafety risk assessment and not merely by spatial arrangement.
R-098 | The design shall consider the nature of laboratory activities, biological agents, aerosol risk, equipment profile, user operations, decontamination needs, waste generation, sample handling, emergency scenarios, repair & maintenance requirements and regulatory expectations. | 23 | 2.5 (f) | Mandatory | Consider the listed factors in the design. | Yes |  |  |  | The design shall consider the nature of laboratory activities, biological agents, aerosol risk, equipment profile, user operations, decontamination needs, waste generation, sample handling, emergency scenarios, repair & maintenance requirements and regulatory expectations.
R-099 | The Biosafety Expert / Consultant shall be involved in developing and reviewing the biosafety basis of design, containment zoning, workflow strategy, pressure zoning philosophy, validation approach, certification, and compliance matrix. | 23 | 2.5 (f) | Mandatory | Involve the Biosafety Expert/Consultant in developing and reviewing the specified design aspects. | Yes |  |  |  | The Biosafety Expert / Consultant shall be involved in developing and reviewing the biosafety basis of design, containment zoning, workflow strategy, pressure zoning philosophy, validation approach, certification, and compliance matrix.
R-100 | The design philosophy shall require full integration of architectural, structural, HVAC, electrical, ELV, BMS / EMS, plumbing, drainage, fire safety, gas systems, laboratory utilities, decontamination systems, cleanroom features, access control, CCTV, communication systems, equipment utilities, BIM, CFD, commissioning and validation requirements. | 23 | 2.5 (g) | Mandatory | Ensure full integration of all listed engineering systems in the design. | Yes |  |  |  | The design philosophy shall require full integration of architectural, structural, HVAC, electrical, ELV, BMS / EMS, plumbing, drainage, fire safety, gas systems, laboratory utilities, decontamination systems, cleanroom features, access control, CCTV, communication systems, equipment utilities, BIM, CFD, commissioning and validation requirements.
R-101 | The A&E Consultant shall ensure that each discipline is coordinated and that the final design is execution-ready, tender-ready, contractor-usable and validation & certification supportive. | 23 | 2.5 (g) | Mandatory | Ensure coordination of disciplines and that the final design is execution-ready, tender-ready, contractor-usable, and validation & certification supportive. | Yes |  |  |  | The A&E Consultant shall ensure that each discipline is coordinated and that the final design is execution-ready, tender-ready, contractor-usable and validation & certification supportive.
R-102 | The BSL-3 facility shall be designed with due consideration of reliability, redundancy and fail-safe operation of critical containment systems. | 23 | 2.5 (h) | Mandatory | Design the BSL-3 facility with due consideration of reliability, redundancy, and fail-safe operation of critical containment systems. | Yes |  |  |  | The BSL-3 facility shall be designed with due consideration of reliability, redundancy and fail-safe operation of critical containment systems.
R-103 | The A&E Consultant shall identify critical systems such as HVAC, exhaust, HEPA filtration, pressure monitoring, access control, emergency power, alarms, autoclaves, decontamination systems, BMS / EMS and other essential utilities, and shall recommend appropriate redundancy, backup, monitoring and emergency provisions based on risk assessment, applicable guidelines and operational requirements etc. | 23 | 2.5 (h) | Mandatory | Identify critical systems and recommend appropriate redundancy, backup, monitoring, and emergency provisions. | Yes |  |  |  | The A&E Consultant shall identify critical systems such as HVAC, exhaust, HEPA filtration, pressure monitoring, access control, emergency power, alarms, autoclaves, decontamination systems, BMS / EMS and other essential utilities, and shall recommend appropriate redundancy, backup, monitoring and emergency provisions based on risk assessment, applicable guidelines and operational requirements etc.
R-104 | The design shall ensure that the BSL-3 facility can be operated, maintained, cleaned, serviced, tested, validated and re-certified without compromising containment. | 23 | 2.5 (i) | Mandatory | Ensure the design allows the BSL-3 facility to be operated, maintained, cleaned, serviced, tested, validated, and re-certified without compromising containment. | Yes |  |  |  | The design shall ensure that the BSL-3 facility can be operated, maintained, cleaned, serviced, tested, validated and re-certified without compromising containment.
R-105 | Maintenance access, service routing, filter replacement strategy, equipment access, utility isolation, drainage, calibration points, monitoring points, ceiling / wall access panels, plant room layout and spare capacity shall be considered at the design stage. | 23 | 2.5 (i) | Mandatory | Consider the listed aspects at the design stage. | Yes |  |  |  | Maintenance access, service routing, filter replacement strategy, equipment access, utility isolation, drainage, calibration points, monitoring points, ceiling / wall access panels, plant room layout and spare capacity shall be considered at the design stage.
R-106 | The design shall avoid arrangements that are difficult to operate, unsafe to maintain or likely to fail during validation/certification. | 23 | 2.5 (i) | Mandatory | Avoid design arrangements that are difficult to operate, unsafe to maintain, or likely to fail during validation/certification. | Yes |  |  |  | The design shall avoid arrangements that are difficult to operate, unsafe to maintain or likely to fail during validation/certification.
R-107 | The design shall reinforce safe behaviour, operational discipline and containment awareness by: Making containment features, pressure status, alarms and safety systems visible and understandable to users; Designing workspaces that facilitate safe work practices rather than hinder them; Providing adequate working space around biological safety cabinets and critical equipment; Organizing workflow to minimize unnecessary movement and cross-contamination; Incorporating redundancy and alarms in critical safety systems; Integrating monitoring and surveillance systems to continuously verify facility performance; Designing communication and alert systems to notify personnel of deviations from required operating parameters; Creating clean, organized, accessible and maintainable work environments; and Locating emergency response infrastructure such as eyewash stations, safety showers, emergency exits and spill response provisions appropriately. | 24 | 2.5 (j) (i)-(ix) | Mandatory | Design to reinforce safe behavior, operational discipline, and containment awareness by incorporating the listed features. | Yes |  |  |  | The design shall reinforce safe behaviour, operational discipline and containment awareness by: (i) Making containment features, pressure status, alarms and safety systems visible and understandable to users; (ii) Designing workspaces that facilitate safe work practices rather than hinder them; (iii) Providing adequate working space around biological safety cabinets and critical equipment; (iv) Organizing workflow to minimize unnecessary movement and cross-contamination; (v) Incorporating redundancy and alarms in critical safety systems; (vi) Integrating monitoring and surveillance systems to continuously verify facility performance; (vii) Designing communication and alert systems to notify personnel of deviations from required operating parameters; (viii) Creating clean, organized, accessible and maintainable work environments; and (ix) Locating emergency response infrastructure such as eyewash stations, safety showers, emergency exits and spill response provisions appropriately.
R-108 | The design shall be developed with a view to compliance, validation and certification readiness from the beginning. | 24 | 2.5 (k) | Mandatory | Develop the design with a view to compliance, validation, and certification readiness from the beginning. | Yes |  |  |  | The design shall be developed with a view to compliance, validation and certification readiness from the beginning.
R-109 | The A&E Consultant shall prepare design deliverables in a manner that supports review by AIIMS Patna, statutory authorities, biosafety reviewers, commissioning agencies, validation teams and certification-related stakeholders. | 24 | 2.5 (k) | Mandatory | Prepare design deliverables to support review by specified stakeholders. | Yes |  |  |  | The A&E Consultant shall prepare design deliverables in a manner that supports review by AIIMS Patna, statutory authorities, biosafety reviewers, commissioning agencies, validation teams and certification-related stakeholders.
R-110 | The Consultant shall prepare necessary compliance matrices, design basis documents, commissioning requirements, validation support documents, testing requirements and handover documentation as and wherever required. | 24 | 2.5 (k) | Mandatory | Prepare necessary compliance matrices, design basis documents, commissioning requirements, validation support documents, testing requirements, and handover documentation as required. | Yes |  |  |  | The Consultant shall prepare necessary compliance matrices, design basis documents, commissioning requirements, validation support documents, testing requirements and handover documentation as and wherever required.
R-111 | The A&E Consultant shall translate the above philosophy into measurable and reviewable deliverables, including but not limited to site assessment, need assessment, biosafety basis of design, containment zoning plan, workflow diagrams, pressure cascade plan, AHU zoning strategy, room data sheets, equipment layout, utility matrix, coordinated drawings, BIM / CFD outputs, technical specifications, BOQ, cost estimates, commissioning matrix, validation matrix, certification matrix compliance matrix and as-built / handover documentation. | 24 | 2.5 (l) | Mandatory | Translate the design philosophy into measurable and reviewable deliverables, including the listed items. | Yes |  |  |  | The A&E Consultant shall translate the above philosophy into measurable and reviewable deliverables, including but not limited to site assessment, need assessment, biosafety basis of design, containment zoning plan, workflow diagrams, pressure cascade plan, AHU zoning strategy, room data sheets, equipment layout, utility matrix, coordinated drawings, BIM / CFD outputs, technical specifications, BOQ, cost estimates, commissioning matrix, validation matrix, certification matrix compliance matrix and as-built / handover documentation.
R-112 | The A&E Consultant shall apply its professional expertise, biosafety expertise & understanding, engineering judgment and experience in high-containment / laboratory facilities to develop a complete, coordinated and fit-for-purpose design. | 24 | 2.5 (m) | Mandatory | Apply professional expertise, biosafety expertise & understanding, engineering judgment, and experience to develop a complete, coordinated, and fit-for-purpose design. | Yes |  |  |  | The A&E Consultant shall apply its professional expertise, biosafety expertise & understanding, engineering judgment and experience in high-containment / laboratory facilities to develop a complete, coordinated and fit-for-purpose design.
R-113 | The Consultant shall not merely reproduce the indicative requirements of this RFP, but shall identify | 24 | 2.5 (m) | Mandatory | Do not merely reproduce indicative RFP requirements, but identify additional needs. | Yes |  |  |  | The Consultant shall not merely reproduce the indicative requirements of this RFP, but shall identify
R-114 | The Consultant shall verify and convert the preliminary URS into a controlled Final URS through stakeholder consultation, site verification, equipment-utility reconciliation and written closure of assumptions. | 25 | 2.7 (ii) | Mandatory | Consultant must verify and convert the preliminary URS into a controlled Final URS. | Yes |  |  |  | The Consultant shall verify and convert the preliminary URS into a controlled Final URS through stakeholder consultation, site verification, equipment-utility reconciliation and written closure of assumptions.
R-115 | The final URS shall become the traceable baseline for the Basis of Design, design reviews, BOQ, specifications, testing and validation. | 25 | 2.7 (ii) | Mandatory | The final URS must serve as the traceable baseline for subsequent design and validation activities. | Yes |  |  |  | The final URS shall become the traceable baseline for the Basis of Design, design reviews, BOQ, specifications, testing and validation.
R-116 | Any incompatibility or material gap between the baseline minimum requirements and the site, approved laboratory activities, equipment list, risk assessment and applicable laws shall be reported and recorded and provided to AIIMS Patna with a recommended decision. | 25 | 2.8 (ii) | Mandatory | Bidder must report any incompatibility or material gap and provide a recommended decision to AIIMS Patna. | Yes |  |  |  | Any incompatibility or material gap shall be reported and recorded and provided to AIIMS Patna with a recommended decision.
R-117 | The consultant shall submit a coordinated basis of design covering the approved URS, biosafety risk basis, room data, containment zoning, pressure relationships, HVAC philosophy, redundancy, HEPA strategy, utilities, EDS/ETP and autoclave interfaces, access control, BMS/EMS, emergency modes, commissioning, validation and certification-support assumptions. | 25 | 2.9 (i) | Mandatory | Consultant must submit a coordinated basis of design. | Yes |  |  |  | The consultant shall submit a coordinated basis of design covering the approved URS, biosafety risk basis, room data, containment zoning, pressure relationships, HVAC philosophy, redundancy, HEPA strategy, utilities,
R-118 | The basis of design shall include a requirement-to-design traceability matrix, a design-assumption register, a system-interface matrix and written sign-off/comments of the Biosafety Expert and the discipline leads. | 26 | 2.9 (ii) | Mandatory | The basis of design must include specific documentation: traceability matrix, assumption register, interface matrix, and written sign-off/comments. | Yes |  |  |  | The basis of design shall include a requirement-to-design traceability matrix, a design-assumption register, a system-interface matrix and written sign-off/comments of the Biosafety Expert and the discipline leads.
R-119 | No subsequent stage shall silently depart from an approved Basis of Design. | 26 | 2.9 (ii) | Mandatory | Subsequent stages must not deviate from an approved Basis of Design without explicit acknowledgment. | Yes |  |  |  | No subsequent stage shall silently depart from an approved Basis of Design.
R-120 | The Bidder shall, before submission of its Bid, independently examine and verify the existing infrastructure, site surroundings and requirement, access conditions, building configuration, available spaces, floor levels, floor heights, structural conditions, service routing possibilities, utility availability, drainage arrangement, electrical supply, water supply, ventilation possibilities, equipment movement constraints, safety and emergency access, and all other site-specific conditions relevant to establishment of the BSL-3 Laboratory. | 29 | 3.1 (vi) | Mandatory | Bidder must independently examine and verify site conditions before bid submission. | Yes |  |  |  | The Bidder shall, before submission of its Bid, independently examine and verify the existing infrastructure, site surroundings and requirement, access conditions, building configuration, available spaces, floor levels, floor heights, structural conditions, service routing possibilities, utility availability, drainage arrangement, electrical supply, water supply, ventilation possibilities, equipment movement constraints, safety and emergency access, and all other site-specific conditions relevant to establishment of the BSL-3 Laboratory.
R-121 | The Bidder shall not rely solely on the indicative drawings, maps, figures, coordinates or information provided in this section. | 29 | 3.1 (vii) | Mandatory | Bidder must not rely solely on the provided indicative information. | Yes |  |  |  | The Bidder shall not rely solely on the indicative drawings, maps, figures, coordinates or information provided in this section.
R-122 | Any discrepancy, insufficiency, inconsistency, uncertainty or site constraint noticed by the Bidder shall be clearly brought out in the Technical Bid, along with the Bidder’s professional assessment, assumptions, risks and suggested approach for retrofitting and integration of BSL-3 systems. | 29 | 3.1 (vii) | Mandatory | Bidder must clearly state any discrepancies or constraints in the Technical Bid, including assessment, assumptions, risks, and suggested approach. | Yes |  |  |  | Any discrepancy, insufficiency, inconsistency, uncertainty or site constraint noticed by the Bidder shall be clearly brought out in the Technical Bid, along with the Bidder’s professional assessment, assumptions, risks and suggested approach for retrofitting and integration of BSL-3 systems.
R-123 | Submission of Bid shall be deemed to constitute confirmation that the Bidder has understood the site context and has considered the existing infrastructure conditions while preparing its proposal. | 29 | 3.1 (viii) | Mandatory | Bid submission implies confirmation of understanding site context and existing infrastructure. | Yes |  |  |  | Submission of Bid shall be deemed to constitute confirmation that the Bidder has understood the site context and has considered the existing infrastructure conditions while preparing its proposal.
R-124 | After award, the selected A&E Consultant shall undertake detailed site verification, measurement, infrastructure assessment, utility assessment, retrofitting assessment and existing building review, and shall identify all modifications, strengthening, service upgrades, containment-related interventions and engineering provisions required to convert the existing building into a compliant, safe, functional, maintainable, validation-supportive and certification-ready BSL-3 Laboratory facility. | 29 | 3.1 (viii) | Mandatory | After award, the A&E Consultant must undertake detailed site verification and assessment, and identify all necessary modifications. | Yes |  |  |  | After award, the selected A&E Consultant shall undertake detailed site verification, measurement, infrastructure assessment, utility assessment, retrofitting assessment and existing building review, and shall identify all modifications, strengthening, service upgrades, containment-related interventions and engineering provisions required to convert the existing building into a compliant, safe, functional, maintainable, validation-supportive and certification-ready BSL-3 Laboratory facility.
R-125 | The Bidder shall examine the available information and, wherever necessary, may consider the same while preparing its Technical Proposal, methodology, site assessment approach, retrofitting approach and design strategy. | 30 | 3.2 (v) | Mandatory | Bidder must examine available information and consider it when preparing the Technical Proposal. | Yes |  |  |  | The Bidder shall examine the available information and, wherever necessary, may consider the same while preparing its Technical Proposal, methodology, site assessment approach, retrofitting approach and design strategy.
R-126 | Submission of Proposal shall be deemed to constitute that the Bidder has understood the indicative nature of the information and has made due allowance for site verification, existing building assessment, infrastructure assessment and design development requirements. | 30 | 3.2 (v) | Mandatory | Proposal submission implies understanding of indicative information and allowance for site verification and assessments. | Yes |  |  |  | Submission of Proposal shall be deemed to constitute that the Bidder has understood the indicative nature of the information and has made due allowance for site verification, existing building assessment, infrastructure assessment and design development requirements.
R-127 | After award, the selected A&E Consultant, shall undertake detailed site verification, measurement, existing building assessment, structural and serviceability review, utility assessment, retrofitting assessment, service routing assessment, equipment movement assessment and feasibility review for establishment of the BSL-3 Laboratory. | 30 | 3.2 (vi) | Mandatory | After award, the A&E Consultant must undertake detailed site verification and various assessments for the BSL-3 Laboratory. | Yes |  |  |  | After award, the selected A&E Consultant, shall undertake detailed site verification, measurement, existing building assessment, structural and serviceability review, utility assessment, retrofitting assessment, service routing assessment, equipment movement assessment and feasibility review for establishment of the BSL-3 Laboratory.
R-128 | The A&E Consultant shall identify all modifications, retrofitting works, boundary wall requirement, landscaping with lighting, signage requirement, building façade, strengthening requirements, service upgrades, containment-related interventions, utility provisions and engineering integrations required for development of a safe, functional, maintainable, validation-supportive and certification-ready BSL-3 facility. | 30 | 3.2 (vi) | Mandatory | The A&E Consultant must identify all required modifications and integrations for the BSL-3 facility. | Yes |  |  |  | The A&E Consultant shall identify all modifications, retrofitting works, boundary wall requirement, landscaping with lighting, signage requirement, building façade, strengthening requirements, service upgrades, containment-related interventions, utility provisions and engineering integrations required for development of a safe, functional, maintainable, validation-supportive and certification-ready BSL-3 facility.
R-129 | Such drawings and records shall not be treated as final, exhaustive or conclusive and shall not relieve the Bidder / A&E Consultant from the responsibility of independent site verification, detailed assessment and preparation of a coordinated design solution in accordance with the scope of services, applicable guidelines, actual site conditions and AIIMS Patna’s approved requirements. | 31 | 3.2 (vii) | Mandatory | Bidder/A&E Consultant is not relieved from independent site verification, detailed assessment, and design preparation despite provided drawings and records. | Yes |  |  |  | Such drawings and records shall not be treated as final, exhaustive or conclusive and shall not relieve the Bidder / A&E Consultant from the responsibility of independent site verification, detailed assessment and preparation of a coordinated design solution in accordance with the scope of services, applicable guidelines, actual site conditions and AIIMS Patna’s approved requirements.
R-130 | Prospective Bidders intending to visit the project site before submission of their bids may do so by submitting a request through email to bsl3@aiimspatna.org, addressed to Prof. (Dr.) Binod Kumar Pati, for scheduling the site visit. | 31 | 3.2 (viii) | Submission logistics | Bidders wishing to visit the site must submit an email request to bsl3@aiimspatna.org, addressed to Prof. (Dr.) Binod Kumar Pati. | Yes |  |  |  | Prospective Bidders intending to visit the project site before submission of their bids may do so by submitting a request through email to bsl3@aiimspatna.org, addressed to Prof. (Dr.) Binod Kumar Pati, for scheduling the site visit.
R-131 | The site visit shall be at the Bidder's own cost and risk, and no claim arising out of or in connection with such visit shall be entertained by AIIMS Patna. | 31 | 3.2 (viii) | Mandatory | Bidders must bear all costs and risks associated with site visits. | Yes |  |  |  | The site visit shall be at the Bidder's own cost and risk, and no claim arising out of or in connection with such visit shall be entertained by AIIMS Patna.
R-132 | The Bidder shall consider this equipment framework while preparing its Technical Proposal, methodology, space planning approach, zoning concept, workflow concept and infrastructure assessment. | 32 | 4.1 (iii) | Mandatory | Bidder must consider the provided equipment framework when preparing their Technical Proposal. | Yes |  |  |  | The Bidder shall consider this equipment framework while preparing its Technical Proposal, methodology, space planning approach, zoning concept, workflow concept and infrastructure assessment.
R-133 | After award, the A&E Consultant shall use the equipment list as a baseline for developing room layouts, equipment layouts, utility matrix, HVAC load calculations, electrical load assessment, UPS / emergency power requirements, plumbing and drainage requirements, gas / vacuum / compressed air requirements, BMS / EMS integration, access control, equipment movement planning, lift setup, storage planning and maintenance access provisions. | 32 | 4.1 (iii) | Mandatory | After award, the A&E Consultant must use the equipment list as a baseline for detailed design development. | Yes |  |  |  | After award, the A&E Consultant shall use the equipment list as a baseline for developing room layouts, equipment layouts, utility matrix, HVAC load calculations, electrical load assessment, UPS / emergency power requirements, plumbing and drainage requirements, gas / vacuum / compressed air requirements, BMS / EMS integration, access control, equipment movement planning, lift setup, storage planning and maintenance access provisions.
R-134 | Adequate consideration shall be given to equipment footprint, installation requirements, service clearances, operational workflow, clean and contaminated movement, sample handling, waste handling, decontamination requirements, equipment replacement pathway, vibration / noise / heat generation, seismic resistance planning for lab equipment, safety provisions, calibration access and validation / certification support requirements. | 32 | 4.1 (iv) | Mandatory | Design must adequately consider various equipment-related factors. | Yes |  |  |  | Adequate consideration shall be given to equipment footprint, installation requirements, service clearances, operational workflow, clean and contaminated movement, sample handling, waste handling, decontamination requirements, equipment replacement pathway, vibration / noise / heat generation, seismic resistance planning for lab equipment, safety provisions, calibration access and validation / certification support requirements.
R-135 | The design shall ensure that equipment placement and infrastructure integration do not compromise containment, biosafety, ergonomics, maintainability or operational efficiency. | 32 | 4.1 (iv) | Mandatory | Design must ensure equipment placement and integration do not compromise containment, biosafety, ergonomics, maintainability, or operational efficiency. | Yes |  |  |  | The design shall ensure that equipment placement and infrastructure integration do not compromise containment, biosafety, ergonomics, maintainability or operational efficiency.
R-136 | The A&E Consultant shall prepare and submit an equipment layout, equipment utility matrix, equipment interface schedule and equipment integration plan as part of the design deliverables. | 33 | 4.2 (vii) | Mandatory | Prepare and submit an equipment layout, equipment utility matrix, equipment interface schedule and equipment integration plan. | Yes |  |  |  | (vii) The A&E Consultant shall prepare and submit an equipment layout, equipment utility matrix, equipment interface schedule and equipment integration plan as part of the design deliverables.
R-137 | The A&E Consultant shall identify any additional equipment, support system, utility provision or spatial requirement considered necessary for safe, compliant, functional and maintainable operation of the BSL-3 facility with justification for review. | 33 | 4.2 (vii) | Mandatory | Identify any additional equipment, support system, utility provision or spatial requirement with justification for review. | Yes |  |  |  | Any additional equipment, support system, utility provision or spatial requirement considered necessary for safe, compliant, functional and maintainable operation of the BSL-3 facility shall be identified by the A&E Consultant with justification for review.
R-138 | Blank quantities in the issued tender shall be completed or expressly marked “to be confirmed during URS”. | 38 | Note | Submission logistics | Complete blank quantities in the equipment list or mark them as "to be confirmed during URS". | Yes |  |  |  | Note: Blank quantities in the issued tender shall be completed or expressly marked “to be confirmed during URS”.
R-139 | The Consultant shall prepare an Agent–Activity Matrix stating the agent/category, sample condition, procedure, culture or propagation status, aerosol-generating step, volume/concentration, containment control and required approval during the URS stage. | 38 | Note | Mandatory | Prepare an Agent–Activity Matrix during the URS stage. | Yes |  |  |  | During the URS stage, the Consultant shall prepare an Agent–Activity Matrix stating the agent/category, sample condition, procedure, culture or propagation status, aerosol-generating step, volume/concentration, containment control and required approval.
R-140 | All design elements of the proposed facility must demonstrate full compliance with the National Guidelines for the Establishment and Certification of Biosafety Level-3 (BSL-3) Containment Facility, 2024, in addition to other relevant provisions applicable for establishment of BSL-3 Laboratories. | 39 | 5.1 (a) (ii) | Mandatory | Ensure all design elements comply with the National Guidelines for the Establishment and Certification of Biosafety Level-3 (BSL-3) Containment Facility, 2024, and other relevant provisions. | Yes |  |  |  | (ii) All design elements of the proposed facility must demonstrate full compliance with these guideline in addition to other relevant provisions applicable for establishment of BSL-3 Laboratories.
R-141 | The bidder shall ensure that the design, planning, and all related deliverables for the proposed facility are in full compliance with the applicable regulatory guidelines, including any amendments, revisions, or updates issued from time to time by the competent authorities. | 39 | Note | Mandatory | Ensure design, planning, and deliverables comply with applicable regulatory guidelines, including amendments, revisions, or updates. | Yes |  |  |  | Note: The bidder shall ensure that the design, planning, and all related deliverables for the proposed facility are in full compliance with the applicable regulatory guidelines, including any amendments, revisions, or updates issued from time to time by the competent authorities.
R-142 | The design shall comply with the standards and guidelines applicable on the Effective Date. | 39 | 5.1 (a) (iii) | Mandatory | Ensure the design complies with standards and guidelines applicable on the Effective Date. | Yes |  |  |  | (iii) The design shall comply with the standards and guidelines applicable on the Effective Date.
R-143 | Any subsequent amendment, statutory direction or regulatory requirement that materially changes the approved scope, design basis, deliverables, cost, timeline, system capacity or certification pathway shall be processed under the Change Management Procedure as a Change in Law / Change in Guidelines. | 39 | 5.1 (a) (iii) | Mandatory | Process any material changes due to subsequent amendments, statutory directions, or regulatory requirements under the Change Management Procedure. | Yes |  |  |  | Any subsequent amendment, statutory direction or regulatory requirement that materially changes the approved scope, design basis, deliverables, cost, timeline, system capacity or certification pathway shall be processed under the Change Management Procedure as a Change in Law / Change in Guidelines.
R-144 | Clarifications that do not materially affect scope, cost or time shall be incorporated without additional claim. | 39 | 5.1 (a) (iii) | Mandatory | Incorporate clarifications that do not materially affect scope, cost or time without additional claim. | Yes |  |  |  | Clarifications that do not materially affect scope, cost or time shall be incorporated without additional claim.
R-145 | The design must provide appropriate infrastructure to support procedures involving recombinant DNA technology and handling of genetically engineered organisms as per Regulations and Guidelines for Recombinant DNA Research and Bio-containment. | 40 | 5.1 (v) | Mandatory | Provide appropriate infrastructure in the design to support recombinant DNA technology and genetically engineered organism handling. | Yes |  |  |  | The design must provide appropriate infrastructure to support these procedures.
R-146 | The facility design must support the IBSC in its administrative functions including risk assessment, SOP development, and monitoring of facility operations. | 40 | 5.1 (vi) | Mandatory | Ensure the facility design supports the IBSC's administrative functions. | Yes |  |  |  | The facility design must support the IBSC in its administrative functions including risk assessment, SOP development, and monitoring of facility operations.
R-147 | The design should be compliant with WHO recommendations as per the World Health Organization (WHO) Laboratory Biosafety Manual, Fourth Edition, 2020. | 40 | 5.2 (x) | Desirable | Ensure the design is compliant with WHO recommendations. | Yes |  |  |  | While the national guidelines are binding, the WHO standards represent international best practices and the design should be compliant with WHO recommendations.
R-148 | The design should be consistent with CDC recommendations where these do not conflict with national guidelines, as per Centers for Disease Control and Prevention (CDC) - Biosafety in Microbiological and Biomedical Laboratories (BMBL), 5th Edition, 2009. | 40 | 5.2 (xi) | Desirable | Ensure the design is consistent with CDC recommendations where they do not conflict with national guidelines. | Yes |  |  |  | The design should be consistent with CDC recommendations where these do not conflict with national guidelines.
R-149 | The design shall consider international biosafety best practices, but these shall not contravene national regulations applicable for high containment laboratory or BSL-3. | 40 | 5.3 | Mandatory | Consider international biosafety best practices in the design, ensuring they do not contravene national regulations. | Yes |  |  |  | The design shall also consider international biosafety best practices. These shall not contravene national regulations applicable for high containment laboratory or BSL-3.
R-150 | The design must incorporate appropriate seismic design features to ensure structural stability inside the lab and continued operational capability during seismic events, in accordance with IS 1893 (Part 1:2016). | 41 | 5.4 (i) | Mandatory | Design the lab structure as earthquake-resistant in accordance with IS 1893 (Part 1:2016). | Yes |  |  |  | The design must incorporate appropriate seismic design features to ensure structural stability inside the lab and continued operational capability during seismic events. The lab structure establishment must be designed as earthquake-resistant in accordance with this standard.
R-151 | The design of holding tanks and waste decontamination systems must be relevant to IS 13030:2008. | 41 | 5.4 (ii) | Mandatory | Ensure design of holding tanks and waste decontamination systems aligns with IS 13030:2008. | Yes |  |  |  | IS 13030:2008 - Code of Practice for Design, Fabrication and Erection of Non- Pressurized Cylindrical Mild Steel Vertical Welded Oil Storage Tanks: Relevant for design of holding tanks and waste decontamination systems.
R-152 | The electrical design in laboratory environments must comply with IS 4651 (Part 1):2018. | 41 | 5.4 (iii) | Mandatory | Adhere to IS 4651 (Part 1):2018 for electrical design in laboratory environments. | Yes |  |  |  | IS 4651 (Part 1):2018 - Code of Practice for the Design, Installation, Operation, and Maintenance of Electrical Installations in Laboratories: Provides requirements for electrical design in laboratory environments.
R-153 | The fire suppression system design in the BSL-3 facility must be applicable to IS 3956:2009. | 41 | 5.4 (iv) | Mandatory | Apply IS 3956:2009 to the fire suppression system design in the BSL-3 facility. | Yes |  |  |  | IS 3956:2009 - Code of Practice for Planning, Design and Installation of Fire Protection Systems: Applicable to fire suppression system design in the BSL- 3 facility.
R-154 | The design must comply with CPCB and BPCB guidelines (as applicable) on hazardous waste management, biomedical waste handling, and environmental pollution control. | 41 | 5.4 (vi) | Mandatory | Ensure design compliance with CPCB and BPCB guidelines for waste management and pollution control. | Yes |  |  |  | The design must comply with CPCB and BPCB guidelines (as applicable) on hazardous waste management, biomedical waste handling, and environmental pollution control.
R-155 | The waste decontamination systems must be designed to ensure that all biological waste is adequately treated before disposal into drainage systems. | 41 | 5.4 (vi) | Mandatory | Design waste decontamination systems to adequately treat all biological waste before disposal. | Yes |  |  |  | Specifically, the waste decontamination systems must be designed to ensure that all biological waste is adequately treated before disposal into drainage systems.
R-156 | The overall project must comply with environmental protection requirements, including appropriate disposal of treated waste and prevention of environmental contamination, as per Environment (Protection) Act, 1986 and Environment (Protection) Rules, 1986. | 41 | 5.4 (vii) | Mandatory | Comply with Environment (Protection) Act, 1986 and Rules, 1986 for waste disposal and contamination prevention. | Yes |  |  |  | The overall project must comply with environmental protection requirements, including appropriate disposal of treated waste and prevention of environmental contamination.
R-157 | The design must generally comply with National Building Code of India (NBC) 2016 requirements including fire safety, means of escape, ventilation, and other general building standards. | 41 | 5.4 (viii) | Mandatory | Ensure general compliance with NBC 2016 requirements for building standards. | Yes |  |  |  | the design must generally comply with NBC requirements including fire safety, means of escape, ventilation, and other general building standards, except where specific laboratory biosafety requirements
R-158 | Any deviations from NBC must be justified based on biosafety requirements. | 42 | 5.4 (viii) | Mandatory | Provide justification for any deviations from NBC based on biosafety requirements. | Yes |  |  |  | Any deviations from NBC must be justified based on biosafety requirements.
R-159 | The design should incorporate energy efficiency measures where these do not compromise biosafety. | 42 | 5.4 (ix) | Desirable | Incorporate energy efficiency measures without compromising biosafety. | Yes |  |  |  | The design should incorporate energy efficiency measures where these do not compromise biosafety.
R-160 | Considerations for efficient HVAC operation, LED lighting, and optimized heating/cooling systems should be incorporated. | 42 | 5.4 (ix) | Desirable | Incorporate considerations for efficient HVAC operation, LED lighting, and optimized heating/cooling systems. | Yes |  |  |  | Considerations for efficient HVAC operation, LED lighting, and optimized heating/cooling systems should be incorporated.
R-161 | The design, planning, and execution of the facility shall follow the order of precedence: (a) Guidelines issued by the Department of Biotechnology (DBT), (b) Guidelines issued by the Indian Council of Medical Research (ICMR), (c) Relevant Indian Standards (IS Codes) issued by the Bureau of Indian Standards, (d) Other applicable and recognized national or international industry standards. | 42 | Note | Mandatory | Adhere to the specified order of precedence for guidelines and standards in design, planning, and execution. | Yes |  |  |  | The design, planning, and execution of the facility shall follow the following order of precedence: (a) Guidelines issued by the Department of Biotechnology (DBT) (b) Guidelines issued by the Indian Council of Medical Research (ICMR) (c) Relevant Indian Standards (IS Codes) issued by the Bureau of Indian Standards (d) Other applicable and recognized national or international industry standards
R-162 | In the event of any conflict or inconsistency among the applicable standards, the specified order of precedence shall prevail, with the higher-ranked standard taking priority. | 42 | Note (e) | Mandatory | Apply the higher-ranked standard in case of conflict or inconsistency. | Yes |  |  |  | In the event of any conflict or inconsistency among the applicable standards, the order of precedence specified above shall prevail, with the higher-ranked standard taking priority.
R-163 | In cases where specific aspects are not covered under the higher-order guidelines, the provisions of the next applicable standard in the hierarchy shall be followed to ensure overall safety, higher containment, compliance, and functionality of the facility. | 42 | Note (f) | Mandatory | Follow the next applicable standard in the hierarchy for aspects not covered by higher-order guidelines. | Yes |  |  |  | In cases where specific aspects are not covered under the higher-order guidelines, the provisions of the next applicable standard in the hierarchy shall be followed to ensure overall safety, higher containment, compliance, and functionality of the facility.
R-164 | A Bidder can be a single legal entity or the Lead Member of a Joint Venture. | 43 | 6.1 (v) | Eligibility criteria | Submit a Proposal as a single legal entity or as the Lead Member of a Joint Venture. | Yes |  |  |  | “Bidder” / “Bidders” means the entity or the Lead Member of a Joint Venture, as the case may be, which submits a Proposal in response to this RFP; the term shall, where the context so admits, include a single legal entity as well as a Joint Venture.
R-165 | A Joint Venture must consist of not more than the permitted number of legal entities. | 43 | 6.1 (vii) | Eligibility criteria | Form a Joint Venture with no more than the permitted number of legal entities. | Yes |  |  |  | “Joint Venture” means a group of not more than the permitted number of legal entities coming together with a formal intent, under an existing agreement or a Joint Bidding Agreement, to jointly submit a Proposal and, if selected, to implement the Project; or an unincorporated JV under a binding agreement.
R-166 | The Lead Member of a Joint Venture must be duly authorised by all other members through a Power of Attorney and the Joint Bidding Agreement. | 43 | 6.1 (viii) | Mandatory | Ensure the Lead Member is authorized by all JV members via Power of Attorney and Joint Bidding Agreement. | Yes |  |  |  | “Lead Member” means the member of a Joint Venture so designated, and duly authorised by all other members through a Power of Attorney and the Joint Bidding Agreement, to act for and on behalf of the Joint Venture in all matters relating to the Selection Process and the Project also as prescribed in the eligibility criteria for JV in this RFP, both should be read together;
R-167 | A Joint Bidding Agreement must be duly registered and entered into between the members of a Joint Venture, in the format prescribed in Appendix 1 to this RFP, recording inter alia their joint and several liability and the designation of the Lead Member. | 44 | 6.1 (xi) | Mandatory | Submit a duly registered Joint Bidding Agreement in the prescribed format (Appendix 1), detailing joint and several liability and Lead Member designation. | Yes |  |  |  | “Joint Bidding Agreement” means the agreement duly regisered to be entered into between the members of a Joint Venture, in the format prescribed in the Appendix 1 to this RFP, recording inter alia their joint and several liability and the designation of the Lead Member;
R-168 | A Power of Attorney must be duly executed and, where applicable, notarised / apostilled, issued in the format prescribed in Appendix 2, authorising the Authorised Representative or the Lead Member to act on behalf of the bidder. | 44 | 6.1 (xii) | Mandatory | Submit a duly executed and, if applicable, notarised/apostilled Power of Attorney in Appendix 2 format, authorizing the representative or Lead Member. | No — check |  |  |  | “Power of Attorney” means a duly executed and, where applicable, notarised / apostilled power of attorney issued in the format prescribed in the Appendix 2, authorising the Authorised Representative or the Lead Member, as the case may be, to act for and on behalf of the bidder.
R-169 | The Authorised Representative / Authorised Signatory must be duly authorised by the bidder (or by all members of the Joint venture in favour of the Lead Member) by way of a Power of Attorney / board resolution to sign, submit and authenticate the Proposal and to represent the Bidder in all dealings with the Authority. | 44 | 6.1 (xiii) | Mandatory | Ensure the Authorised Representative is duly authorized via Power of Attorney/board resolution to sign, submit, authenticate the Proposal, and represent the Bidder. | Yes |  |  |  | “Authorised Representative” / “Authorised Signatory” means the person duly authorised by the bidder (or by all members of the Joint venture in favour of the Lead Member) by way of a Power of Attorney / board resolution to sign, submit and authenticate the Proposal and to represent the Bidder in all dealings with the Authority;
R-170 | The Proposal must include the Technical Proposal and the Financial Proposal, along with all Forms, Annexures, Appendices, declarations, enclosures and supporting documents. | 44 | 6.1 (xiv) | Submission logistics | Submit a complete Proposal comprising Technical and Financial Proposals, and all required supporting documents. | Yes |  |  |  | “Proposal” / “Bid” means the Technical Proposal together with the Financial Proposal, along with all Forms, Annexures, Appendices, declarations, enclosures and supporting documents, submitted by an Bidder in response to this RFP;
R-171 | The Technical Proposal must contain the Forms, documents and information specified in the RFP relating to the eligibility, technical capacity, methodology, work plan and key personnel of the Bidder, but excluding any financial information. | 44 | 6.1 (xv) | Submission logistics | Submit a Technical Proposal containing all specified eligibility, technical capacity, methodology, work plan, and key personnel information, without financial details. | Yes |  |  |  | “Technical Proposal” means the part of the Proposal containing the Forms, documents and information specified in the RFP relating to the eligibility, technical capacity, methodology, work plan and key personnel of the Bidder, but excluding any financial information;
R-172 | The Financial Proposal must be submitted in the prescribed format indicating the fee / price quoted by the Bidder for executing the Project. | 44 | 6.1 (xvi) | Submission logistics | Submit the Financial Proposal in the prescribed format, quoting the fee/price for the Project. | Yes |  |  |  | “Financial Proposal” means the part of the Proposal submitted in the prescribed format indicating the fee / price quoted by the Bidder for executing the Project in accordance with the terms of the Contract;
R-173 | An Bidder must satisfy the minimum technical and financial qualification requirements set out in the RFP for its Proposal to be considered for evaluations. | 44 | 6.1 (xx) | Eligibility criteria | Meet the minimum technical and financial qualification requirements specified in the RFP. | Yes |  |  |  | “Conditions of Eligibility” / “Minimum Eligibility Criteria” means the minimum technical and financial qualification requirements set out in the RFP which an Bidder must satisfy for its Proposal to be considered for evaluations;
R-174 | An Eligible Assignment must be a consultancy / execution assignment of the nature specified in the RFP — namely services relating to design, engineering, detailed engineering, technical specifications, construction drawings and approval of engineering designs and drawings for GMP/GLP-compliant Biosafety Level 3 and above laboratories (or Animal Biosafety Level 3 and above facilities) with supporting building utilities and infrastructure — undertaken and completed within the period preceding the Proposal Due Date as specified in the RFP. | 45 | 6.1 (xxiii) | Eligibility criteria | Demonstrate experience with Eligible Assignments completed within the specified period before the Proposal Due Date. | Yes |  |  |  | “Eligible Assignment” means a consultancy / execution assignment of the nature specified in the RFP — namely services relating to design, engineering, detailed engineering, technical specifications, construction drawings and approval of engineering designs and drawings for GMP/GLP-compliant Biosafety Level 3 and above laboratories (or Animal Biosafety Level 3 and above facilities) with supporting building utilities and infrastructure — undertaken and completed within the period preceding the Proposal Due Date as specified in the RFP;
R-175 | An assignment which is ongoing as on the Proposal Due Date shall not qualify as an Eligible Assignment subject to RFP conditions. | 45 | 6.1 (xxiii) | Eligibility criteria | Ensure that submitted Eligible Assignments are completed, not ongoing, as of the Proposal Due Date. | Yes |  |  |  | an assignment which is ongoing as on the Proposal Due Date shall not qualify as an Eligible Assignment subject to RFP conditions;
R-176 | The Bid Security / Earnest Money Deposit (EMD) must be furnished by an Bidder along with its Proposal, in the form and for the amount specified in the RFP, by way of demand draft, bank guarantee or Bid Security Declaration, as the case may be. | 46 | 6.1 (xxxvi) | Mandatory | Furnish Bid Security/EMD in the specified form and amount (demand draft, bank guarantee, or Bid Security Declaration) with the Proposal. | Yes |  |  |  | “Bid Security” / “Earnest Money Deposit (EMD)” means the security to be furnished by an Bidder along with its Proposal, in the form and for the amount specified in the RFP, by way of demand draft, bank guarantee or Bid Security Declaration, as the case may be;
R-177 | Bidders claiming exemption from furnishing Bid Security must submit a Bid Security Declaration in the prescribed format in accordance with the applicable Government policy or as per bid document terms. | 46 | 6.1 (xxxvii) | Mandatory | Submit a Bid Security Declaration in the prescribed format if claiming exemption from Bid Security. | Yes |  |  |  | “Bid Security Declaration” means the declaration to be submitted in the prescribed format by Bidders claiming exemption from furnishing Bid Security in accordance with the applicable Government policy or as per bid document terms;
R-178 | Proposals are required to be submitted online through the e-Procurement Portal / Tender Portal. | 46 | 6.1 (xxxix) | Submission logistics | Submit Proposals online via the e-Procurement Portal. | Yes |  |  |  | “e-Procurement Portal” / “Tender Portal” means the electronic procurement portal through which the RFP is published and on which Proposals are required to be submitted online;
R-179 | In the event of any inconsistency, conflict, ambiguity or discrepancy between this RFP and the previously issued Expression of Interest (“EoI”), including any amendment, clarification or document issued in relation thereto, the provisions of this RFP shall prevail to the extent of such inconsistency, conflict, ambiguity or discrepancy. | 48 | 6.2 (xi) | Mandatory | Adhere to the provisions of this RFP in case of any inconsistency or conflict with the previously issued EoI. | Yes |  |  |  | In the event of any inconsistency, conflict, ambiguity or discrepancy between this RFP and the previously issued Expression of Interest (“EoI”), including any amendment, clarification or document issued in relation thereto, the provisions of this RFP shall prevail to the extent of such inconsistency, conflict, ambiguity or discrepancy.
R-180 | The A&E Consultant shall provide comprehensive and sequential professional services for establishment of the proposed BSL-3 Lab-in-Lab facility, with its associated BSL-2 and support areas, within the identified existing space at AIIMS Patna. | 50 | 7.1 (i) | Mandatory | Provide comprehensive and sequential professional services for the BSL-3 Lab-in-Lab facility, BSL-2, and support areas within existing space at AIIMS Patna. | Yes |  |  |  | The A&E Consultant shall provide comprehensive and sequential professional services for establishment of the proposed BSL-3 Lab-in-Lab facility, with its associated BSL-2 and support areas, within the identified existing space at AIIMS Patna.
R-181 | External site works, utilities and ancillary enclosures shall be included only to the extent established by site verification, the approved basis of design and in consultation of AIIMS Patna. | 50 | 7.1 (i) | Mandatory | Include external site works, utilities, and ancillary enclosures only as established by site verification, approved basis of design, and consultation with AIIMS Patna. | Yes |  |  |  | External site works, utilities and ancillary enclosures shall be included only to the extent established by site verification, the approved basis of design and in consultation of AIIMS Patna.
R-182 | The services shall cover existing-building assessment; User required specifications (URS) and biosafety risk assessment; containment zoning and personnel/material/sample/waste workflows; architectural, structural, HVAC/containment, electrical, ELV, fire and life safety, plumbing, ETP/EDS, process utility, BMS/EMS, access-control and security design; equipment planning and integration; BIM and CFD; DPR, cost estimates, BOQ, specifications and Good-for-Tender procurement packages; tender support; periodic construction-stage technical support; commissioning planning and review; independent-validation coordination; certification-support documentation; training; digital/as-built handover; and Defect Liability Support. | 50 | 7.1 (ii) | Mandatory | Provide services covering all listed aspects from existing-building assessment to Defect Liability Support. | Yes |  |  |  | The services shall cover existing-building assessment; User required specifications (URS) and biosafety risk assessment; containment zoning and personnel/material/sample/waste workflows; architectural, structural, HVAC/containment, electrical, ELV, fire and life safety, plumbing, ETP/EDS, process utility, BMS/EMS, access-control and security design; equipment planning and integration; BIM and CFD; DPR, cost estimates, BOQ, specifications and Good-for-Tender procurement packages; tender support; periodic construction-stage technical support; commissioning planning and review; independent-validation coordination; certification-support documentation; training; digital/as-built handover; and Defect Liability Support.
R-183 | The Consultant shall act as the single-point professional coordinator for its design and technical deliverables. | 50 | 7.1 (iii) | Mandatory | Act as the single-point professional coordinator for design and technical deliverables. | Yes |  |  |  | The Consultant shall act as the single-point professional coordinator for its design and technical deliverables.
R-184 | All deliverables shall be integrated, internally coordinated, technically verifiable, procurement-neutral, contractor-usable, maintainable and traceable to the approved requirements, Basis of Design, risk register and applicable compliance matrix. | 50 | 7.1 (iv) | Mandatory | Ensure all deliverables are integrated, internally coordinated, technically verifiable, procurement-neutral, contractor-usable, maintainable, and traceable to approved requirements, Basis of Design, risk register, and compliance matrix. | Yes |  |  |  | All deliverables shall be integrated, internally coordinated, technically verifiable, procurement-neutral, contractor-usable, maintainable and traceable to the approved requirements, Basis of Design, risk register and applicable compliance matrix.
R-185 | Provide a dedicated, access-controlled and functionally segregated BSL-3 containment facility with an associated BSL-2/support laboratory arrangement whose exact extent and room Program are confirmed through the User Requirements. | 50 | 7.2 (i) | Mandatory | Provide a dedicated, access-controlled, and functionally segregated BSL-3 containment facility with an associated BSL-2/support laboratory arrangement, with extent and room program confirmed by User Requirements. | Yes |  |  |  | Provide a dedicated, access-controlled and functionally segregated BSL-3 containment facility with an associated BSL-2/support laboratory arrangement whose exact extent and room Program are confirmed through the User Requirements.
R-186 | Establish a documented pressure cascade and directional inward airflow from lower-risk to higher-risk areas, supported by room-wise design values, monitoring, alarms, failure-mode analysis and measurable acceptance criteria. | 50 | 7.2 (ii) | Mandatory | Establish a documented pressure cascade and directional inward airflow from lower-risk to higher-risk areas, supported by design values, monitoring, alarms, failure-mode analysis, and measurable acceptance criteria. | Yes |  |  |  | Establish a documented pressure cascade and directional inward airflow from lower-risk to higher-risk areas, supported by room-wise design values, monitoring, alarms, failure-mode analysis and measurable acceptance criteria.
R-187 | Provide a dedicated containment HVAC solution with suitable filtration, safe-maintenance access, redundancy and fail-safe control. | 50 | 7.2 (iii) | Mandatory | Provide a dedicated containment HVAC solution with suitable filtration, safe-maintenance access, redundancy, and fail-safe control. | Yes |  |  |  | Provide a dedicated containment HVAC solution with suitable filtration, safe-maintenance access, redundancy and fail-safe control.
R-188 | UVGI may be proposed only as a justified supplementary measure and shall not substitute for HEPA filtration, validated decontamination, cleaning, commissioning, validation or certification requirements. | 50 | 7.2 (iii) | Mandatory | Propose UVGI only as a justified supplementary measure, ensuring it does not substitute for HEPA filtration, validated decontamination, cleaning, commissioning, validation, or certification requirements. | Yes |  |  |  | UVGI may be proposed only as a justified supplementary measure and shall not substitute for HEPA filtration, validated decontamination, cleaning, commissioning, validation or certification requirements.
R-189 | Provide durable, sealed, cleanable and decontamination-compatible containment barriers, finishes, penetrations, doors and equipment interfaces, with permanent access and test provisions for barrier inspection, commissioning and annual revalidation. | 51 | 7.2 (iv) | Mandatory | Provide durable, sealed, cleanable, and decontamination-compatible containment barriers, finishes, penetrations, doors, and equipment interfaces, with permanent access and test provisions for inspection, commissioning, and annual revalidation. | Yes |  |  |  | Provide durable, sealed, cleanable and decontamination-compatible containment barriers, finishes, penetrations, doors and equipment interfaces, with permanent access and test provisions for barrier inspection, commissioning and annual revalidation.
R-190 | Integrate decontamination and waste systems, including separate treatment pathways for potentially contaminated effluent and general wastewater, together with safe solid-waste and material-transfer arrangements. | 51 | 7.2 (v) | Mandatory | Integrate decontamination and waste systems, including separate treatment pathways for contaminated effluent and general wastewater, and safe solid-waste and material-transfer arrangements. | Yes |  |  |  | Integrate decontamination and waste systems, including separate treatment pathways for potentially contaminated effluent and general wastewater, together with safe solid-waste and material-transfer arrangements.
R-191 | Coordinate laboratory equipment, utilities, electrical loads, emergency power, process gases, water, drainage, BMS/EMS and space/maintenance clearances on the basis of an approved equipment-and-utility matrix. | 51 | 7.2 (vi) | Mandatory | Coordinate laboratory equipment, utilities, electrical loads, emergency power, process gases, water, drainage, BMS/EMS, and space/maintenance clearances based on an approved equipment-and-utility matrix. | Yes |  |  |  | Coordinate laboratory equipment, utilities, electrical loads, emergency power, process gases, water, drainage, BMS/EMS and space/maintenance clearances on the basis of an approved equipment-and-utility matrix.
R-192 | Provide life-safety-compliant egress, emergency release, fire protection, biosecurity, access control, CCTV, emergency communication and construction-stage security without trapping personnel or compromising containment. | 51 | 7.2 (vii) | Mandatory | Provide life-safety-compliant egress, emergency release, fire protection, biosecurity, access control, CCTV, emergency communication, and construction-stage security without trapping personnel or compromising containment. | Yes |  |  |  | Provide life-safety-compliant egress, emergency release, fire protection, biosecurity, access control, CCTV, emergency communication and construction-stage security without trapping personnel or compromising containment.
R-193 | Apply Validation by Design so that the works tender, testing plan, FAT/SAT requirements, commissioning, independent validation, certification support and handover requirements are defined before procurement. | 51 | 7.2 (viii) | Mandatory | Apply Validation by Design to define works tender, testing plan, FAT/SAT, commissioning, independent validation, certification support, and handover requirements before procurement. | Yes |  |  |  | Apply Validation by Design so that the works tender, testing plan, FAT/SAT requirements, commissioning, independent validation, certification support and handover requirements are defined before procurement.
R-194 | Support safe, economical and maintainable long-term operation through lifecycle-cost review, spares and AMC planning, calibration/revalidation access, editable digital records and avoidance of unnecessary vendor or software lock-in. | 51 | 7.2 (ix) | Mandatory | Support safe, economical, and maintainable long-term operation through lifecycle-cost review, spares and AMC planning, calibration/revalidation access, editable digital records, and avoidance of unnecessary vendor or software lock-in. | Yes |  |  |  | Support safe, economical and maintainable long-term operation through lifecycle-cost review, spares and AMC planning, calibration/revalidation access, editable digital records and avoidance of unnecessary vendor or software lock-in.
R-195 | Prepare a certification-ready, operationally usable facility solution without authorising work with viable pathogenic, high-risk or genetically engineered organisms before the required statutory certification and institutional authorisations are in place. | 51 | 7.2 (x) | Mandatory | Prepare a certification-ready, operationally usable facility solution, ensuring no authorization for work with pathogenic, high-risk, or genetically engineered organisms occurs before statutory certification and institutional authorizations are in place. | Yes |  |  |  | Prepare a certification-ready, operationally usable facility solution without authorising work with viable pathogenic, high-risk or genetically engineered organisms before the required statutory certification and institutional authorisations are in place.
R-196 | The Consultant shall verify every input, identify assumptions and departures in the Basis of Design before freezing the affected design. | 51 | 7.3 (i) | Mandatory | Verify every input, identify assumptions and departures in the Basis of Design before freezing the affected design. | Yes |  |  |  | The Consultant shall verify every input, identify assumptions and departures in the Basis of Design before freezing the affected design.
R-197 | The applicable national statutory and DBT-ICMR biosafety framework shall govern. | 51 | 7.3 (ii) | Mandatory | Adhere to the applicable national statutory and DBT-ICMR biosafety framework. | Yes |  |  |  | The applicable national statutory and DBT-ICMR biosafety framework shall govern.
R-198 | International guidance may supplement the national requirements where it is consistent with them. | 51 | 7.3 (ii) | Mandatory | Use international guidance to supplement national requirements only if consistent. | Yes |  |  |  | International guidance may supplement the national requirements where it is consistent with them.
R-199 | A higher-containment option may be recommended only with a recorded technical basis, cost and operational impact, and prior approval of AIIMS Patna after confirming consistency with applicable Indian law and the national DBT-ICMR biosafety framework, recording the technical, cost and operational implications, and obtaining prior approval of AIIMS Patna. | 51 | 7.3 (ii) | Mandatory | Recommend a higher-containment option only with a recorded technical basis, cost, and operational impact, and prior approval from AIIMS Patna, ensuring consistency with Indian law and DBT-ICMR biosafety framework. | Yes |  |  |  | A higher-containment option may be recommended only with a recorded technical basis, cost and operational impact, and prior approval of AIIMS Patna after confirming consistency with applicable Indian law and the national DBT-ICMR biosafety framework, recording the technical, cost and operational implications, and obtaining prior approval of AIIMS Patna.
R-200 | Any annexe, vertical extension, third-floor/terrace enclosure, new lift shaft, lintel or other material structural intervention shall be treated as an option requiring structural and statutory feasibility, itemised cost and Program impact, budget availability and; it shall not be assumed as an automatic baseline scope. | 51 | 7.3 (iii) | Mandatory | Treat any annexe, vertical extension, third-floor/terrace enclosure, new lift shaft, lintel, or other material structural intervention as an option requiring structural and statutory feasibility, itemized cost, Program impact, and budget availability, not as automatic baseline scope. | Yes |  |  |  | Any annexe, vertical extension, third-floor/terrace enclosure, new lift shaft, lintel or other material structural intervention shall be treated as an option requiring structural and statutory feasibility, itemised cost and Program impact, budget availability and; it shall not be assumed as an automatic baseline scope.
R-201 | Phase I comprises Milestones M-1 to M-8 and culminates in the accepted Final DPR and complete Good-for-Tender packages within sixty (60) days from the Notice to Proceed. | 52 | 7.4 (i) | Submission logistics | Complete Milestones M-1 to M-8, including accepted Final DPR and complete Good-for-Tender packages, within 60 days from the Notice to Proceed. | Yes |  |  |  | Phase I comprises Milestones M-1 to M-8 and culminates in the accepted Final DPR and complete Good-for-Tender packages within sixty (60) days from the Notice to Proceed.
R-202 | Day 61 to Day 75 is available only for exceptional consolidated comment closure expressly approved in writing by AIIMS Patna. | 52 | 7.4 (i) | Submission logistics | Utilize Day 61 to Day 75 only for exceptional consolidated comment closure, with express written approval from AIIMS Patna. | Yes |  |  |  | Day 61 to Day 75 is available only for exceptional consolidated comment closure expressly approved in writing by AIIMS Patna.
R-203 | The Consultant shall develop, coordinate and refine all requirements with due professional care in accordance with applicable statutory provisions, recognised biosafety guidelines, engineering standards, good industry practice and the specific needs of AIIMS Patna. | 53 | 8.1 | Mandatory | Develop, coordinate, and refine all requirements with due professional care, adhering to applicable statutory provisions, recognized biosafety guidelines, engineering standards, good industry practice, and AIIMS Patna's specific needs. | Yes |  |  |  | The Consultant shall develop, coordinate and refine all requirements with due professional care in accordance with applicable statutory provisions, recognised biosafety guidelines, engineering standards, good industry practice and the specific needs of AIIMS Patna.
R-204 | It is the Consultant's responsibility to ensure that no applicable requirement is left unaddressed, and that this responsibility extends fully to commissioning, validation, certification and accreditation, not only to physical design and construction. | 54 | 8.2 (iii) | Mandatory | Ensure all applicable requirements are addressed, extending responsibility to commissioning, validation, certification, and accreditation, beyond physical design and construction. | Yes |  |  |  | It is the Consultant's responsibility to ensure that no applicable requirement is left unaddressed, and that this responsibility extends fully to commissioning, validation, certification and accreditation, not only to physical design and construction.
R-205 | It remains the Consultant's professional duty, in preparing the Basis of Design and all subsequent deliverables, to satisfy itself independently that every applicable statutory, regulatory and good-practice requirement — whether or not separately restated in this document — has in fact been addressed, and to identify and resolve, any matter that this document does not appear to cover. | 54 | 8.2 (iii) | Mandatory | Independently verify that all applicable statutory, regulatory, and good-practice requirements are addressed in the Basis of Design and subsequent deliverables, and identify/resolve any uncovered matters. | Yes |  |  |  | It remains the Consultant's professional duty, in preparing the Basis of Design and all subsequent deliverables, to satisfy itself independently that every applicable statutory, regulatory and good-practice requirement — whether or not separately restated in this document — has in fact been addressed, and to identify and resolve, any matter that this document does not appear to cover.
R-206 | The Consultant shall prepare the Commissioning Plan, test requirements, sequence and acceptance criteria and shall coordinate, technically oversee and review implementation. | 54 | 8.2 (iii) (a) | Mandatory | Prepare the Commissioning Plan, test requirements, sequence, and acceptance criteria, and coordinate, technically oversee, and review implementation. | Yes |  |  |  | The Consultant shall prepare the Commissioning Plan, test requirements, sequence and acceptance criteria and shall coordinate, technically oversee and review implementation.
R-207 | The Consultant shall plan and support Validation through Design Qualification, Installation Qualification, Operational Qualification and Performance Qualification, supported by risk-based Factory Acceptance Testing (FAT), Site Acceptance Testing (SAT) and Integrated Systems Testing (IST) for containment-critical systems through test protocols, responsibilities, prerequisites, calibrated instruments, acceptance criteria, deviation control, retesting requirements and records included in the Good-for-Tender works package, demonstrating reliable performance under normal and defined worst-case conditions. | 54 | 8.2 (iii) (b) | Mandatory | Plan and support Validation through DQ, IQ, OQ, PQ, FAT, SAT, and IST for containment-critical systems, including test protocols, responsibilities, prerequisites, calibrated instruments, acceptance criteria, deviation control, retesting requirements, and records in the Good-for-Tender works package. | No — check |  |  |  | The Consultant shall plan and support Validation through Design Qualification, Installation Qualification, Operational Qualification and Performance Qualification, supported by risk-based Factory Acceptance Testing (FAT), Site Acceptance Testing (SAT) and Integrated Systems Testing (IST) for containment-critical systems through test protocols, responsibilities, prerequisites, calibrated instruments, acceptance criteria, deviation control, retesting requirements and records included in the Good-for-Tender works package, demonstrating reliable performance under normal and defined worst-case conditions.
R-208 | The Consultant shall prepare and support with all necessary documentation Certification: The formal submission to, and approval by, the competent national regulatory authority confirming that the facility meets the prescribed standard for operation as a BSL-3 facility. | 55 | 8.2 (iii) (c) | Mandatory | Prepare and support with all necessary documentation for formal submission and approval by the national regulatory authority for BSL-3 facility certification. | Yes |  |  |  | Certification: The formal submission to, and approval by, the competent national regulatory authority confirming that the facility meets the prescribed standard for operation as a BSL-3 facility, which the Consultant shall prepare and support with all necessary documentation;
R-209 | The Consultant shall prepare the scope, accreditation/competence requirements, test matrix, acceptance criteria and other technical inputs required for testing and validation. | 55 | 8.2 (iii) (d) | Mandatory | Prepare the scope, accreditation/competence requirements, test matrix, acceptance criteria, and other technical inputs for independent testing and validation agencies. | Yes |  |  |  | The Consultant shall prepare the scope, accreditation/competence requirements, test matrix, acceptance criteria and other technical inputs required for testing and validation.
R-210 | The Consultant shall coordinate and technically support their work but shall not appoint them in its own name or substitute their independent function. | 55 | 8.2 (iii) (d) | Mandatory | Coordinate and technically support the work of independent testing and validation agencies, but do not appoint them or substitute their independent function. | Yes |  |  |  | The Consultant shall coordinate and technically support their work but shall not appoint them in its own name or substitute their independent function.
R-211 | The Consultant's design and documentation shall be structured to facilitate Annual re-validation: The recurring, lifecycle obligation, which the Consultant's design and documentation shall be structured to facilitate, to re-verify after the facility becomes operational that every critical containment parameter continues to perform to the standard established at commissioning, for as long as the facility remains in service. | 55 | 8.2 (iii) (e) | Mandatory | Structure the design and documentation to facilitate annual re-validation, ensuring critical containment parameters continue to perform to commissioning standards for the facility's service life. | Yes |  |  |  | Annual re-validation: The recurring, lifecycle obligation, which the Consultant's design and documentation shall be structured to facilitate, to re-verify after the facility becomes operational that every critical containment parameter continues to perform to the standard established at commissioning, for as long as the facility remains in service.
R-212 | The Consultant shall apply Validation by Design from the first design stage. | 55 | 8.2 (iv) | Mandatory | Apply Validation by Design from the first design stage. | Yes |  |  |  | The Consultant shall apply Validation by Design from the first design stage.
R-213 | Any ambiguity, gap or apparent conflict shall be recorded in the design-issue register and submitted to AIIMS Patna; it shall not be resolved silently or used to dilute an applicable requirement. | 55 | 8.2 (iv) | Mandatory | Record any ambiguity, gap, or apparent conflict in the design-issue register and submit to AIIMS Patna; do not resolve silently or dilute applicable requirements. | Yes |  |  |  | Any ambiguity, gap or apparent conflict shall be recorded in the design-issue register and submitted to AIIMS Patna; it shall not be resolved silently or used to dilute an applicable requirement.
R-214 | The Consultant shall evaluate each design decision against its operational consequence — workflow efficiency, ease and cost of routine maintenance, energy and resource consumption, staff comfort and safety in daily use, and the practical burden of compliance with biosafety SOPs — and shall not finalise a design feature solely because it satisfies a physical/dimensional requirement, without also confirming that it serves the facility's day-to-day operation well. | 55 | 8.2 (v) | Mandatory | Evaluate each design decision against operational consequences (workflow, maintenance, energy, staff comfort/safety, biosafety SOPs) and confirm it serves day-to-day operation well, not just physical/dimensional requirements. | Yes |  |  |  | The Consultant shall evaluate each design decision against its operational consequence — workflow efficiency, ease and cost of routine maintenance, energy and resource consumption, staff comfort and safety in daily use, and the practical burden of compliance with biosafety SOPs — and shall not finalise a design feature solely because it satisfies a physical/dimensional requirement, without also confirming that it serves the facility's day-to-day operation well.
R-215 | Where the physical-design solution that is simplest to draw is not the one that operates best, the Consultant shall identify this trade-off and bring it to AIIMS Patna's attention rather than defaulting silently to the simpler option. | 55 | 8.2 (v) | Mandatory | Identify and bring to AIIMS Patna's attention any trade-off where the simplest physical design is not the best operational solution, instead of silently defaulting to the simpler option. | Yes |  |  |  | Where the physical-design solution that is simplest to draw is not the one that operates best, the Consultant shall identify this trade-off and bring it to AIIMS Patna's attention rather than defaulting silently to the simpler option.
R-216 | The facility shall comply first with applicable Indian law, statutory requirements and the applicable national DBT-ICMR biosafety framework. | 55 | 8.3 (i) | Mandatory | Ensure the facility complies first with applicable Indian law, statutory requirements, and the national DBT-ICMR biosafety framework. | Yes |  |  |  | The facility shall comply first with applicable Indian law, statutory requirements and the applicable national DBT-ICMR biosafety framework.
R-217 | Recognised international engineering and biosafety guidance may supplement the national framework only where it does not conflict with it. | 56 | 8.3 (i) | Mandatory | Supplement the national framework with recognized international engineering and biosafety guidance only if it does not conflict. | Yes |  |  |  | Recognised international engineering and biosafety guidance may supplement the national framework only where it does not conflict with it.
R-218 | If a conflict exists, the national/statutory requirement shall prevail. | 56 | 8.3 (i) | Mandatory | Ensure national/statutory requirements prevail if a conflict exists. | Yes |  |  |  | If a conflict exists, the national/statutory requirement shall prevail.
R-219 | A more stringent international or higher-containment provision may be adopted only where technically justified and, where it affects cost, space, Program or operation, in consultation with AIIMS Patna. | 56 | 8.3 (i) | Mandatory | Adopt more stringent international or higher-containment provisions only if technically justified and, if affecting cost, space, Program, or operation, in consultation with AIIMS Patna. | Yes |  |  |  | A more stringent international or higher-containment provision may be adopted only where technically justified and, where it affects cost, space, Program or operation, in consultation with AIIMS Patna.
R-220 | The Consultant shall identify the applicable codes, standards and regulatory instruments in their latest applicable edition as on the Notice to Proceed/Letter (Notice) of Award. | 56 | 8.3 (ii) | Mandatory | Identify applicable codes, standards, and regulatory instruments in their latest edition as of the Notice to Proceed/Letter of Award. | Yes |  |  |  | The Consultant shall identify the applicable codes, standards and regulatory instruments in their latest applicable edition as on the Notice to Proceed/Letter (Notice) of Award.
R-221 | The Consultant shall maintain, as part of the Basis of Design, a consolidated record identifying every code, standard, and regulatory instrument applied to the design, the specific design decisions governed by each, and the basis for resolving any conflict between them, so that AIIMS Patna and any reviewing regulatory authority can readily verify the regulatory foundation of the design. | 56 | 8.3 (iii) | Mandatory | Maintain a consolidated record within the Basis of Design, identifying all applied codes, standards, regulatory instruments, specific design decisions governed by each, and conflict resolution basis for verification by AIIMS Patna and regulatory authorities. | Yes |  |  |  | The Consultant shall maintain, as part of the Basis of Design, a consolidated record identifying every code, standard, and regulatory instrument applied to the design, the specific design decisions governed by each, and the basis for resolving any conflict between them, so that AIIMS Patna and any reviewing regulatory authority can readily verify the regulatory foundation of the design.
R-222 | Value Engineering (VE) is a documented comparison of technically compliant alternatives to achieve the approved function, containment performance, quality and maintainability at reasonable lifecycle cost. | 56 | 8.4 (i) | Mandatory | Conduct Value Engineering as a documented comparison of technically compliant alternatives to achieve approved function, containment performance, quality, and maintainability at reasonable lifecycle cost. | Yes |  |  |  | Value Engineering (VE) is a documented comparison of technically compliant alternatives to achieve the approved function, containment performance, quality and maintainability at reasonable lifecycle cost.
R-223 | It shall not be used to reduce a mandatory biosafety, statutory or acceptance requirement. | 56 | 8.4 (i) | Mandatory | Do not use Value Engineering to reduce any mandatory biosafety, statutory, or acceptance requirement. | Yes |  |  |  | It shall not be used to reduce a mandatory biosafety, statutory or acceptance requirement.
R-224 | Submit a Design Options and Recommendation Register at each major design gate covering specified major design decisions. | 57 | 8.4(ii) | Mandatory | Prepare and submit the register at each major design gate. | Yes |  |  |  | At each major design gate the Consultant shall submit a Design Options and Recommendation Register for major architectural, structural, HVAC, electrical, plumbing/EDS, BMS/security and equipment-interface decisions.
R-225 | Document and submit the outcome of each Value Engineering review at the corresponding design milestone and retain it in the Basis of Design. | 57 | 8.4(iii) | Mandatory | Document options considered and rejected, explain the selected option, submit the review outcome to AIIMS Patna, and retain it in the Basis of Design. | Yes |  |  |  | The outcome of each Value Engineering review, including options considered and rejected and the reasoning for the option selected, shall be documented and submitted to AIIMS Patna for review at the corresponding design milestone, and shall be retained as part of the Basis of Design.
R-226 | Establish the administrative framework and specified controls for complete commissioning and verification. | 57 | 8.5(i) | Mandatory | Establish responsibilities, prerequisites, test sequence, acceptance criteria, records, deviation control and retesting requirements for commissioning. | Yes |  |  |  | The Consultant shall establish the administrative framework, responsibilities, prerequisites, test sequence, acceptance criteria, records, deviation control and retesting requirements for this complete process.
R-227 | Prepare the tender-level Master Testing, Commissioning and Validation Control Plan with the specified contents. | 57 | 8.5(ii) | Mandatory | Prepare the control plan identifying FAT, SAT and IST applicability, inspection and test plans, hold and witness points, responsibilities, prerequisites, calibrated instruments, acceptance criteria, records, deviation control, retesting and linkage to independent Validation. | Yes |  |  |  | The Consultant shall prepare the tender-level Master Testing, Commissioning and Validation Control Plan. It shall identify system-wise FAT, SAT and IST applicability; Inspection and Test Plans; hold and witness points; responsibilities; prerequisites; calibrated instruments; acceptance criteria; records; deviation control; retesting; and linkage to independent Validation.
R-228 | Coordinate security systems as one integrated security architecture with measurable testing and acceptance criteria. | 58 | 8.6(i) | Mandatory | Coordinate access control, door interlocks, biometric or card-based access, CCTV, intrusion detection, emergency release, BMS/EMS interfaces, network security, event logging, backup power and safe egress as an integrated architecture, and provide measurable testing and acceptance criteria. | Yes |  |  |  | The Consultant shall coordinate facility-level access control, laboratory and airlock door interlocks, biometric or card-based access, CCTV, intrusion detection, emergency release, BMS/EMS interfaces, network security, event logging, backup power and safe egress as one integrated security architecture, with measurable testing and acceptance criteria.
R-229 | Document the integration of all security-related design elements in the Basis of Design. | 58 | 8.6(ii) | Mandatory | Coordinate access control, CCTV, intrusion detection and containment-door interlocking as a single integrated security architecture and document the integration in the Basis of Design. | Yes |  |  |  | The Consultant shall coordinate all security-related design elements — access control, CCTV, intrusion detection, and the interlocking of containment doors — as a single, integrated security architecture, even though the supporting technical requirements for each component appear in different chapters of this document, and shall document this integration in the Basis of Design.
R-230 | Prepare a documented comparison of technically compliant alternatives and recommend the best overall-value option without diluting mandatory requirements. | 58 | 8.7(i) | Mandatory | Compare alternatives on the specified design, compliance, biosafety, validation, reliability, maintainability, energy, cost and procurement factors, and recommend the best-value option. | Yes |  |  |  | Where more than one technically compliant solution is available, the Consultant shall prepare a documented comparison of the alternatives, including design basis, compliance effect, biosafety and validation effect, reliability, maintainability, energy use, capital cost, recurring cost, procurement dependency and lifecycle cost, and shall recommend the option that provides the best overall value without diluting any mandatory requirement.
R-231 | Technically justify any increase above the stated baseline and identify its impacts. | 58 | 8.7(ii) | Mandatory | Provide technical justification for increases above the baseline and identify capital, operating, space, Program and validation impacts. | Yes |  |  |  | Any increase above the stated baseline shall be technically justified and shall identify capital, operating, space, Program and validation impacts.
R-232 | Recommend higher values where calculations, risk assessments or national requirements establish them, with specified effects. | 58 | 8.7.1(i) | Mandatory | Recommend the higher value and state its technical, capital, operating, space, program and validation effects. | Yes |  |  |  | Where a room-wise calculation, risk assessment or governing national requirement establishes a value higher than an express minimum, the Consultant shall recommend the higher value with its technical, capital, operating, space, program and validation effects.
R-233 | Use the approved value consistently across all specified design and acceptance documents. | 58 | 8.7.1(ii) | Mandatory | Apply the approved value consistently in the Basis of Design, drawings, specifications, BOQ, BIM/CFD, testing and acceptance criteria. | Yes |  |  |  | The approved value shall be used consistently in the Basis of Design, drawings, specifications, BOQ, BIM/CFD, testing and acceptance criteria.
R-234 | Design the facility to maintain specified containment and biosafety features. | 59 | 8.8(ii) | Mandatory | Ensure work is conducted in certified biological safety cabinets, maintain negative pressure, filter exiting air through verified-efficiency HEPA systems, provide appropriate PPE, and establish emergency response procedures. | Yes |  |  |  | The design shall ensure that: all work with biological agents is conducted within appropriately rated and certified biological safety cabinets that provide physical barriers and controlled airflow to prevent aerosol exposure; the laboratory environment maintains negative pressure relative to non- containment areas, providing a protective pressure gradient that prevents escape of potentially contaminated air; all air exiting the laboratory is filtered through HEPA filtration systems of verified efficiency; personal protective equipment is readily available and appropriate to the level of risk; and emergency response procedures are in place to address potential exposure incidents.
R-235 | Provide the specified secondary containment and environmental protection features. | 59 | 8.8(iii) | Mandatory | Provide a sealed and tested building envelope, decontaminate or treat materials leaving the laboratory, separate the facility from other buildings and public areas, provide fail-safe barriers, and provide monitoring/surveillance systems. | Yes |  |  |  | This is achieved through: a sealed building envelope acting as a secondary containment barrier, with all penetrations sealed and tested; appropriate decontamination or treatment of all materials (air, liquid waste, or solid waste) leaving the laboratory before environmental release; adequate separation of the facility from other institutional buildings and public areas; fail-safe mechanisms that maintain protective barriers during equipment malfunction or emergency; and monitoring/surveillance systems enabling early detection of containment breaches.
R-236 | Implement the four complementary containment strategies. | 59 | 8.8(iv) | Mandatory | Implement physical containment, safety equipment, facility design and procedural containment as integrated strategies, without treating any one as sufficient in isolation. | Yes |  |  |  | The facility shall achieve comprehensive containment through the integrated implementation of four complementary and mutually reinforcing containment strategies, no one of which shall be considered sufficient in isolation:
R-237 | Provide the specified facility-design containment features. | 60 | 8.8(iv)(c) | Mandatory | Provide a sealed and impermeable envelope, negative-pressure gradient, HEPA filtration for discharged air, sealed waste-decontamination systems, restricted and controlled entry/exit, and continuous monitoring/surveillance. | Yes |  |  |  | Facility design — a secondary containment layer comprising a sealed and impermeable building envelope, negative-pressure gradient relative to non- containment areas, HEPA filtration of all air discharged to the environment, sealed waste-decontamination systems, restricted and controlled entry/exit, and continuous monitoring/surveillance;
R-238 | Design the facility to embody and reinforce biosafety culture. | 60 | 8.8(v) | Mandatory | Make containment features visible, facilitate safe practice, provide redundancy in critical safety systems, enable continuous monitoring, immediately notify personnel of deviations, and maintain a clean and organized environment. | Yes |  |  |  | The facility design shall itself embody and reinforce a culture of biosafety: containment features shall be made visible and prominent; work spaces shall be designed to facilitate rather than hinder safe practice; redundancy shall be built into critical safety systems; monitoring and surveillance shall allow continuous verification of correct operation; communication and alert systems shall immediately notify personnel of any deviation from required parameters; and the physical environment shall be clean, well-organised, and comfortable enough to support sustained compliance with safety procedures.
R-239 | Translate facility objectives into measurable room-wise and system-wise criteria. | 60 | 8.9(i) | Mandatory | Define measurable criteria covering the listed segregation, pressure, airflow, containment, decontamination, waste, utilities, alarms, emergency, maintenance, commissioning, validation, certification and acceptance matters. | Yes |  |  |  | The approved design shall translate the required facility objectives into measurable room-wise and system-wise criteria, including access-controlled functional segregation, pressure relationships, directional airflow, containment-envelope integrity, decontamination, waste management, utilities, alarms, emergency response, maintenance access, commissioning, independent Validation, certification readiness and acceptance evidence.
R-240 | Show traceability from user requirements and biosafety risk assessment to design and certification-support deliverables at each design stage. | 60 | 8.9(ii) | Mandatory | Include traceability in every design-stage submission through drawings, calculations, specifications, BOQ, commissioning/validation matrix and certification-support dossier. | Yes |  |  |  | Each design-stage submission shall show traceability from the User Requirements and biosafety risk assessment to the drawings, calculations, specifications, BOQ, commissioning/validation matrix and certification- support dossier.
R-241 | Identify unresolved assumptions, interfaces and risks at each review gate and do not silently defer critical dependencies. | 60 | 8.9(iii) | Mandatory | Identify all unresolved assumptions, interfaces and risks at every review gate and explicitly address biosafety-critical and procurement-critical dependencies. | Yes |  |  |  | The Consultant shall identify unresolved assumptions, interfaces and risks at each review gate; no biosafety-critical or procurement-critical dependency shall be deferred silently to the Works Agency or a future vendor.
R-242 | Coordinate all listed disciplines and functions as one design system. | 60 | 8.10(i) | Mandatory | Coordinate architecture, structure, containment HVAC, electrical, ELV, fire/life safety, plumbing, ETP/EDS, utilities, BMS/EMS, security, equipment, BIM, CFD, compliance, commissioning, validation and handover. | Yes |  |  |  | The Consultant shall coordinate architecture, structure, containment HVAC, electrical, ELV, fire/life safety, plumbing, ETP/EDS, process utilities, BMS/EMS, security, laboratory equipment, BIM, CFD, statutory compliance, commissioning, validation and handover as one design system.
R-243 | Provide the named specialist and key personnel inputs without reducing single-point responsibility. | 60 | 8.10(ii) | Mandatory | Provide inputs from the listed project, biosafety, equipment, BIM, compliance, HVAC, electrical, fire/life safety, structural and commissioning/validation personnel, while retaining responsibility for complete and consistent deliverables. | Yes |  |  |  | Discipline and specialist inputs shall be provided by the named Project Director or Single Point of Contact, Biosafety Expert, Laboratory Equipment Planning and Integration Specialist, BIM Manager or BIM Architect, Environmental and Statutory Compliance Expert, HVAC and Containment Lead, Electrical Lead, Fire and Life-Safety Lead, Structural Lead, Commissioning and Validation Coordinator and any other specialist required for the approved scope. Specialist/key expert/personnel participation shall not divide or reduce the Consultant’s single-point responsibility for the completeness and internal consistency of its deliverables.
R-244 | Provide the complete stage-wise scope and specified deliverables and support. | 60 | 8.10(iii) | Mandatory | Provide stage-wise scope, procurement packages, design and technical deliverables, construction-stage support, commissioning and independent-Validation support, certification documentation, digital handover and responsibility allocation. | Yes |  |  |  | The Consultant shall provide the complete stage-wise scope, procurement packages, design and technical deliverables, construction-stage technical support, commissioning and independent-Validation support, certification documentation, digital handover and responsibility allocation required for the assignment.
R-245 | Conduct multidisciplinary Design Risk Workshops at Concept Design and before final Detailed Design. | 61 | 8.10(iv) | Mandatory | Conduct both workshops and examine the specified operational, maintenance, failure, safety, flow, replacement and recovery scenarios. | Yes |  |  |  | The Consultant shall conduct a multidisciplinary Design Risk Workshop at Concept Design and again before final Detailed Design. The workshop shall examine normal operation, maintenance, utility failure, fire mode, pressure reversal, filter change, decontamination, spill response, personnel/material flow, equipment replacement and emergency recovery.
R-246 | Conduct a comprehensive site and existing-structure investigation covering the specified site conditions and opportunities. | 61 | 8.11(i) | Mandatory | Investigate electrical supply, water, drainage and wastewater, telecommunications, compressed air and vacuum, and gas supply as specified. | Yes |  |  |  | The Consultant shall conduct a comprehensive site and existing-structure investigation to establish site conditions, requirements and opportunities for the BSL-3 facility design within the specified building, covering at minimum:
R-247 | Assess electrical supply adequacy and backup requirements for the facility. | 61 | 8.11(i)(a) | Mandatory | Assess existing electrical capacity, UPS provision, prevention of complete power failure, diesel-generator backup, round-the-clock operation capability, and need for utility augmentation or upgrade. | Yes |  |  |  | Electrical supply — assessment of the adequacy of the existing electrical supply to meet facility requirements, including provision of UPS systems, measures to prevent complete power failure in laboratory and operational areas, dedicated diesel-generator backup, and capability for uninterrupted round-the-clock operation; and a determination of whether augmentation or upgrade from the utility provider is required;
R-248 | Evaluate water-supply infrastructure and adequacy. | 61 | 8.11(i)(b) | Mandatory | Evaluate infrastructure, capacity, quality, pressure and seasonal variation, including adequacy for HVAC makeup water, laboratory operations and emergency showers/eyewash stations. | Yes |  |  |  | Water supply — evaluation of existing infrastructure, capacity, water quality, pressure characteristics and seasonal variation, and assessment of adequacy for facility needs including HVAC makeup water, laboratory operations, and emergency showers/eyewash stations;
R-249 | Evaluate drainage and wastewater infrastructure and capacity. | 61 | 8.11(i)(c) | Mandatory | Evaluate drainage infrastructure, capacity and municipal sewerage connection, including adequacy for treated laboratory waste after decontamination. | Yes |  |  |  | Drainage and wastewater — evaluation of existing drainage infrastructure, capacity, and connection to the municipal sewerage system, and assessment of adequacy for handling treated laboratory waste after decontamination;
R-250 | Evaluate telecommunications infrastructure and wiring arrangements. | 61 | 8.11(i)(d) | Mandatory | Evaluate communication infrastructure, fibre-optic availability for building-management and monitoring/surveillance systems, and wiring for landline, Wi-Fi, cable/D2H and CCTV connectivity. | Yes |  |  |  | Telecommunications — evaluation of required communication infrastructure, including fibre-optic availability for building- management and monitoring/surveillance systems, and the wiring arrangement needed for landline, Wi-Fi, cable/D2H and CCTV connectivity;
R-251 | Assess required compressed-air or vacuum systems and dedicated provision. | 61 | 8.11(i)(e) | Mandatory | Assess the required systems and appropriate level of dedicated provision for BSL-3 operations. | Yes |  |  |  | Compressed air and vacuum — assessment of required compressed-air or vacuum systems and the appropriate level of dedicated provision for BSL-3 operations;
R-252 | Assess the need for specialty gases for equipment or laboratory work. | 61 | 8.11(i)(f) | Mandatory | Assess the need for gases such as nitrogen, argon and carbon dioxide. | Yes |  |  |  | Gas supply — assessment of the need for specialty gases (e.g., nitrogen, argon, carbon dioxide), as required for equipment operation or laboratory work.
R-253 | Assess environmental and potential contamination conditions. | 61 | 8.11(ii) | Mandatory | Assess ambient air quality and inlet-air contamination sources, ambient noise and interference, electromagnetic interference and vibration sources. | Yes |  |  |  | The Consultant shall further assess environmental and potential contamination conditions, including: ambient air quality and potential sources of inlet-air contamination (dust, pollen, vehicular or industrial emissions); ambient noise levels and potential sources of interference with sensitive equipment or monitoring systems; sources of electromagnetic interference; and sources of vibration that could affect sensitive equipment or compromise precision instrumentation.
R-254 | Conduct a structural audit of the existing structure against current seismic provisions and identify retrofit deficiencies. | 61 | 8.11(iii) | Mandatory | Audit the existing structure for the relevant seismic zone of Patna, Bihar and identify deficiencies requiring retrofit. | Yes |  |  |  | Since the facility is proposed within an existing building, the consultant shall conduct a structural audit of the existing structure against current seismic design provisions for the relevant seismic zone of Patna, Bihar, and shall identify any deficiency requiring retrofit.
R-255 | Design the facility as a completely integrated, self-contained unit based on the box-in-box principle. | 62 | 8.12(i) | Mandatory | Apply the box-in-box containment layout principle in the facility design. | Yes |  |  |  | The facility shall be designed as a completely integrated, self-contained unit, based on the "box-in-box" principle — the more-contaminated (core) area surrounded by progressively less- contaminated areas — such that the laboratory room itself acts as the secondary barrier when infectious work is conducted within primary barriers (biological safety cabinets).
R-256 | Prepare a documented workflow and flow-chart covering personnel, material and pathogen movement before finalising the spatial layout. | 62 | 8.12(ii) | Mandatory | Prepare and document the required workflow and flow-chart before finalising the layout. | Yes |  |  |  | The Consultant shall prepare a documented workflow and flow-chart of personnel, material and pathogen movement covering the entire scope of work, before finalising the spatial layout, and shall avoid columns and beams within the containment laboratory room wherever feasible, to facilitate cleaning and decontamination.
R-257 | Avoid columns and beams within the containment laboratory room wherever feasible. | 62 | 8.12(ii) | Mandatory | Avoid columns and beams in the containment laboratory room where feasible. | Yes |  |  |  | The Consultant shall prepare a documented workflow and flow-chart of personnel, material and pathogen movement covering the entire scope of work, before finalising the spatial layout, and shall avoid columns and beams within the containment laboratory room wherever feasible, to facilitate cleaning and decontamination.
R-258 | Provide ample laboratory space, adequate immediate-use and long-term storage, and space for safe handling and storage of chemicals, solvents and compressed/liquefied gases where used. | 62 | 8.12(iii) | Mandatory | Provide the specified workspace, storage and chemical/gas handling facilities. | Yes |  |  |  | Ample space shall be provided for the safe conduct of laboratory work, cleaning and maintenance. Storage space shall be adequate to hold immediate-use supplies, preventing bench-top clutter, with additional long-term storage provided outside the laboratory. No facility for storage or consumption of food, drink, or personal items shall be provided inside the laboratory; dedicated space for these purposes shall be provided outside the containment zone. Space and facilities shall be provided for the safe handling and storage of chemicals, solvents and compressed/liquefied gases, where used.
R-259 | Include at least a Sample Handling/Lysis Room and a Culture Room in the BSL-3 laboratory. | 62 | 8.13(i) | Mandatory | Design the BSL-3 laboratory with the two specified containment zones. | Yes |  |  |  | The BSL-3 laboratory shall comprise, at minimum, two distinct containment zones: (a) A Sample Handling/Lysis Room, for receipt and initial processing of incoming samples; and (b) A Culture Room, for handling of mycobacterial and other relevant infectious/viral agents.
R-260 | Ensure segregation, containment integrity and workflow continuity between BSL-3 zones, and document the risk assessment and specified facility provisions in the Basis of Design. | 62 | 8.13(ii) | Mandatory | Provide the required segregation and safety features and record the classification and secondary-barrier requirements in the Basis of Design. | Yes |  |  |  | The design shall ensure proper segregation, containment integrity, and workflow continuity between these zones, with appropriate provision for biosafety, access control, and operational safety, and shall confirm, through a documented risk assessment recorded in the Basis of Design, the precise classification and secondary-barrier requirements applicable to the facility (Class II biological safety cabinets, eyewash, hand-wash, shower provision, on-site autoclave, 100% fresh-air ventilation, and air-change rate).
R-261 | Determine the number and layout of biological safety cabinets according to the scope of work and position them away from walking areas and cross-currents. | 62 | 8.13(iii) | Mandatory | Determine and position biological safety cabinets as specified. | Yes |  |  |  | The number and layout of biological safety cabinets shall be determined by the scope of work; cabinets shall be positioned away from walking areas and cross-currents from doors and ventilation outlets.
R-262 | Provide the necessary BSL-3 ancillary and containment-supporting spaces listed in the tender. | 63 | 8.14(i) | Mandatory | Include the listed support spaces in the BSL-3 design. | Yes |  |  |  | The BSL-3 laboratory shall be supported by all necessary ancillary and containment-supporting spaces, including, without limitation: store room; anteroom/airlock; change rooms; shower rooms (preferably separate for male and female staff, where feasible within the building footprint); fumigation/decontamination room; control/monitoring room; post-shower change area; autoclave area; pass-box; dunk tank; sample storage area; locker facilities; and instrument storage space.
R-263 | Provide entry and exit through a dedicated cloth-change anteroom and shower room, with at least two anterooms and clearly illustrated clean/dedicated clothing separation and workflow. | 63 | 8.14(ii) | Mandatory | Design the entry/exit route and anteroom arrangement as specified and illustrate the layout and workflow in the drawings. | Yes |  |  |  | Entry/exit shall be through a dedicated cloth-change anteroom and, on exit, a shower room. The design shall incorporate at least two anterooms — the first for logging-in and donning of initial protective layers, and the second for donning the full complement of personal protective equipment — with clearly demarcated facilities for separating clean (street) clothing from dedicated BSL-3 laboratory clothing, the layout and workflow for which shall be clearly illustrated in the drawings.
R-264 | Make airlock, anteroom and shower doors self-closing and interlocked as required, with life-safety-compliant emergency release and fail-safe/fail-secure provisions. | 63 | 8.14(iii) | Mandatory | Provide the specified door interlocks, emergency release, alarms, interfaces, logging and controlled re-entry features. | Yes |  |  |  | All airlock, anteroom and shower doors shall be self-closing and interlocked as required for containment, but shall also include a life-safety-compliant emergency release and approved fail-safe/fail-secure philosophy. Manual emergency release/break-glass operation, fire-alarm and emergency-power interfaces, audible/visual alarm, event logging and controlled re-entry shall be defined so that no person can be trapped and normal containment logic cannot obstruct emergency egress.
R-265 | Provide a gaseous-decontamination airlock for materials and equipment that cannot be autoclaved, with interlocking doors and airlocks at every required transitional point. | 63 | 8.14(iv) | Mandatory | Provide and design the required airlocks and door interlocking arrangement. | Yes |  |  |  | An airlock with a gaseous decontamination system shall be provided for entry/exit of materials and equipment that cannot be autoclaved, with interlocking doors ensuring only one door opens at a time and the clean-side door opening only after completion of the decontamination cycle. Airlocks shall be provided at every transitional point between spaces of different bio- containment level through which personnel or materials must pass.
R-266 | Provide an independent emergency exit, keep it available without a removable key, and monitor, alarm, test and restore security and containment after emergency release. | 63 | 8.14(v) | Mandatory | Provide, monitor, alarm and test the emergency exit and define post-release restoration controls. | Yes |  |  |  | An emergency exit independent of the normal entry/exit route shall be provided and kept available without reliance on a removable key. Emergency release shall be monitored and alarmed, shall permit immediate egress, and shall be tested during SAT/IST and periodic drills. The design shall separately define the controlled response needed to restore security and containment after an emergency release.
R-267 | Provide a functionally integrated BSL-2 facility with a Positive Pressure Zone, Nucleic Acid Extraction and Purification Room, and Instrument Room. | 63 | 8.15(i) | Mandatory | Design the BSL-2 facility with the three defined operational zones. | Yes |  |  |  | The BSL-3 laboratory shall be supported by a functionally integrated BSL-2 facility, designed with three defined operational zones: (a) A Positive Pressure Zone; (b) A Nucleic Acid Extraction and Purification Room; and (c) An Instrument Room.
R-268 | Provide specified BSL-2 equipment and accommodate Real-Time PCR operations in the Instrument Room. | 63 | 8.15(ii) | Mandatory | Provide at least one biological safety cabinet, a chest freezer and refrigerated centrifuge in each specified zone, working tables and associated equipment, and accommodate Real-Time PCR in the Instrument Room. | Yes |  |  |  | The BSL-2 facility shall include, at minimum: at least one biological safety cabinet; a chest freezer (−20°C); and a refrigerated centrifuge in each of the Positive Pressure Zone and the Nucleic Acid Extraction and Purification Room; together with working tables and associated laboratory equipment. Real-Time PCR operations shall be accommodated within the Instrument Room, under appropriate environmental and operational conditions.
R-269 | Maintain functional linkage, biosafety separation, workflow efficiency and operational reliability between the BSL-2 and BSL-3 facilities. | 63 | 8.15(ii) | Mandatory | Design the two facilities to maintain the stated linkage and separation requirements. | Yes |  |  |  | The overall design shall maintain clear functional linkage with the BSL-3 facility while preserving the required biosafety separation, workflow efficiency, and operational reliability between the two areas.
R-270 | Detail all specified functional zones in architectural drawings and accompanying room data sheets. | 64 | 8.16(i) | Mandatory | Include each specified functional zone in the architectural drawings and room data sheets. | Yes |  |  |  | The spatial organisation of the facility shall provide for the following functional zones, each detailed in the architectural drawings and accompanying room data sheets:
R-271 | Provide the primary containment laboratory area with specified working, cabinet, storage, preparation and electrical provisions. | 64 | 8.16(i)(a) | Mandatory | Design and equip the primary containment laboratory area with the specified provisions. | Yes |  |  |  | Primary containment laboratory area — the core working area for all work with biological agents, including bench space for non-cabinet work, biological safety cabinet installations with adequate clearance on all sides for safe operation and maintenance access, equipment storage, and sample-preparation space, with adequate electrical outlets at bench height and, where needed, pendant ceiling outlets;
R-272 | Provide dedicated biological safety cabinet work areas isolated from air currents and traffic flow, with operator and exhaust access clearance. | 64 | 8.16(i)(b) | Mandatory | Provide and isolate biological safety cabinet work areas with the specified clearances. | Yes |  |  |  | Biological safety cabinet work areas — dedicated spaces isolated from facility air currents and traffic flow, with clearance for operator seating and access to exhaust ducting;
R-273 | Provide a decontamination/ante-area with disinfectant supplies and hand-hygiene facilities. | 64 | 8.16(i)(c) | Mandatory | Provide the specified transition zone, supplies and hygiene facilities. | Yes |  |  |  | Decontamination/ante-area — a transition zone between the laboratory and non-containment areas, equipped with disinfectant supplies and hand-hygiene facilities, designed to support proper hygiene practice before personnel move out of the containment area;
R-274 | Provide an equipment/utility room for the listed equipment and ancillary plant. | 64 | 8.16(i)(d) | Mandatory | Provide the specified equipment and utility room space. | Yes |  |  |  | Equipment/utility room — space for autoclaves, biological liquid-waste decontamination systems, air-handling units, electrical equipment and other ancillary plant;
R-275 | Provide a dedicated material pass-through area for a double-door pass-through autoclave or equivalent chamber. | 64 | 8.16(i)(e) | Mandatory | Provide the specified material transfer area and chamber. | Yes |  |  |  | Material pass-through area — a dedicated space for the double-door pass-through autoclave or equivalent chamber used to transfer materials and samples between containment and non-containment areas;
R-276 | Provide secure, climate-controlled sample/specimen storage with refrigeration at 4°C, −20°C and −80°C as required. | 64 | 8.16(i)(f) | Mandatory | Provide the specified secure storage and refrigeration temperatures as required for preservation. | Yes |  |  |  | Sample/specimen storage — secure, climate-controlled storage within the containment area, with refrigeration at 4°C, −20°C and −80°C as required for sample preservation;
R-277 | Provide a personnel donning area with specified storage and anti-cross-contamination provisions. | 64 | 8.16(i)(g) | Mandatory | Provide and design the donning area with shelving, hooks and separation of clean and contaminated items. | Yes |  |  |  | Personnel donning area — space for personnel to put on protective equipment before entry, with shelving for personal belongings and hooks for protective apparel, designed to prevent cross-contamination between clean and contaminated items;
R-278 | Provide a personnel doffing area with disposal, reusable-clothing and on-site autoclaving provisions. | 64 | 8.16(i)(h) | Mandatory | Provide the specified doffing area, containers, receptacles and autoclaving provision. | Yes |  |  |  | Personnel doffing area — space for personnel to remove protective equipment and contaminated clothing on exit, with containers for disposable items and receptacles for reusable protective clothing requiring decontamination, and provision for on-site autoclaving;
R-279 | Provide an emergency shower and eyewash station with at least one station directly accessible from the emergency exit and supplied with tepid water. | 64 | 8.16(i)(i) | Mandatory | Install the required emergency shower and eyewash facilities in the specified location and condition. | Yes |  |  |  | Emergency shower and eyewash — positioned for convenient access, with at least one shower/eyewash station having direct access to the emergency exit, supplied with tepid water in compliance with applicable emergency-fixture standards;
R-280 | Provide independent, illuminated, unobstructed emergency exits with self-closing mechanisms. | 64 | 8.16(i)(j) | Mandatory | Provide and maintain emergency exits with the specified marking, clearance and mechanisms. | Yes |  |  |  | Emergency exits — independent of the normal route, clearly marked with illuminated signage, kept clear of obstruction, and fitted with self- closing mechanisms;
R-281 | Provide an office/administrative area for documentation, record-keeping and supervisory functions. | 64 | 8.16(i)(k) | Mandatory | Provide the office/administrative area within or outside containment according to operational need. | Yes |  |  |  | Office/administrative area — for documentation, record-keeping and supervisory functions, located within or outside the containment area depending on operational need;
R-282 | Provide support spaces for supply storage, cleaning equipment and other support functions. | 64 | 8.16(i)(l) | Mandatory | Provide the specified support spaces. | Yes |  |  |  | Support spaces — for supply storage, cleaning equipment, and other support functions.
R-283 | Incorporate layered facility, building, laboratory, anteroom/airlock and emergency access controls. | 65 | 8.17(i) | Mandatory | Design and implement the five specified levels of access control and their stated features. | Yes |  |  |  | The facility design shall incorporate multiple, layered levels of access control: (a) Facility-level access — perimeter security control for the entire BSL-3 facility building/area, restricted to personnel holding valid institutional credentials; (b) Building-level access — a single designated entry point equipped with electronic access control (card reader, biometric authentication, or a combination thereof), subject to monitoring by security personnel and/or surveillance systems at all times; (c) Laboratory-level access — electronically controlled access to the primary containment laboratory, with access credentials logged and access restricted to personnel who have completed the required training and received authorisation from the Institutional Biosafety Committee; (d) Anteroom/airlock access — entry through a properly designed buffer zone, with doors to the containment and non-containment sides incapable of being opened simultaneously; and (e) Emergency access — emergency exits permitting rapid, unobstructed evacuation while incorporating alarmed or monitored egress to prevent unauthorised re-entry, without compromising safety, security or containment.
R-284 | Implement a three-tiered electronic security access-control system with the specified authentication, interlock, logging, emergency, power and cybersecurity features. | 65 | 8.17(ii) | Mandatory | Implement Tier 1, Tier 2 and Tier 3 access control with all listed system features. | Yes |  |  |  | A three-tiered electronic security access-control system shall be implemented: Tier 1 for general institutional facility access; Tier 2 for specialised laboratory access restricted to trained and authorised personnel; and Tier 3 for the BSL- 3 primary containment area requiring additional authorisation. The system shall include card or institutional-credential readers, biometric authentication at Tier 3, door interlocks with electromagnetic locks and control panels, secure communication and data backup, network integration, role-based access, event and audit logging, emergency release, fail-safe egress, backup power and cybersecurity controls.
R-285 | Provide separate ETP and dedicated EDS systems for general wastewater and biologically contaminated liquid waste. | 65 | 8.18(i) | Mandatory | Design and provide distinct ETP and EDS systems for their specified waste streams. | Yes |  |  |  | The facility shall provide purpose-specific systems for liquid effluent, which shall not be conflated with one another: (a) An Effluent treatment plant (ETP), serving the general, non-biologically- contaminated wastewater of the facility; and (b) A dedicated Effluent Decontamination System (EDS) — also referred to as a biological kill-tank system — serving exclusively the biologically contaminated liquid waste generated within the containment zone.
R-286 | Engineer the ETP/EDS with segregated waste routing and the specified EDS collection, treatment, recording, sampling, maintenance, decontamination and discharge arrangements. | 65 | 8.18(ii) | Mandatory | Engineer the systems and incorporate all specified arrangements from the earliest design stage. | Yes |  |  |  | The ETP/EDS shall be engineered. The ETP shall receive only general non-biologically contaminated wastewater. The EDS shall receive all potentially biologically contaminated liquid waste from the containment zone through fully segregated, leak-proof drainage and shall include dedicated collection and treatment tankage, pumps, instrumentation, treatment-cycle recording, sampling, safe maintenance, decontamination and controlled discharge arrangements. Their space, access, utility, maintenance and replacement requirements shall be incorporated from the earliest design stage.
R-287 | Assess and report all specified implications of the dedicated EDS at the earliest design stage, including footprint adequacy, enclosure needs, itemised cost and programme implications. | 66 | 8.18(iii) | Mandatory | Prepare and submit the required EDS assessment and report with cost and programme implications. | Yes |  |  |  | The Consultant shall assess and report the space, access, structural load, utility, ventilation, maintenance, replacement and safe-material-movement implications of the dedicated EDS at the earliest design stage. The assessment shall identify whether the existing footprint is adequate or whether reconfiguration or an additional approved enclosure is required, together with itemised cost and Program implications.
R-288 | Provide a double-sided, pass-through, double-door barrier autoclave at the containment barrier for solid waste and equipment decontamination. | 66 |  | Mandatory | Provide the specified barrier autoclave at the containment barrier. | Yes |  |  |  | A double-sided, pass-through, double-door barrier autoclave shall be provided at the containment barrier for decontamination of solid waste and equipment leaving the facility.
R-289 | Fully specify the fumigation or gaseous-decontamination airlock, BIBO filter-change arrangements, pass-through cabinets, dunk tank, interlocks, utilities, maintenance access, testing, qualification and acceptance criteria. | 66 |  | Mandatory | Include complete specifications for all listed decontamination and containment-support systems and their testing and acceptance requirements. | Yes |  |  |  | The design shall also fully specify the required fumigation or gaseous-decontamination airlock, Bag-In/Bag-Out filter-change arrangements, pass-through cabinets, dunk tank, interlocks, utilities, safe maintenance access, testing, qualification and acceptance criteria.
R-290 | The Consultant's design must include comprehensive external environment planning including landscaping compatible with BSL-3 biosafety norms, land development, grading/paving/drainage, anti-climb/anti-bird/monkey fencing, controlled access, external lighting, signage, and chiller/major utility-equipment locations. | 67 | 8.19(i) | Mandatory | Plan and design the external environment, landscaping, site grading/drainage, boundary wall/fencing, security, lighting, signage, and utility-equipment placement compliant with BSL-3 norms. | Yes |  |  |  | The design shall include comprehensive planning of the external environment, comprising: landscaping compatible with BSL-3 biosafety norms and avoidance of pest/vector harbourage; land development and refurbishment of surrounding areas including grading, paving and drainage; design of the entry gate and boundary wall/fencing, incorporating anti-climb and anti- bird/monkey measures (e.g., wired fencing), controlled access points, and security features; external lighting, pathway illumination, and signage (including biosafety and biomedical-waste signage); and identification and planning of chiller and major utility-equipment locations ensuring safe, accessible, and non-contaminating placement.
R-291 | The Consultant must prepare a coordinated Signage and Identification Schedule covering statutory, fire, biohazard, route, exit, room, door, waste, and utility signage. | 67 | 8.19(ii) | Mandatory | Prepare and coordinate a detailed Signage and Identification Schedule across architectural, fire, security, and O&M documents detailing location, legend, language, material, size, illumination, fixing detail, and responsibility. | Yes |  |  |  | The Consultant shall prepare a coordinated Signage and Identification Schedule covering statutory and fire signage, biohazard and access warnings, personnel/material/waste routes, emergency exits and assembly points, room and door identification, biomedical-waste identification, utility/equipment labels and operational notices. The schedule shall show location, legend, language, material, size, illumination/photoluminescence where required, fixing detail and responsibility, and shall be coordinated across architectural, fire, security and O&M documents.
R-292 | The Consultant must verify existing lift space, staircases, and equipment-movement routes, and obtain prior approval from AIIMS Patna for any structural alterations or new openings. | 67 | 8.20(i) | Mandatory | Verify clear dimensions, load capacities, door openings, and fire safety interfaces of existing vertical transport and routes, and obtain AIIMS Patna approval with itemised costs and program impact before assuming new structural openings or shafts. | Yes |  |  |  | The Consultant shall verify the existing lift space, staircase and equipment- movement routes, including clear dimensions, load capacity, door openings, fire and life-safety interfaces and access to all required levels. Retention, upgrade or provision of a service lift or dumbwaiter shall be recommended only where justified by the equipment and material-movement study. Any new shaft, structural opening, lintel alteration or terrace or upper-level work shall require necessary inputs, statutory feasibility, itemised cost and program impact, budget availability and prior approval of AIIMS Patna and shall not be included as an unapproved baseline assumption. Zoning, donning and doffing, controlled movement, storage, standby wiring and future-access provisions shall be coordinated with the approved option.
R-293 | All interior surfaces, fixtures, floors, walls, ceilings, benchtops, furniture, doors, windows, penetrations, electrical outlets, and lighting fixtures within the containment laboratory must comply with decontamination and biosafety specifications. | 68 | 8.21(i) | Mandatory | Design and specify all containment laboratory interior surfaces and fixtures to be seamless, chemical/heat/disinfectant resistant, non-porous, airtight, and sealed according to specified parameters (e.g., epoxy-resin seamless coved flooring, fixed double-glass windows, sealed penetrations). | Yes |  |  |  | All interior surfaces, fixtures and materials within the containment laboratory shall support decontamination, cleanability, and prevention of harbourage of biological agents, in accordance with the following minimum specification: (a) Floors — seamless, monolithic, impervious to liquids, abrasion- resistant, non-slip when wet, and capable of withstanding disinfectants and hot water (up to approximately 82°C) with detergents under hose pressure; epoxy-resin (or equivalent) flooring is required, with no open seams permitted, and an integral cove base running continuously up the wall at every floor-wall junction; (b) Walls — constructed of non-porous materials, finished with industrial- grade epoxy, polyurethane, or low-lustre acrylic/latex enamel paint; surfaces shall be scratch-, stain-, moisture-, chemical- and heat- resistant, and resistant to the disinfection and fumigation agents to be used in the facility (e.g., formaldehyde, vapour-phase hydrogen peroxide, or peracetic acid, as selected by the Consultant in consultation with the user);Ceilings — monolithic, resistant to liquids and chemicals, with all penetrations sealed, and continuity of seal maintained at every wall- ceiling interface; (c) Bench tops — impervious to water, resistant to disinfectants, acids, alkalis, organic solvents and moderate heat; monolithic, with no open seams, fitted with marine edges/drip-stops for spillage containment, and backsplashes (where provided) sealed tight to the wall; (d) Laboratory furniture — fit for purpose, with open spaces between and under benches, cabinets and equipment accessible for cleaning; doors, drawers and handles with rounded rims/corners; cabinet doors self- closing and lockable; drawers of one-piece construction with catches; and reagent shelving fitted with lip edges; (e) Doors — designed to ensure controlled access, proper sealing, and safe operation, configured to prevent unintended airflow or cross- contamination, with vision panels to avoid accidents on opening, appropriate fire rating, self-closing mechanisms, and international biohazard signage wherever biohazardous material is handled or stored; (f) Windows — where provided, fixed (non-openable), sealed, and constructed of unbreakable double glass, maintaining containment integrity at all times; no operable windows are permitted anywhere within the containment envelope; (g) Penetrations — all utility and service penetrations executed to ensure airtightness, sealing integrity, and ease of inspection and maintenance, without compromising containment; (h) Electrical outlets and switches — designed for safe operation, protection from environmental exposure, and compatibility with cleaning/decontamination requirements; and (i) Lighting fixtures — sealed and flush-integrated with the building envelope, compatible with cleaning and decontamination processes,
R-294 | Mock-up samples of all proposed finish systems along with manufacturer performance certification and chemical-resistance data must be submitted to AIIMS Patna. | 69 | 8.21(iv) | Mandatory | Prepare and submit mock-up samples and manufacturer chemical-resistance/performance certifications for all proposed finish systems to AIIMS Patna. | Yes |  |  |  | Mock-up samples of all proposed finish systems shall be prepared and submitted to AIIMS Patna, together with manufacturer performance certification and chemical-resistance data confirming compatibility with every disinfectant and room-decontamination agent proposed for routine cleaning, spill response, fumigation and emergency decontamination.
R-295 | Evacuation routes from the containment laboratory must have illuminated signage, emergency lighting, unobstructed path, smoke control, and coordinated fire/life-safety features preventing circulation back into contaminated areas. | 69 | 8.22(i) | Mandatory | Design life-safety egress routes with illuminated signage, emergency lighting, and proper fire/containment logic coordination. | Yes |  |  |  | Evacuation routes from the containment laboratory to external safety shall be clearly marked with illuminated signage, maintained free of obstruction, lit by emergency lighting during power failure and sized for rapid egress of all personnel. The design shall prevent circulation back into contaminated areas and shall coordinate fire-rated construction, smoke control, fire detection and alarm, emergency communication, door release, emergency power, assembly points and life-safety-compliant egress without allowing containment logic to trap personnel.
R-296 | Emergency decontamination capability must be provided for personnel during evacuation, including emergency showers and change facilities. | 69 | 8.22(ii) | Mandatory | Include emergency decontamination showers, change facilities for contaminated clothing removal, PPE receptacles, and medical evaluation connectivity provisions in the facility design. | Yes |  |  |  | Emergency decontamination capability for personnel during evacuation shall include an emergency shower capable of decontaminating personnel before leaving the facility, change facilities for removal of contaminated clothing, receptacles for contaminated clothing/PPE, and provision for connecting evacuated personnel to medical evaluation where exposure may have occurred.
R-297 | First-aid facilities and an integrated medical-emergency response plan covering fire, flood, and system failure emergencies must be designed and indicated in drawings. | 70 | 8.22(iii) | Mandatory | Incorporate accessible first-aid facilities into drawings and integrate a comprehensive medical-emergency response plan into facility design and safety protocols. | Yes |  |  |  | First-aid facilities shall be readily accessible and suitably equipped and stocked, with location indicated in the drawings. A medical-emergency response plan, addressing first aid and internal incident response, and preparedness for fire, flood, and system-failure emergencies, shall be integrated into the design and into the facility's safety protocols.
R-298 | The Consultant must independently conduct a structural assessment of the existing structure against seismic and structural provisions and design/cost retrofitting measures in the DPR. | 71 | 8.23(i) | Mandatory | Perform an independent structural assessment of the existing building and incorporate necessary retrofitting designs and costs into the DPR. | Yes |  |  |  | Since the BSL-3 facility is proposed within an existing building, the Consultant shall conduct a structural assessment of the existing structure against current seismic and structural design provisions and identify any deficiency. Where deficiency is found, retrofitting measures shall be designed and costed as part of the DPR. AIIMS Patna's preliminary understanding is that the building was constructed with containment-facility considerations in view; this must nonetheless be independently verified by the Consultant and not assumed.
R-299 | The Consultant must submit equipment-load schedules at the earliest design stage and check floors and structural members for vibration performance and live/dead loads. | 71 | 8.23(ii) | Mandatory | Submit equipment-load schedules early and perform floor vibration and load analysis for heavy or vibration-sensitive equipment. | Yes |  |  |  | In addition to seismic design, floors and structural members carrying autoclaves, air-handling units, biological safety cabinets and other vibration- sensitive or heavy equipment shall be checked for floor vibration performance and equipment-imposed live/dead loads. The Consultant shall submit equipment-load schedules to design team at the earliest design stage to avoid late-stage redesign.
R-300 | The structural assessment must record feasibility of proposed alterations and heavy plant locations; no alterations may be included in the BOQ/base design without structural verification, statutory feasibility, and itemised costs. | 71 | 8.23(iii) | Mandatory | Verify and document structural feasibility, statutory compliance, and itemised costs for any proposed alterations, structural openings, or heavy plant locations before including them in the design/BOQ. | Yes |  |  |  | The structural assessment shall specifically record the feasibility and implications of any proposed alteration, new opening or lintel, terrace service platform/enclosure, upper-level or third-floor intervention, and heavy plant location. No such intervention shall be carried into the base design or BOQ without structural verification, statutory feasibility and itemised cost.
R-301 | Structural members enclosing or supporting containment ductwork and boundaries must withstand 1.25 times maximum design pressure under fan-failure conditions without distortion, damage, or loss of seal integrity. | 71 | 8.24(i) | Mandatory | Design and coordinate structural, partition, and ductwork systems to maintain stability and seal integrity under 1.25 times maximum design differential pressure during supply/exhaust fan failure. | Yes |  |  |  | Structural members supporting or enclosing the containment zone's ductwork and pressure boundaries shall be designed for stability under 1.25 times (indicative) the maximum design pressure anticipated during supply or exhaust fan-failure conditions, with no wall distortion or damage permitted. The Consultant shall coordinate the structural, partition and low-leakage ductwork systems so that the containment envelope withstands the design differential pressure without loss of seal integrity and satisfies the approved room-integrity and pressure-decay acceptance criteria.
R-302 | Every room-wise HVAC design value must be supported by approved Basis of Design, heat-load and airflow calculations, biosafety risk assessment, failure-mode analysis, and commissioning/validation criteria. | 72 | CHAPTER 6 (i) | Mandatory | Provide room-wise design values substantiated by the Basis of Design, calculations, biosafety risk assessment, failure-mode analysis, and validation criteria. | Yes |  |  |  | Every room-wise design value shall be supported by the approved Basis of Design, heat-load and airflow calculations, biosafety risk assessment, failure-mode analysis and measurable commissioning and Validation criteria.
R-303 | The BSL-3 containment HVAC system must be dedicated and independent from the institution's general HVAC system. | 72 | 8.25 (i) | Mandatory | Design and provide a dedicated, independent HVAC system for the BSL-3 zone with no shared components with the general HVAC system. | Yes |  |  |  | The HVAC system serving the BSL-3 containment zone shall be a dedicated, independent system, not connected to and not sharing any component with the institution's general HVAC system, eliminating any possibility of cross- contamination between the BSL-3 facility and other institutional areas.
R-304 | Separate AHUs must be provided for containment, non-containment, and isolation zones, constructed of double-skin, thermally insulated, low-leakage design with antimicrobial interior coating. | 72 | 8.25 (i) | Mandatory | Provide separate double-skin, thermally insulated, low-leakage AHUs with internal antimicrobial coating for containment and non-containment zones. | Yes |  |  |  | Separate air-handling units (AHUs) shall be provided for containment and non-containment zones, and separate AHUs for each isolation zone within the containment area wherever such isolation is required. AHUs serving the containment zone shall be of double-skin, thermally insulated, low-leakage construction, with internal surfaces finished in an antimicrobial coating to limit microbial growth within the unit over its service life.
R-305 | Containment AHUs must supply 100% once-through fresh air without recirculation. | 72 | 8.25 (ii) | Mandatory | Ensure each AHU serving containment areas supplies 100% fresh air with zero recirculation from the containment zone. | Yes |  |  |  | Each AHU serving a containment area shall supply 100% fresh air, with no recirculation of air from the containment zone.
R-306 | Airflow must strictly flow from clean to dirty zones, and a documented airflow schematic must be submitted at design stage. | 72 | 8.25 (iii) | Mandatory | Submit a documented airflow schematic at design stage proving unidirectional airflow from clean to dirty areas and eliminating stagnant zones. | Yes |  |  |  | Airflow direction shall at all times be from less-contaminated to more- contaminated areas, and within the containment area, from entrance towards the rear/innermost zone. The system shall be designed to strictly preclude any recirculation pathway or dead/stagnant zone, with a documented airflow schematic demonstrating the unidirectional path from clean to dirty zones, to be submitted at the design stage.
R-307 | Exhaust air from containment must discharge through a dedicated system with HEPA filtration, safe isolation, in-situ test access, downstream fan, and roof discharge. | 72 | 8.26 (i) | Mandatory | Incorporate a dedicated exhaust system with HEPA filters, isolation, test ports, downstream fan configuration, and roof discharge. | Yes |  |  |  | Air from the containment zone shall be exhausted through a dedicated system with HEPA filtration, safe isolation, in-situ test access, downstream fan arrangement and roof discharge.
R-308 | The exhaust system must include pressure relief to prevent reverse airflow transients. | 72 | 8.26 (ii) | Mandatory | Provision pressure relief in the exhaust system to prevent unintended pressure transients from causing reverse airflow out of containment. | Yes |  |  |  | The exhaust system shall provision for pressure relief, such that no unintended pressure transient (whether from fan start/stop, damper actuation, or door operation) is capable of forcing reverse airflow out of the containment zone.
R-309 | The Consultant must calculate and establish a pressure cascade maintaining at least 15 Pa differential between adjacent spaces, with the laboratory negative relative to lower-risk spaces. | 73 | 8.27 (i) | Mandatory | Calculate and finalize negative pressure cascade maintaining a minimum 15 Pa differential between adjacent zones. | Yes |  |  |  | The Consultant shall determine, through pressure-cascade calculation and risk assessment, the negative- pressure regime appropriate to each zone of the facility, such that the containment laboratory is maintained at a differential negative pressure of not less than 15 Pascal (Pa) relative to the immediately adjoining lower-risk space at every stage of the cascade.
R-310 | Differential pressure readings must reference a single common atmospheric set point with continuous BAS monitoring and alarming. | 73 | 8.27 (ii) | Mandatory | Reference all pressure readings to a single common atmospheric setpoint and integrate continuous measurement, display, and alarms into BAS. | Yes |  |  |  | All negative-pressure readings shall be referenced to a single, common atmospheric set point for the facility, with continuous measurement, display, and BAS-integrated monitoring and alarming of pressure differentials at each zone boundary.
R-311 | Supply and exhaust fans must be interlocked with fail-safe control logic to ensure the containment space never achieves positive pressure. | 73 | 8.27 (iii) | Mandatory | Interlock supply fan to start only after exhaust fan confirmation, and tune control logic/isolation dampers so containment never goes positive upon fan failure. | Yes |  |  |  | The supply fan shall be interlocked to start only after the exhaust fan has been switched on and verified running, preventing positive pressurisation at start-up. On failure of either the supply or exhaust fan, the control logic shall ensure that supply airflow reduces at least as quickly as exhaust airflow, such that the containment space never goes positive; isolation-damper closing rates shall be tuned so that the affected ("lagging") system is isolated faster than the unaffected ("leading") system on any single-point fault.
R-312 | A visual strobe alarm must trigger along with audible alarm if pressure reverses for more than ~20 seconds or on HVAC failure. | 73 | 8.27 (iii) | Mandatory | Incorporate visual strobe and audible alarms activated upon space pressure reversal exceeding approx. 20 seconds or any HVAC failure. | Yes |  |  |  | Where any space pressure reverses relative to its intended condition for more than approximately 20 seconds (indicative), or on any HVAC failure, a visual strobe alarm shall be triggered in addition to the audible alarm.
R-313 | Exhaust discharge must maintain negative pressure under all weather conditions and achieve a minimum discharge velocity of 3000 fpm (900 m/min). | 73 | 8.27 (iv) | Mandatory | Design exhaust discharge to maintain negative pressure in all weather conditions with an exhaust discharge velocity of not less than 3000 fpm. | Yes |  |  |  | The Consultant shall design the HVAC system to sense and respond to unusual outside pressure conditions (such as storms) and to maintain negative pressure in the containment area under all weather conditions, sizing the exhaust discharge for a velocity the Consultant determines adequate for this purpose, which shall in no case be less than 3000 fpm (approximately 900 metres per minute).
R-314 | Room-wise ACH must be calculated with a minimum baseline of 8 ACH and a normal design range of 8–12 ACH. | 74 | 8.28 (i) | Mandatory | Calculate room-wise ACH using 8 ACH as the lower bound and 8–12 ACH as the normal design range. | Yes |  |  |  | The Consultant shall calculate and state the room- wise design ACH from the approved activity, risk, heat load, occupancy and equipment density. Based on the present project baseline, 8 ACH shall be treated as the lower bound and the normal design range shall be 8–12 ACH, with a higher value adopted where the calculation, applicable national requirement or approved risk assessment requires it.
R-315 | Airflow patterns must be verified during commissioning using visual smoke-pencil or tracer-particle testing. | 74 | 8.28 (iv) | Mandatory | Conduct smoke-pencil or tracer-particle testing during commissioning to verify unidirectional airflow from low- to high-contamination areas. | Yes |  |  |  | Verification of airflow patterns — by visual smoke- pencil or equivalent tracer-particle testing, demonstrating a unidirectional smoke pattern from low- to high-contamination areas — shall be conducted during commissioning to confirm compliance with design intent.
R-316 | Exhaust HEPA/ULPA filtration technical baseline efficiency must not be lower than 99.97% at 0.3 micron. | 75 | 8.29 (i) | Mandatory | Specify HEPA/ULPA filters with a minimum efficiency of 99.97% at 0.3 micron for containment exhaust. | Yes |  |  |  | The Consultant shall specify HEPA or ULPA filtration for exhaust from containment equipment and the containment area in accordance with the governing national requirement, approved biosafety risk assessment and Basis of Design. The technical baseline shall not be lower than 99.97% efficiency at 0.3 micron.
R-317 | Supply air to containment must have a pre-filter stage upstream of final filtration. | 75 | 8.29 (ii) | Mandatory | Provide a pre-filter stage upstream of final supply air filters. | Yes |  |  |  | Incoming air to containment areas shall be filtered to maintain the required environmental quality and protect personnel and operations, with a pre-filter stage upstream of the final filtration stage to extend service life.
R-318 | HEPA filters must be sized at approximately 50% of rated capacity for progressive dust loading margin. | 75 | 8.29 (iv) | Mandatory | Size HEPA filters at approx. 50% of rated capacity to account for dust loading. | Yes |  |  |  | HEPA filters shall be sized at approximately 50% of their rated capacity, providing adequate margin for progressive dust loading over the service life of the filter while maintaining required airflow and pressure relationships; this sizing approach, together with the associated performance parameters, shall be detailed at the design-development stage.
R-319 | HEPA filter housings must include upstream/downstream zero-leakage bio-seal dampers, DP gauges, scan-test ports, and chemical decontamination ports. | 75 | 8.29 (v) | Mandatory | Equip HEPA housings with zero-leakage bio-seal dampers on both sides, DP meters, in-situ scan-test ports, and chemical injection ports. | Yes |  |  |  | HEPA filter housings shall be robust, adequately supported, and airtight, with: isolation valves (zero-leakage bio- seal dampers) on both the upstream and downstream sides, to permit safe isolation for maintenance and for gaseous decontamination of the housing; a pressure-differential gauge/meter indicating filter loading/choking status; in- situ leak-testing facility (scan-test ports) to verify filter and housing integrity after installation and periodically thereafter; and provision for chemical injection to decontaminate the filter prior to removal/replacement.
R-320 | A Bag-In-Bag-Out (BIBO) filter housing and replacement system must be provided for all containment HEPA filter banks. | 75 | 8.29 (vi) | Mandatory | Provide BIBO housing systems for all containment HEPA filter banks to allow filter removal without containment breach. | No — check |  |  |  | A Bag- In-Bag-Out (BIBO) filter housing/replacement system shall be provided as the standard arrangement for all containment HEPA filter banks, to permit safe removal of contaminated filters without breach of containment; filters shall be decontaminated (typically by steam sterilisation or chemical treatment) before disposal or incineration.
R-321 | Containment supply and exhaust ductwork must be airtight, leak-proof SS-304, with no internal duct lining and no flexible ductwork. | 76 | 8.30 (i) | Mandatory | Construct containment ductwork from SS-304 stainless steel without internal duct lining or flexible ducting in containment/critical exhaust paths. | Yes |  |  |  | Supply and exhaust ductwork within the contaminated zone shall be airtight, leak-proof, and constructed of stainless steel (SS-304), resistant to corrosion and compatible with the fumigation/decontamination agents to be used. Duct lining shall not be used for acoustic or any other purpose anywhere within containment ductwork, and flexible ductwork shall not be used within the containment envelope or in any critical exhaust path.
R-322 | Ductwork must be pressure tested before commissioning at +1000 Pa with pressure drop under 0.1% of duct volume per minute. | 76 | 8.30 (ii) | Mandatory | Test ductwork using soap-bubble or pressure-decay testing at +1000 Pa test pressure with leakage under 0.1% volume/min; keep joints exposed until validated. | Yes |  |  |  | Ductwork shall be tested for leakage prior to commissioning by the soap- bubble test or by the pressure-decay method at +1000 Pa test pressure, with an acceptance criterion of pressure drop less than 0.1% of duct volume per minute. All welds and duct joints shall remain exposed and accessible for inspection and repair until this testing is complete and validated; where leakage is found, the affected joint shall be repaired and the section re-tested.
R-323 | Zero-leakage bio-seal isolation dampers must be placed between room supply/exhaust terminals and grilles, accessible outside containment. | 76 | 8.30 (iii) | Mandatory | Install airtight isolation dampers between room terminals and diffusers/grilles, with maintenance/operational access located outside the containment suite. | Yes |  |  |  | Isolation dampers shall be located between the room supply air terminal and the room supply diffuser, and between the room exhaust grille and the room exhaust air terminal, with access for maintenance and operation from outside the laboratory suite rather than from within the containment space. All supply and exhaust dampers shall be airtight and tested before installation.
R-324 | Supply intake and exhaust discharge must be separated by at least 7 metres or greater based on dispersion study, with discharge vertically upward at minimum 3000 fpm. | 76 | 8.31 (i) | Mandatory | Separate supply intake and vertical exhaust discharge by minimum 7 metres (or per dispersion study) and discharge upward at no less than 3000 fpm (900 m/min). | Yes |  |  |  | Exhaust air shall be discharged preferably from the roof and vertically upward at a velocity adequate to maintain containment under all weather conditions and in no case less than 3000 feet per minute, approximately 900 metres per minute, with the discharge point protected against rainwater ingress. The supply-air intake and exhaust discharge shall be separated by not less than 7 metres or by a greater distance established through a site-specific air- dispersion study.
R-325 | Outside-air intakes must have bird screens (6 mm or 12 mm mesh) and be designed to prevent rain ingress into supply-air filters. | 76 | 8.31 (ii) | Mandatory | Fit outdoor air intakes with 6 mm or 12 mm bird screens and rain ingress protection. | Yes |  |  |  | Outside-air intakes shall be protected against rain ingress by a bird screen (6 mm or 12 mm mesh as appropriate), and shall be positioned and designed so that rain does not wet or clog the supply-air filters.
R-326 | Where multiple biological safety cabinets are manifolded into a common exhaust plenum, the Consultant must demonstrate by calculation that the plenum is sized for combined airflow without back-pressure and prevents back-drafting. | 77 | 8.32 (ii) | Mandatory | Demonstrate by calculation that the common exhaust plenum is sized to handle combined airflow without back-pressure and ensure design prevents back-drafting between cabinets. | Yes |  |  |  | Where multiple cabinets are manifolded into a common exhaust plenum, the Consultant shall demonstrate, by calculation, that the plenum is sized to handle the combined airflow without back-pressure, and that the design prevents back-drafting between cabinets (through appropriate baffles/separators where needed) before connecting to the facility's HEPA filtration and exhaust train.
R-327 | Relative humidity must generally be maintained between 30% and 60% with appropriate humidification or dehumidification equipment. | 77 | 8.33 (ii) | Mandatory | Include humidification or dehumidification equipment to maintain relative humidity between 30% and 60%, confirming room-specific set points during detailed design. | Yes |  |  |  | Relative humidity shall be maintained generally within the range of 30% to 60%, to avoid static-electricity discharge and discomfort at the lower bound and to avoid condensation and microbial growth at the upper bound; appropriate humidification or dehumidification equipment shall be included to maintain this range under varying external humidity conditions, with the specific set point for each room confirmed at the detailed design stage having regard to the equipment and work conducted in that room.
R-328 | Internal acoustic lining must not be used within containment ductwork. | 78 | 8.34 (i) | Mandatory | Ensure internal acoustic lining is not used within containment ductwork and achieve acoustic control through external treatment, silencer design, and vibration isolation. | Yes |  |  |  | Internal acoustic lining shall not be used within containment ductwork because it may impair cleanability, decontamination and integrity.
R-329 | The FMEA for containment HVAC must cover AHUs, fans, chillers/heat-rejection, controls, power, dampers, and filtration, with details reflected in schematics, control narrative, matrix, BOQ, and IST criteria. | 78 | 8.35 (ii) | Mandatory | Perform FMEA for containment HVAC covering specified equipment and show standby arrangements, automatic changeover, and isolation across tender schematics, control narrative, cause-and-effect matrix, BOQ, and IST acceptance criteria. | Yes |  |  |  | For containment HVAC, the FMEA shall address AHUs, supply/exhaust fans, chillers or heat-rejection equipment, controls, power, dampers and filtration. The selected standby arrangement, automatic changeover, maintenance isolation and performance during changeover shall be shown in the schematics, control narrative, cause-and-effect matrix, BOQ and IST acceptance criteria.
R-330 | Emergency electrical power for containment fans, dampers, and controls must be available within 10 seconds of normal power interruption. | 78 | 8.35 (iii) | Mandatory | Design and provide emergency electrical power systems capable of powering containment fans, dampers, and controls within 10 seconds of a normal power outage. | Yes |  |  |  | Emergency electrical power for all fans, dampers, and controls required to maintain containment shall be available within 10 seconds of a normal-power interruption.
R-331 | Ventilation-system performance for the containment zone must be tested with calibrated instruments following ANSI/ASSP Z9.14 or an equivalent recognized standard. | 78 | 8.35 (iv) | Mandatory | Test containment zone ventilation performance using calibrated instruments under recognized standards such as ANSI/ASSP Z9.14. | Yes |  |  |  | Ventilation-system performance for the containment zone, including directional airflow, pressure differentials, air-change rate, door-opening recovery, failure-mode response, containment integrity, HEPA integrity, alarms, interlocks and integrated control, shall be tested with calibrated instruments using recognised performance-verification methods suitable for BSL-3 ventilation systems, such as ANSI/ASSP Z9.14 or an equivalent recognised standard.
R-332 | Differential-pressure sensors must measure pressure differentials with an accuracy of ±0.5 Pa and be subject to periodic calibration. | 79 | 8.36 (i) | Mandatory | Install differential-pressure sensors accurate to ±0.5 Pa with proper tubing/venting and implement a defined periodic calibration schedule. | Yes |  |  |  | Sensors shall have a range and sensitivity sufficient to resolve differentials with an accuracy of ±0.5 Pa, shall be installed with appropriate tubing/venting to avoid measurement error from vibration or thermal effects, and shall be subject to a defined periodic calibration schedule.
R-333 | The BAS must maintain detailed records of parameters, events, alarms, adjustments, and maintenance retained for a minimum of 5 years. | 80 | 8.38 (iv) | Mandatory | Configure the BAS to retain operational records, parameter logs, time-stamped alarms, adjustments, and calibration activities for at least 5 years. | Yes |  |  |  | The BAS shall maintain detailed records of all measured parameters, all equipment operation events, all alarm/alert events with time stamps, all manual adjustments by personnel, and all maintenance/calibration activities performed, retained for a minimum of 5 years, to document facility performance and to support certification and re-validation.
R-334 | The Consultant must develop a detailed Sequence of Operations document for the BAS for review by AIIMS Patna prior to procurement and installation. | 80 | 8.38 (v) | Mandatory | Prepare and submit a detailed Sequence of Operations document for the BAS covering normal, fault, override, and restoration modes for AIIMS Patna's review. | Yes |  |  |  | The Consultant shall develop a detailed Sequence of Operations document for the BAS, covering normal operation, fault conditions, emergency override, and power-restoration behaviour, for AIIMS Patna's review prior to BAS procurement and installation.
R-335 | The building automation system must communicate using open protocols like BACnet or Modbus and incorporate cybersecurity measures. | 80 | 8.38 (vi) | Mandatory | Implement open industry-standard communication protocols (BACnet or Modbus) and incorporate cybersecurity controls including authentication, RBAC, encryption in transit, firewalls, and audit logging. | Yes |  |  |  | The building automation system shall communicate using open, industry-standard protocols (such as BACnet or Modbus, or an equivalent open protocol) to avoid vendor lock-in and to facilitate future integration and expansion, and the overall network architecture — including the BAS, access-control, and CCTV networks — shall incorporate appropriate cybersecurity measures (user authentication, role-based access control, data encryption in transit, firewall protection, and audit logging) consistent with the sensitivity of the data and systems involved.
R-336 | The facility must be equipped with a biological liquid-waste decontamination system sized for worst-case throughput using either chemical disinfection or steam-based decontamination. | 81 | 8.40 (i) | Mandatory | Design and provide a biological liquid-waste decontamination system sized for worst-case throughput, selecting chemical disinfection or thermal steam-based decontamination based on agent risk assessment. | Yes |  |  |  | The facility shall be provided with a biological liquid-waste decontamination system for the safe collection, storage, treatment and disposal of laboratory-generated liquid waste. The system shall be sized for the anticipated worst-case operational throughput of the facility, and shall achieve effective treatment and decontamination through one of the following validated approaches, to be selected by the Consultant based on the nature of agents handled and confirmed through the risk assessment:
R-337 | Autoclave and decontamination-system condensate must be cooled before entering the drainage system and routed through treatment without bypassing. | 81 | 8.40 (ii) | Mandatory | Cool condensate prior to discharge into drainage and route it through the decontamination treatment system without allowing any bypass. | Yes |  |  |  | Autoclave/decontamination-system condensate shall be cooled before entering the drainage system to prevent thermal stress on pipes, and shall be routed through the treatment system before discharge — it shall not bypass treatment.
R-338 | A double-sided, pass-through, double-door barrier autoclave with HEPA-filtered exhaust must be installed at the containment barrier. | 81 | 8.41 (i) | Mandatory | Install a double-door pass-through barrier autoclave with HEPA-filtered exhaust and required service connections at the containment boundary. | Yes |  |  |  | A double-sided, pass-through, double-door barrier autoclave shall be installed at the containment barrier, providing: a double-door design permitting loading from the containment area and removal from the non-containment area without direct connection between the two; a chamber size adequate for anticipated waste volumes and equipment to be sterilised; validated cycle parameters appropriate to different waste types (wrapped items, unwrapped items, liquids, fabric materials, with or without pre/post-vacuum, as applicable); HEPA-filtered exhaust to prevent environmental release of steam or aerosols; and connection to the facility's supply water and drainage systems.
R-339 | Autoclave must be PLC-controlled, record cycle data, have interlocked doors that open only after a validated cycle, and undergo IQ, OQ, and PQ through approved protocols. | 82 | 8.42(ii) | Mandatory | Design/provide a PLC-controlled autoclave that records cycle data, locks the clean-side door until cycle completion, resets the timer if temperature drops, and conduct IQ/OQ/PQ validation with signed reports. | Yes |  |  |  | The autoclave shall be PLC-controlled and capable of recording complete real- time cycle data, including temperature, pressure, exposure time and cycle type. The clean-side door shall open only after successful completion of the validated decontamination cycle; if temperature falls below the validated set point, the exposure timer shall reset. All cycle records shall be retained, and laboratory clothing shall be decontaminated before laundering. Installation Qualification, Operational Qualification and Performance Qualification shall be conducted through approved protocols, calibrated instruments, defined loading patterns, biological indicators, acceptance criteria, deviation control, retesting and signed reports.
R-340 | Provide a fumigation airlock or chemical/gaseous decontamination chamber with door interlocking for items that cannot be steam-autoclaved, incorporating a neutralization step for formaldehyde fumigation. | 82 | 8.42(iii) | Mandatory | Incorporate a fumigation airlock or chemical/gaseous decontamination chamber at the barrier with door interlocking, including an ammonia neutralization step if formaldehyde is used. | Yes |  |  |  | For equipment and materials that cannot be steam-autoclaved (e.g., heat- sensitive instruments, films, certain samples), a fumigation airlock or chemical/gaseous decontamination chamber shall be provided at the barrier, with door interlocking such that the clean-side door opens only after the decontamination cycle is complete; where formaldehyde fumigation is used, a neutralisation step (e.g., ammonia) shall be incorporated.
R-341 | Provide a Bag-In-Bag-Out (BIBO) system for items too large for the pass-through autoclave. | 82 | 8.42(iv) | Mandatory | Provide a BIBO system permitting double-bagging of contaminated material within the lab, external bag decontamination, transfer via pass-through box/chamber with decontamination capability, and final removal in non-contaminated form. | Yes |  |  |  | A Bag-In-Bag-Out (BIBO) system shall be provided for items too large for the pass-through autoclave (such as HEPA filters requiring replacement), permitting: double-bagging of contaminated material within the laboratory; external bag decontamination after removal; passage through a pass-through box or chamber with decontamination capability; and final removal in non- contaminated form for appropriate disposal.
R-342 | Provide pass-through cabinets and/or a dunk tank for transfer of biological materials between zones, with door interlocking and override facility. | 82 | 8.42(v) | Mandatory | Install interlocked pass-through cabinets and/or a dunk tank with override facility, ensuring any dunk-tank partition depth exceeds the expected maximum pressure differential across the barrier. | Yes |  |  |  | Pass-through cabinets and/or a dunk tank shall be provided for transfer of biological materials between zones, with door interlocking and override facility; the depth of any dunk-tank partition shall exceed the expected maximum pressure differential across the barrier. The need for and configuration of the dunk tank shall be determined by the risk assessment.
R-343 | Design plumbing, drainage, effluent decontamination, and wastewater treatment systems as an integrated yet segregated arrangement. | 82 | 8.42 | Mandatory | Design plumbing, drainage, EDS, and ETP systems to prevent cross-connection, backflow, leakage, or unintended release of biologically contaminated effluent. | Yes |  |  |  | The Consultant shall design the plumbing, drainage, effluent decontamination and wastewater treatment systems as an integrated yet appropriately segregated arrangement, ensuring safe collection, conveyance, treatment and discharge of all liquid waste generated within the facility. The design shall prevent cross- connection, backflow, leakage or unintended release of biologically contaminated effluent and shall support reliable operation, maintenance, monitoring, validation and regulatory compliance.
R-344 | Provide two distinct, purpose-specific systems: an Effluent Treatment Plant (ETP) for general wastewater and a dedicated Effluent Decontamination System (EDS) for containment-zone liquid waste. | 82 | 8.43 | Mandatory | Ensure the facility includes separate ETP and EDS systems that are not conflated with one another. | Yes |  |  |  | The facility shall provide two distinct, purpose-specific systems, which shall not be conflated with one another: (i) An Effluent Treatment Plant (ETP), serving the general, non-biologically- contaminated wastewater of the facility (washroom and general support-area discharge, where such discharge does not originate from within the containment zone), sized and designed to meet applicable environmental discharge standards before release to the municipal sewer; and (ii) A dedicated Effluent Decontamination System (EDS) — also referred to as a biological kill-tank system — serving exclusively the biologically contaminated liquid waste generated within the containment zone (floor drains, sinks,
R-345 | Provide a dedicated containment-grade EDS with collection and kill tankage, segregated leak-proof drainage, duty/standby pumps, instrumentation, and validated decontamination. | 83 | 8.43(iii) | Mandatory | Design and provide a containment-grade EDS comprising collection tankage, worst-case load kill tankage, dedicated leak-proof drainage, duty and standby pumps, recording instrumentation, and validated treatment method. | Yes |  |  |  | The EDS shall be a dedicated containment-grade system comprising, at minimum, collection tankage; kill tankage sized for the facility's worst-case batch or continuous-flow biological-waste load; dedicated leak-proof drainage from every containment-zone liquid-waste outlet; complete segregation from the general ETP; duty and standby transfer or circulation pumps; and instrumentation for temperature, pressure, pH where relevant, cycle time, treatment status and permanent cycle recording. Treatment shall use validated chemical disinfection, steam or thermal decontamination, or another approved method selected for the biological agents and waste characteristics, with defined acceptance criteria, sampling, neutralisation where required, safe maintenance, emergency containment and controlled discharge.
R-346 | Treat the EDS as a containment space with dedicated controlled entry, decontamination exit protocol, and a small-item VHP-compatible pass-box. | 83 | 8.43(iv) | Mandatory | Incorporate controlled entry, decontamination exit protocol, and a small-item decontamination pass-box compatible with VHP for the EDS area. | Yes |  |  |  | The EDS shall itself be treated as a containment space: it shall have a dedicated, controlled entry with a decontamination exit protocol for personnel and equipment associated with its operation and maintenance, and shall include a small-item decontamination pass-box (compatible with vapour- phase decontamination agents such as Vaporized Hydrogen Peroxide) for transfer of instruments, samples, or components into and out of the EDS area without compromising its containment integrity.
R-347 | Conduct an assessment during initial site investigation on whether the footprint accommodates the complete EDS system and state all implications before design freeze. | 83 | 8.43(v) | Mandatory | Assess footprint adequacy for EDS during initial site investigation, identifying required reconfigurations, enclosures, or utility augmentations with structural, statutory, cost, program, and O&M implications before design freeze. | Yes |  |  |  | Because the EDS requires dedicated tankage, pumps, treatment entry and exit arrangements, maintenance access and associated utility and material- transfer provisions in addition to the general ETP, the Consultant shall assess during the initial site and existing-building investigation whether the current footprint can accommodate the complete system. The assessment shall identify any required reconfiguration, additional approved enclosure or utility augmentation and shall state structural, statutory, cost, Program, operation and maintenance implications before design freeze.
R-348 | ETP must feature monitoring, control, verification, automatic discharge prevention safeguards, BAS alarms, and containment measures at EDS maintenance access points. | 83 | 8.43(vi) | Mandatory | Equip ETP with treatment monitoring/control, safeguards against discharging untreated effluent, BAS alarming, and containment airlocks at EDS access points. | Yes |  |  |  | The ETP shall include provisions for monitoring, control and verification of treatment performance, with automatic safeguards preventing discharge of untreated or inadequately treated effluent, and shall be alarmed to the building automation system. Where the EDS area requires access for maintenance, its access points shall incorporate appropriate containment measures (an airlock or equivalent arrangement) to ensure controlled movement and prevent release of contaminants.
R-349 | Containment-zone floor drains must feature a minimum 125 mm deep water-seal trap with chemical disinfectant, cleanouts within containment, and connect directly to the EDS via chemical-resistant pipe capable of withstanding maximum negative pressure. | 83 | 8.43(vii) | Mandatory | Install 125 mm deep chemical disinfectant-filled water-seal traps on containment floor drains connected to EDS via acid/chemical-resistant pipe (HDPE, PP-H, PVDF, preferably 150 mm) capable of withstanding maximum room negative pressure; route washroom effluent to ETP with 125 mm traps. | Yes |  |  |  | Each floor drain within the containment zone shall have a minimum 125 mm deep water-seal trap, filled with chemical disinfectant and topped up as frequently as required, directly connected to the EDS (not the general ETP), with cleanout plugs provided within the containment zone; the drain pipe shall be acid- and chemical-resistant, leak-proof, easily cleanable, and preferably 150 mm in size, constructed of HDPE, PP-H (homopolymer polypropylene), PVDF, or an equivalent approved chemical- and corrosion-resistant material, and shall be capable of withstanding the maximum negative pressure anticipated in the room it serves (so as to prevent reverse airflow through the drain). Where washrooms are provided in association with the facility (outside the containment zone), washroom effluent shall be routed to the ETP, with a minimum 125 mm water-sealed trap.
R-350 | Provide automatic backwater valves on drainage mains serving flood-level rim fixtures; design drainage to flow by gravity to EDS, or provide N+1 chemical/gas-resistant sump/lift pumps. | 84 | 8.43(viii) | Mandatory | Install automatic backwater valves and design gravity drainage to EDS where possible; if sumps or lift pumps are required, equip them with N+1 standby redundancy and hydrogen-sulphide/chemical resistance. | Yes |  |  |  | Backwater valves shall be automatic, provided on any drainage main serving fixtures or equipment with a flood-level rim. Drainage shall be designed to flow by gravity from the containment zone to the EDS wherever possible; where a sump or lift pump is unavoidable, it shall be resistant to hydrogen-sulphide gas and routine decontamination chemicals, and provided with standby (N+1) redundancy.
R-351 | Provide convenient access to chemical disinfectants; ensure all specified materials/coatings/finishes are compatible with cleaning, disinfection, and decontamination agents. | 84 | 8.44(i) | Mandatory | Demonstrate compatibility of all surfaces, coatings, seals, finishes, and service materials with routine/emergency cleaning agents including VHP, formaldehyde, peracetic acid, sodium hypochlorite, quats, and alcohol disinfectants. | Yes |  |  |  | The facility shall provide convenient access to appropriate chemical disinfectants at work benches, containment exits and waste-handling areas. Disinfectants shall have documented effectiveness against the intended agents. All specified surfaces, coatings, seals, equipment finishes and service materials shall be demonstrated compatible with the complete range of routine and emergency cleaning, disinfection and room-decontamination agents, including Vaporized Hydrogen Peroxide, formaldehyde, peracetic acid, sodium hypochlorite, quaternary ammonium compounds and alcohol-based disinfectants where proposed.
R-352 | Provide hands-free hand-washing sinks with gooseneck spouts, vacuum breakers, non-aerating outlets, single mixed outlets, and hands-free emergency eyewash stations. | 84 | 8.44(ii) | Mandatory | Provide foot-, elbow-, or sensor-operated hand-washing stations near exits with acid/chemical-resistant sinks, hands-free gooseneck faucets with vacuum breaker, laminar-flow non-aerating single mixed outlet, and a hands-free emergency eyewash station near the lab exit. | Yes |  |  |  | A hands-free (foot-, elbow- or sensor-operated) hand-washing station shall be provided near the exit of every functional space, with sinks of acid- and chemical-resistant material (stainless steel or epoxy-coated resin preferred). Hand-wash and laboratory faucets within the containment zone shall be of gooseneck-spout, fully hands-free design, fitted with an integral atmospheric vacuum breaker and a laminar-flow, non-aerating, non-splash outlet; separate outlet taps for hot and cold water are not acceptable — a single tempered/mixed outlet shall be provided. A sensor- or foot/elbow-operated emergency eyewash station shall be provided in the laboratory, preferably near the exit door.
R-353 | Service pipes must be sloped, fitted with backflow preventers (N+1 redundancy where serving multiple suites), and mounted with clearance gaps from walls. | 84 | 8.44(iii) | Mandatory | Install sloped service pipes with backflow preventers (providing N+1 redundancy where serving multiple suites) and clearance gaps off walls. | Yes |  |  |  | Service pipes shall be installed with sloping lines and fitted with backflow preventers to isolate branch water lines, with N+1 redundancy provided in the backflow-preventer arrangement where a single device serves multiple containment suites; piping shall be mounted with a clearance gap from walls to facilitate cleaning and avoid contamination.
R-354 | Provide water supply with dedicated water meter, maintenance isolation valves, pressure regulation, and backup storage/pressure-maintenance. | 84 | 8.45(i) | Mandatory | Equip the water supply system with dedicated water meter, isolation valves, pressure regulation, and backup storage or pressure-maintenance provisions. | Yes |  |  |  | The facility shall receive adequate water supply from the institutional system, with a dedicated water meter, isolation valves permitting shutdown for maintenance without affecting other institutional areas, pressure regulation, and backup storage or pressure-maintenance provision to ensure continuity even if institutional pressure drops.
R-355 | Emergency eyewash and shower water must be tepid (~25°C), supplied through thermostatic mixing valves with pressure limiting, flow alarms, backflow protection, and isolated potable connection. | 85 | 8.46(i) | Mandatory | Provide tepid water (~25°C) via thermostatic/mixing valve with pressure limiting, audible/visible flow alarms on shower activation, isolated potable water supply with backflow protection, and drain shower water to treatment. | Yes |  |  |  | Emergency eyewash and shower water shall be tepid (approximately 25°C, or as otherwise required by the applicable emergency-fixture standard), supplied through a thermostatic or mixing valve that automatically adjusts to maintain a constant outlet temperature as incoming water temperature varies, with pressure limiting to prevent excessive pressure or temperature, and readily accessible for maintenance and adjustment. A local audible and visible flow alarm shall activate on use of the emergency shower, alerting personnel elsewhere in the facility. Floor drainage at emergency-shower locations shall be routed to treatment rather than permitted to pool, and emergency showers located within conventional laboratory spaces shall not rely solely on a floor drain that could compromise containment integrity of that room. Emergency eyewash and shower fixtures shall be supplied from an isolated potable-water connection, with backflow protection provided on the service before it enters the containment zone.
R-356 | Showers within the containment zone must deliver a minimum flow rate of 10 L/min without hand-held shower heads (unless required for accessibility, with vacuum breaker). | 85 | 8.46(ii) | Mandatory | Ensure containment zone showers deliver at least 10 L/min and exclude hand-held shower heads unless required for accessibility compliance (fitted with vacuum breakers). | Yes |  |  |  | Showers provided within the containment zone (whether for routine personnel exit or for emergency use) shall deliver a minimum flow rate of 10 litres per minute (approximately 2.5 gallons per minute). Hand-held shower heads shall not be used within the containment zone, except where specifically required to achieve barrier-free/accessibility compliance, in which case a vacuum breaker shall be fitted.
R-357 | Supply hot water through an electric water heater or steam/hot-water system connection, with insulated piping, relief valves, and a return circulation loop. | 85 | 8.47(i) | Mandatory | Provide hot water via electric heater or institutional connection, with insulated pipes, temperature/pressure relief valves, and a return circulation loop. | Yes |  |  |  | Hot water, where required for hand-washing, autoclave operation, or equipment use, shall be supplied through an electric water heater or connection to the institutional steam/hot-water system, with appropriately insulated piping to prevent heat loss and condensation, a temperature/pressure relief valve, and a return circulation loop to maintain ready availability without excessive waiting time at the point of use.
R-358 | Water closets inside containment must be wall-mounted, blow-out flushing-action type with deep-seal trap and 13.5 L flush volume; avoid floor drains/sinks unless justified. | 85 | 8.48(i) | Mandatory | Install wall-mounted, blow-out type water closets with deep-seal vented self-cleaning traps and 13.5 litre flush volumes if placed within containment; avoid floor drains/sinks unless justified by risk assessment. | Yes |  |  |  | Any water closet located within the containment zone shall be wall-mounted, with a deep-seal, vented, self-cleaning trap arrangement located directly below the fixture, and shall be of the blow-out flushing-action type with a flush volume of 13.5 litres (approximately 3.5 gallons) per flush, selected specifically to prevent stoppages and to reliably clear the trap given the deep-seal configuration required for containment. Floor drains and floor sinks shall generally be avoided within the containment zone unless specifically required by the operational Program and justified through the risk assessment.
R-359 | Segregate laboratory wastewater and route every potentially contaminated liquid stream to EDS via dedicated leak-proof drainage without bypass to ETP. | 85 | 8.49(i) | Mandatory | Route all potentially contaminated liquid streams through dedicated, leak-proof, identifiable drainage to the EDS without bypass or crossover to the general ETP. | Yes |  |  |  | Laboratory wastewater shall be segregated from all other building drainage. Every potentially contaminated liquid stream, including sinks, equipment drains, autoclave condensate and justified containment-zone floor drains, shall be routed through dedicated, leak-proof and identifiable drainage to the EDS without connection, bypass or cross-over to the general ETP before validated decontamination. The design shall define traps, venting, backflow prevention, isolation, sampling, decontamination, emergency containment, monitoring and controlled discharge.
R-360 | Floor drains must have P-traps/S-traps, cleanout ports, overflow prevention, and debris screens. | 85 | 8.49(ii) | Mandatory | Provide P-trap/S-trap, accessible cleanout port, screens/strainers, and design to prevent back-siphoning and overflow during system overload on each floor drain. | Yes |  |  |  | Each floor drain shall have a P-trap or S-trap (or equivalent) to prevent back- siphoning of sewer gases, shall be regularly flushed and maintained to prevent accumulation of biological material, shall have an accessible cleanout port, and shall be designed to prevent overflow into the laboratory during system overload, with screens or strainers excluding larger debris.
R-361 | Drainage cleanouts must not be located above or within sensitive spaces or fixed sensitive/hazardous equipment areas. | 86 | 8.49(iii) | Mandatory | Locate cleanouts away from sensitive spaces and fixed sensitive or hazardous equipment areas. | Yes |  |  |  | Cleanouts shall not be located above or within sensitive spaces, or fixed sensitive/hazardous equipment areas, where the risk associated with a cleanout opening (and any consequent waste clean-up) would itself be hazardous.
R-362 | Provide compressed air system with oil/water/particle filtration, check valves, and automatic drain; air compressor must be outside containment, oil-free, moisture-free, sound level below 60 dB, and on vibration isolators. | 86 | 8.50(i) | Mandatory | Install oil-free and moisture-free air compressor outside containment operating below 60 dB on vibration isolators with automatic moisture-drain; fit instrument control lines with in-line HEPA filters and backflow preventers. | Yes |  |  |  | Where required for equipment operation, a compressed-air system shall be provided with filtration for oil, water and particle removal, pressure regulation and check valves to prevent contamination backflow, drain valves for periodic condensate removal, and air quality meeting the requirements of the laboratory equipment served. The air compressor shall be installed outside the containment area, shall be oil-free and moisture-free, shall operate at a sound level below 60 dB, shall be mounted on vibration isolators, and shall have an automatic moisture-drain valve. Compressed-air lines for instrument control shall be oil-free and moisture-free, fitted with small in-line HEPA filters and backflow preventers.
R-363 | Vacuum system must have traps/filtration, HEPA filtration of pump exhaust, point-of-use liquid-disinfectant traps, in-line sterilising filters, independent pump decontamination, and roof exhaust. | 86 | 8.50(ii) | Mandatory | Provide vacuum system with liquid-disinfectant trap, in-line HEPA/sterilising filter, isolation valve and decontamination port at points of use; isolate and decontaminate pump independently, and discharge exhaust above roof. | Yes |  |  |  | Where required for equipment operation or biological safety cabinet function, a vacuum system shall include traps and filtration preventing contaminated material from reaching the pump, HEPA filtration of pump exhaust where biological material may be handled, pressure monitoring, check valves and alarms. Each point of use shall have a liquid-disinfectant trap, HEPA-efficiency or sterilising-grade in-line filter, isolation valve and decontamination port. The vacuum pump shall be capable of independent isolation and decontamination, and exhaust shall be discharged separately above the roof at a location demonstrated to prevent re-entrainment. Specialty-gas systems beyond instrument air shall be independently zoned, labelled, secured, pressure-regulated, monitored, provided with emergency isolation and designed to prevent backflow and cross-connection.
R-364 | Conduct an analysis at design stage comparing centralised vs stand-alone electric steam generator(s) for autoclaves, liquid-waste decontamination, and hot water. | 86 | 8.50(iii) | Mandatory | Perform a design-stage analysis evaluating centralised boiler vs stand-alone steam generator options based on operational loads. | Yes |  |  |  | An analysis shall be conducted, at the design stage, of whether a centralised steam generator (oil-fired or electric boiler) or stand-alone electric steam generator(s) best serve the facility's requirement for autoclave operation, liquid-waste decontamination, and hot-water generation for showers/central heating, based on the specific operational load.
R-365 | Determine the appropriate fire-suppression system type, configuration, and selection for the high-containment laboratory in consultation with a fire-safety expert. | 87 | 8.52(i) | Mandatory | Assess and finalise the fire-suppression system design in consultation with a fire-safety expert, ensuring containment barriers and biological safety are not compromised. | Yes |  |  |  | A fire-suppression system appropriate to a high-containment laboratory environment shall be provided, with the system type, configuration and selection (e.g., wet sprinkler with appropriate precautions, or an alternative agent where pressure transients or suppression-agent characteristics could damage containment barriers or interfere with biological safety) determined by the Consultant in consultation with the fire-safety expert and finalised at the design stage.
R-366 | Assess the condition of the existing building's fire-protection systems and propose necessary integration, augmentation, or replacement. | 88 | 8.53(ii) | Mandatory | Evaluate existing fire-protection infrastructure and submit proposals to meet applicable fire-safety norms for the facility. | Yes |  |  |  | The Consultant shall assess the condition of the existing building's fire-protection systems and propose the extent of integration, augmentation or replacement needed to meet applicable fire-safety norms for this facility.
R-367 | Submit a technical and commercial comparison between a single dedicated electrical feed with standby generation versus two physically separate sources before design freeze. | 89 | 8.54(i) | Mandatory | Prepare and submit an options comparison covering reliability, single-failure exposure, capital cost, recurring cost, space, maintenance, statutory and Program implications for AIIMS Patna's written decision. | Yes |  |  |  | Where the existing institutional infrastructure permits, the Consultant shall compare a single dedicated feed with standby generation against two physically separate sources, each independently capable of carrying the facility's design load. The comparison shall state reliability, single-failure exposure, capital cost, recurring cost, space, maintenance, statutory and Program implications and shall be submitted for AIIMS Patna's written decision before design freeze.
R-368 | Calculate facility electrical connected and demand loads and size distribution boards with at least 30–35% reserve capacity. | 89 | 8.54(ii) | Mandatory | Calculate connected and demand loads including anticipated future additions and size distribution boards with a minimum 30–35% reserve margin. | Yes |  |  |  | The Consultant shall calculate the facility's connected and demand load, including reasonably anticipated future equipment additions identified through the site investigation and equipment-list review, and shall size the distribution boards with a reserve capacity of not less than 30–35% above that calculated load — a higher reserve being warranted where the Consultant's own assessment of likely future expansion supports it.
R-369 | Deliver a comprehensive electrical design package and auditable BOQ and rate analysis. | 89 | 8.54(iii) | Mandatory | Include all specified calculations, studies, schedules, single-line diagrams, point lists, item-wise BOQ measurement bases, and rate analyses in the electrical design submission. | Yes |  |  |  | The electrical design package shall include the existing-supply/transformer assessment, load flow and demand/diversity calculations, fault-level and protection-coordination study, earthing/lightning-protection basis, transformer/DG/UPS sizing and option analysis, cable and panel schedules, single-line diagrams, instrument/field-device schedule and complete I/O/point list for electrical, ELV and BMS/EMS interfaces. The BOQ and estimate shall include item-wise measurement basis and auditable rate analysis for transformer(s), DG, UPS, panels, cables, controls and other major electrical equipment, including installation, testing, spares, taxes/duties assumptions and applicable civil/interface works.
R-370 | Size an online UPS with a minimum 2 hours autonomy and provide a 100% capacity standby UPS. | 89 | 8.55(i) | Mandatory | Size an online UPS with at least 2 hours backup autonomy for critical systems, and provide an additional standby UPS sized at 100% of the designed capacity. | Yes |  |  |  | The Consultant shall size an online UPS to provide temporary backup power on utility failure, with an autonomy the Consultant determines adequate to allow safe shutdown of equipment and a robust bridging window for transition to generator power, which shall in no case be less than 2 hours or as suggested by the consultant.
R-371 | Provide a dedicated diesel generator set capable of bearing 100% connected load with AMF panel, ATS, and noise levels below 60 dB. | 90 | 8.55(ii) | Mandatory | Design and specify a dedicated DG set capable of 100% connected load, featuring soundproofing (<60 dB), AMF panel, ATS switchover, and independent exhaust routing. | Yes |  |  |  | A dedicated diesel generator set, capable of bearing 100% of the facility's connected load, shall be provided with an Automatic Mains Failure (AMF) panel, sized for all essential facility systems, housed separately with appropriate exhaust routing and soundproofing (noise level below 60 dB, meeting applicable pollution-control-board emission norms), and fitted with an Automatic Transfer Switch (ATS) for seamless, automatic switchover to and from utility supply, with manual bypass capability and appropriate protective relays.
R-372 | Provide a 100%-capacity standby cable for the main electrical feeder. | 90 | 8.55(iii) | Mandatory | Include a 100%-capacity standby backup cable to the main feeder cable in the electrical design. | Yes |  |  |  | A 100%-capacity standby cable shall be provided as backup to the main feeder cable, to minimise downtime in the event of a cable fault.
R-373 | Provide dedicated circuits with 30–35% capacity margin and equal load balancing across three phases. | 90 | 8.56(i) | Mandatory | Design dedicated and redundant circuits for essential systems, maintain 30–35% capacity margins on all circuits, and balance loads equally across all three phases. | Yes |  |  |  | The facility shall be served by dedicated circuits for: HVAC equipment, compressors and motors; laboratory equipment and biological safety cabinets; lighting; emergency systems; UPS charging; the building automation system; and IT/security-surveillance infrastructure — with redundant circuits provided for critical equipment to permit continued operation in the event of a single circuit failure, and a capacity margin of 30–35% maintained on all circuits to prevent overloading. Electrical load shall be balanced equally across all three phases, and electrical-load calculations shall account for reasonably anticipated future equipment additions.
R-374 | Install rigid galvanised steel (RGS) electrical conduit with threaded fittings and seal-off fittings within the containment zone. | 91 | 8.56(v) | Mandatory | Specify rigid galvanised steel conduit with threaded fittings inside containment, prohibit surface-mounted raceways, and detail seal-off fittings and silicone sealant at all containment penetrations. | Yes |  |  |  | Within the containment zone, electrical conduit shall be of rigid galvanised steel (RGS) type with threaded fittings; surface-mounted metal raceway systems shall not be used within the containment zone. Seal-off fittings shall be provided wherever a conduit exits the defined containment perimeter, and a silicone-based sealant compatible with the conduit insulation shall be applied around every conduit and device-box penetration through the containment barrier, including a continuous bead of sealant between each device box and the adjoining wall/ceiling surface and around each device cover plate.
R-375 | Detail containment-barrier penetrations in construction documents and construct and test a mock-up prior to general installation. | 91 | 8.56(vi) | Mandatory | Detail electrical and service penetrations in construction drawings, and mandate construction and airtightness testing of a mock-up before replication. | Yes |  |  |  | All containment-barrier penetrations for electrical conduits and device boxes (along with equivalent penetrations for other building services) shall be detailed in the construction documents and shall be constructed and tested as a mock-up prior to general installation, to confirm that the sealing detail achieves the required airtightness before it is replicated throughout the facility.
R-376 | Design earthing system with copper earth plate (600 mm × 600 mm × 3 mm) maintaining neutral-to-earth voltage below 5V. | 91 | 8.57(i) | Mandatory | Provide earthing with copper earth plates in masonry enclosures with watering pipe/funnel, separating neutral, general, main supply, and generator earthings, ensuring neutral-to-earth voltage is under 5V. | Yes |  |  |  | Earthing shall be provided with a copper earth plate (600 mm × 600 mm × 3 mm) in a masonry enclosure with a watering pipe and funnel of adequate length, with separate earthing for neutral and for general earthing, and separate, similar earthing for the main electrical supply and for each generator, all in accordance with applicable Indian electrical regulations; the voltage difference between neutral and earth shall be less than 5V.
R-377 | Design lighting with a minimum of 500 lux on work surfaces and 700–800 lux in cleaning/decontamination areas. | 91 | 8.58(i) | Mandatory | Calculate and specify lighting fixtures to achieve at least 500 lux on laboratory work surfaces and 700–800 lux in decontamination areas. | Yes |  |  |  | The Consultant shall determine the illumination level appropriate to each room's function and design the lighting accordingly, providing a minimum of 500 lux (50 foot-candles) on laboratory work surfaces as the floor for detailed laboratory work and assessment of surface cleanliness, and assessing whether particular rooms — such as microscopy stations, where up to 750 lux is indicatively appropriate — warrant a higher level. Cleaning-cycle/decontamination areas shall similarly be assessed and shall in any case be illuminated at not less than 700–800 lux.
R-378 | Battery-backed emergency lighting with at least two hours autonomy must automatically activate on main-power failure in work and egress areas, providing at least 10 foot-candles (approx. 100 lux), with at least 50% of laboratory room fixtures on emergency power and at least one fixture equipped with a self-testing emergency battery ballast. | 92 | (iii) | Mandatory | Provide battery-backed emergency lighting with minimum 2 hours autonomy, 100 lux along egress paths and exits, 50% of fixtures in each containment room connected to emergency power, and at least one fixture with a self-testing emergency battery ballast on an unswitched circuit. | Yes |  |  |  | Battery-backed emergency lighting shall automatically activate on main-power failure in all work and egress areas, providing at least 10 foot-candles, approximately 100 lux, along egress paths and at emergency exits, supplemented by visual alarm strobes. The emergency-lighting system shall have not less than two hours of autonomy. Within each containment laboratory room, at least 50% of light fixtures shall be connected to emergency power, and at least one fixture shall have a self-testing emergency battery ballast connected to an unswitched local emergency-generator circuit so that illumination remains available during an emergency-lighting-circuit fault.
R-379 | Lighting switches must be clearly marked, logically grouped by area, include manual override for emergencies, interface with BAS for monitoring/scheduling, and protect against accidental activation of master switches. | 92 | (iv) | Mandatory | Design and install lighting switches that are clearly marked, grouped by area, equipped with manual override, interfaced with BAS, and protected against accidental activation. | Yes |  |  |  | Lighting switches shall be clearly marked and logically grouped by area, include manual override for emergencies, interface with the building automation system for monitoring and scheduling, and be protected against accidental activation of master switches.
R-380 | The laboratory must be equipped with a communication network featuring CAT-6A or higher structured cabling, an EPABX/IP-PBX system, and connectivity to a 24/7 staffed location during laboratory operations. | 93 | 8.59(i) | Mandatory | Install structured cabling of CAT-6A or higher specification, voice/data points across all zones, and an EPABX/IP-PBX system connected to a continuously staffed location for emergency response. | Yes |  |  |  | The laboratory shall be equipped with a communication network connecting the containment area, support area, and service areas, with data and voice points (structured cabling of CAT-6A specification or higher) in all zones and a suitable EPABX/IP-PBX system for incoming/outgoing lines; the system shall be connected to a location staffed at all times during laboratory operation, for emergency response.
R-381 | LAN and data-transfer systems must support electronic information transfer, and any paper removed from the containment area must be decontaminated via autoclave, fumigation chamber, or airlock. | 93 | 8.59(ii) | Mandatory | Implement electronic data-transfer systems and ensure procedures and facilities exist to decontaminate paper via autoclave, fumigation chamber, or airlock prior to removal from containment. | Yes |  |  |  | LAN and data-transfer systems shall support electronic transfer of information within and out of the containment laboratory, in preference to paper transfer; where paper must be removed from the containment area, it shall be decontaminated through autoclave, fumigation chamber, or airlock before removal.
R-382 | Electronic access control must deploy a three-tier security system (card readers, biometric authentication, and PIN-keypad backup) integrated with door interlocks, CCTV, event logging, emergency release, safe egress, and backup power. | 93 | 8.60(i) | Mandatory | Provide a 3-tier electronic access control system utilizing institutional card readers, biometric authentication, and PIN keypad backup, fully integrated with door interlocks, CCTV, logging, emergency release, egress, and backup power. | Yes |  |  |  | Electronic access control shall use institutional credential or card readers for general facility access, biometric authentication for the primary containment area and PIN-keypad entry as secondary or backup authentication. Tier 1 shall control general institutional facility access; Tier 2 shall restrict specialised laboratory access to trained and authorised personnel; and Tier 3 shall impose additional authorisation for the BSL-3 primary containment area. All tiers shall be integrated with door interlocks, CCTV, event logging, emergency release, safe egress and backup power. The CCTVs installed should be privacy sensitive.
R-383 | Access-control logs must be retained for at least 1 year, and the system must interface with BAS to restrict access during dangerous conditions, enable automated lockdown during emergencies, and provide auditable emergency overrides. | 93 | 8.60(ii) | Mandatory | Maintain detailed access-control logs for a minimum of 1 year, configure BAS interface for access restriction during dangerous conditions and automated lockdown while preserving egress, and provide auditable emergency-override protocols. | Yes |  |  |  | The access-control system shall maintain detailed logs (who accessed, when, for how long; unauthorised attempts; system malfunctions or security breaches), retained for a minimum of 1 year and reviewed periodically for security audit. The system shall interface with the building automation system to restrict facility access automatically if dangerous conditions exist (such as loss of negative pressure), shall record access events alongside other facility events for incident investigation, and shall be capable of automated lockdown under predefined emergency conditions while always preserving safe and unobstructed egress for personnel. Controlled, monitored, and auditable emergency-override protocols shall be provided for authorised emergency-response personnel (fire, medical, rescue), limited strictly to authorised use and recorded for traceability.
R-384 | CCTV cameras must provide 24x7 continuous monitoring in sealed, corrosion-resistant housings across laboratory work areas, entry/exit points, biosafety cabinet areas, and waste handling areas. | 93 | 8.61(i) | Mandatory | Install 24x7 continuous CCTV surveillance in sealed, corrosion-resistant enclosures covering all work areas, entries/exits, BSC work areas, and waste-handling areas. | Yes |  |  |  | CCTV cameras shall continuously (24×7) monitor all laboratory work areas (without obstructing laboratory work), entry/exit points, biological safety cabinet work areas, and waste-handling areas, balancing security with privacy and operational requirements. Cameras shall have resolution sufficient to identify personnel and document activity, shall operate across the range of lighting conditions present in the facility, shall be housed in sealed, corrosion-resistant enclosures, and shall be positioned to avoid blinding from bright lights or HVAC airflow.
R-385 | CCTV recordings must be continuously stored with a minimum retention period of 90 days, time-stamped, protected with role-based access control, and include a mirror display of feeds and BAS parameters in the Laboratory In-charge's office. | 94 | 8.61(ii) | Mandatory | Provide secure storage for CCTV recordings with at least 90 days retention, role-based access control, and a mirror display in the Laboratory In-charge's office. | Yes |  |  |  | Recordings shall be continuously stored with a minimum 90 days retention, time-stamped, accessible to authorised personnel for incident or security review, and securely protected against unauthorised access or tampering, with role-based access control restricting playback/export rights to authorised personnel only. A mirror display of key camera feeds and BAS parameters in the Laboratory In-charge's office is required.
R-386 | The facility design must provide infrastructure for a Laboratory Information Management System (LIMS) for sample tracking, test/result management, and chain-of-custody documentation. | 94 | 8.62(i) | Mandatory | Include provisions for LIMS server and workstation network and power infrastructure to support sample tracking and chain-of-custody documentation. | Yes |  |  |  | The design shall make provision for a Laboratory Information Management System (LIMS) to support sample tracking, test/result data management, and chain-of-custody documentation for materials handled within the facility, with appropriate network and power infrastructure provided for the LIMS server and workstations.
R-387 | The design must support a secure pathogen inventory system and incorporate cybersecurity safeguards across the inventory system, LIMS, and BAS. | 94 | 8.62(ii) | Mandatory | Design a secure pathogen inventory management system and implement cybersecurity controls (authentication, access control, encryption, and audit logging) for IT and network infrastructure. | Yes |  |  |  | The design shall support a secure pathogen/agent inventory management system, including provision for secure storage of stocks and cultures, with access logging and inventory reconciliation procedures forming part of the facility's biosecurity Program; the IT and network infrastructure supporting this inventory system, the LIMS, and the BAS shall incorporate cybersecurity safeguards (user authentication, access control, encryption, and audit logging) commensurate with the sensitivity of the data held.
R-388 | Two-way emergency communication systems with audible/visual alarms and recording capabilities must be provided between the laboratory, emergency responders, and management. | 94 | 8.63(i) | Mandatory | Install two-way emergency communication systems equipped with audible/visual breach alarms and recording capabilities. | Yes |  |  |  | Two-way emergency communication systems shall enable communication from the laboratory to emergency responders and institutional authorities, and from laboratory management to personnel, with audible/visual alarms for system malfunction or containment breach and recording capability for incident documentation.
R-389 | Biological safety cabinets must be Class II Type A2 at minimum, positioned away from traffic and drafts, with exhaust connections coordinated with room HVAC and canopy/thimble connections verified during commissioning. | 95 | 8.64(i) | Mandatory | Supply and integrate Class II Type A2 minimum BSCs, coordinate exhaust connections with HVAC systems, and verify air gap and exhaust compliance during commissioning. | Yes |  |  |  | Biological safety cabinets shall be Class II Type A2 at minimum, with Class III considered for the highest-risk activities identified by risk assessment. Cabinets shall be positioned away from walking routes, doors and ventilation cross-currents. The cabinet exhaust connection and room HVAC shall be coordinated so that filtered cabinet exhaust does not interfere with the cabinet's certified airflow balance or the building exhaust system. Where a canopy or thimble connection is used instead of hard ducting, its air gap and exhaust quantities shall comply with the cabinet manufacturer's certification requirements and shall be verified during commissioning.
R-390 | Piping and distribution systems for specialised laboratory equipment must adhere to containment, redundancy, cleanability, decontamination, and safe-maintenance standards and coordinate with facility matrices and drawings. | 95 | 8.65(i) | Mandatory | Coordinate process piping for specialised equipment with approved matrices, layouts, specifications, and testing records applying facility containment and maintenance principles. | Yes |  |  |  | Piping and distribution systems for specialised laboratory equipment, including dedicated chillers and point-of-use high-purity-water polishers where required, shall apply the same containment, redundancy, cleanability, decontamination, isolation, monitoring and safe-maintenance principles required for the facility. These systems shall be fully coordinated with the approved equipment and utility matrix, room data sheets, layouts, coordinated drawings, BOQ, technical specifications, testing requirements and handover records.
R-391 | Dedicated gas-pipeline systems must be designed and installed with pressure regulation, isolation valves, identification, leak detection, ventilation, and safety provisions. | 95 | 8.65(iii) | Mandatory | Design and install dedicated gas-pipeline systems meeting applicable codes and equipment utility requirements. | Yes |  |  |  | Wherever required for laboratory operations or equipment, dedicated gas-pipeline systems shall be designed and installed for the specified gases, with appropriate pressure regulation, isolation valves, identification, leak detection, ventilation and safety provisions, in accordance with applicable codes and the approved equipment utility requirements.
R-392 | Calibrated differential-pressure instruments must verify room pressure cascades, maintaining a differential of at least 15 Pa between adjacent functional spaces becoming progressively more negative toward higher-risk spaces. | 96 | 8.66(i) | Mandatory | Verify room-wise pressure gradients using calibrated differential-pressure instruments, ensuring at least a 15 Pa differential between adjacent functional spaces. | Yes |  |  |  | Following construction, calibrated differential-pressure instruments shall verify the approved room-wise pressure gradient at multiple locations under normal operating conditions, typical occupancy, closed-door steady state and defined door-opening scenarios. The pressure cascade shall become progressively more negative from lower-risk to higher-risk spaces and shall maintain a differential of not less than 15 Pa between adjacent functional spaces unless a higher approved value is required by risk assessment or the governing national requirement.
R-393 | Laboratory envelopes must pass a pressure-hold test consisting of visual soap-bubble leak inspection at 125 Pa, followed by pressure decay monitoring at 250 Pa for 20 minutes with a maximum allowable pressure drop of less than 125 Pa. | 96 | 8.66(ii) | Mandatory | Perform pressure-hold testing on the sealed laboratory envelope by testing at 125 Pa for leaks and verifying pressure drop is less than 125 Pa over 20 minutes when pressurised to 250 Pa. | Yes |  |  |  | Pressure-hold test: With the HVAC system switched off, the initial pressure shall be measured and then re-measured at regular intervals (every 5–10 minutes), with the rate of pressure change recorded; a properly sealed room shall show minimal drift. The complete laboratory envelope shall be tested for leakage by: sealing supply/exhaust openings and closing all doors; pressurising to 125 Pa and visually inspecting for leakage (soap-bubble test); repairing any leak found and re-testing; then pressurising to 250 Pa and monitoring pressure decay for 20 minutes, recording pressure at one-minute intervals; an acceptance criterion of pressure drop less than 125 Pa in 20 minutes (i.e., no more than half the starting 250 Pa) shall apply.
R-394 | Visual smoke testing must confirm unidirectional airflow patterns from non-containment/low-contamination areas to high-contamination areas, with documented and photographed smoke patterns. | 96 | 8.66(iii) | Mandatory | Perform and document visual smoke testing with photographs showing unidirectional smoke patterns flowing toward higher contamination areas. | Yes |  |  |  | Smoke/airflow visualisation testing: Visual smoke testing shall verify directional airflow patterns, confirming that air flows into the laboratory from non-containment areas and identifying any unintended leakage path or dead zone; smoke patterns shall be photographed and documented, with the acceptance criterion being a unidirectional smoke pattern from areas of low contamination to areas of high contamination.
R-395 | Every HEPA filter must have pre-installation manufacturer certification demonstrating efficiency of at least 99.97% at 0.3 micron, traceable to approved test methods and retained in the handover dossier. | 96 | 8.67(i) | Mandatory | Provide and retain pre-installation manufacturer test certificates confirming HEPA filter efficiency of not less than 99.97% at 0.3 micron. | Yes |  |  |  | Pre-installation: Before installation, every HEPA filter shall have manufacturer certification demonstrating efficiency not lower than 99.97% at 0.3 micron, identification and traceability of the filter and test method, and compliance with the approved filter grade and pressure-drop requirement. Certification records shall be retained in the commissioning and handover dossier.
R-396 | Post-installation in-situ HEPA filter testing must verify aerosol challenge leakage of less than 0.01% for 0.3-micron particles with calibrated equipment and zero leakage at the housing seal. | 96 | 8.67(ii) | Mandatory | Perform upstream aerosol challenge and downstream scanning after installation, repairing leaks to achieve less than 0.01% leakage for 0.3-micron particles with zero housing seal leakage. | Yes |  |  |  | Post-installation: After installation, upstream aerosol challenge and downstream scanning shall be performed with calibrated equipment. Any pinhole leakage shall be repaired and the filter re-scanned. Field or in-situ filter leakage shall be less than 0.01% for 0.3-micron particles, with no leakage at the housing seal.
R-397 | Air-change rates must meet the approved design value, be verified by calibrated measurement or approved tracer-gas concentration-decay method, and not fall below 8 air changes per hour. | 97 | 8.68(i) | Mandatory | Verify air-change rates using calibrated airflow measurement or tracer-gas concentration decay, ensuring room-wise rates meet design values and are at least 8 ACH (or higher where required). | Yes |  |  |  | Air-change rates shall be verified by calibrated measurement of supply and exhaust airflow or by an approved tracer-gas concentration-decay method. The measured room-wise rate shall meet the approved design value and shall not be lower than 8 air changes per hour; a higher value shall apply wherever required by room calculation, heat load, occupancy, equipment density, biosafety risk assessment or governing national requirement.
R-398 | If chemical disinfection is selected, the decontamination system must be validated with representative pathogen cultures, verifying pH, temperature, and contact time, and validation documentation must be retained. | 97 | 8.69(i) | Mandatory | Validate chemical decontamination systems using representative pathogen or surrogate cultures, confirm zero surviving organisms and proper parameters, and prepare and retain validation documentation. | Yes |  |  |  | Where chemical disinfection is the selected method, the system shall be validated using cultures of representative pathogens (or suitable non-pathogenic surrogate organisms) mixed with waste, subjected to the standard disinfectant treatment, with post-treatment culturing confirming no surviving organisms, and pH, temperature and contact-time parameters verified against design specification; validation documentation shall be prepared and retained.
R-399 | If steam decontamination is selected, liquid waste must undergo controlled steam treatment at validated parameters with complete inactivation demonstrated, parameters recorded via calibrated instruments, and validation documentation maintained. | 97 | 8.69(ii) | Mandatory | Validate steam-based decontamination by demonstrating complete pathogen inactivation, uniform heat distribution, and calibrated parameter recording, and maintain performance-qualification documentation. | Yes |  |  |  | Where steam-based decontamination is the selected or additional method, liquid waste containing representative pathogens (or suitable surrogates) shall be subjected to controlled steam treatment at the validated temperature, pressure and exposure time (e.g., equivalent to autoclaving standards, with chamber temperature maintained above 121°C or 134°C as applicable, and the cycle timer reset to zero if temperature falls below the set point during the cycle), with post-treatment culturing confirming complete inactivation, uniform heat distribution and adequate penetration within the waste stream demonstrated, and all critical parameters (temperature, pressure, time) monitored and recorded through calibrated instruments; validation and performance-qualification documentation shall be prepared and maintained.
R-400 | The ETP and EDS must be independently sized and synchronized with DBT requirements, with capacities and design calculations documented in the Basis of Design and validated against DBT-ICMR and environmental requirements. | 97 | 8.69(iv) | Mandatory | Independently size and synchronize ETP and EDS based on source-wise wastewater generation and demand, documenting proposed capacities, treatment cycles, and design calculations in the Basis of Design. | Yes |  |  |  | The ETP and EDS shall be independently sized &synced with DBT requirement along with the basis of source-wise wastewater generation, peak and average flow, laboratory workload, cleaning and decontamination requirements, autoclave condensate, treatment-cycle duration and anticipated future demand.
R-401 | Biological safety cabinets must undergo field-testing covering specified performance and operator-safety criteria. | 98 | 8.70(i) | Mandatory | Field-test biological safety cabinets against recognized criteria including HEPA filter integrity, work-zone integrity, downflow and inflow velocity, smoke patterns, fan interlocking, and alarm checks. | Yes |  |  |  | Biological safety cabinets shall be field-tested against recognised cabinet-performance criteria, including: HEPA filter installation-integrity test; work-zone integrity test; cabinet integrity test; downflow-velocity test; face (inflow)-velocity test; airflow smoke-pattern test; supply/exhaust fan-interlocking control test; and alarm-operational check; together with non-critical operator-safety checks of vibration, sound level, lighting and UV-light performance, where fitted.
R-402 | Airlock doors must be tested for leakage using soap-bubble and pressure-decay methods, with door interlocks preventing simultaneous opening. | 98 | 8.70(ii) | Mandatory | Test airlock doors for leakage using specified methods and verify door interlock functionality to ensure clean-side doors open only after accepted decontamination cycles. | Yes |  |  |  | Airlock doors shall be tested for leakage by soap-bubble and pressure-decay methods, with the selected acceptance limit stated in the approved test protocol. Dirty-side and clean-side door interlocks shall prevent simultaneous opening, and the clean-side door shall open only after completion and acceptance of the required decontamination cycle.
R-403 | Steam autoclaves must be tested for each PLC program using calibrated instruments and biological indicators to confirm complete sterilization at required temperatures. | 98 | 8.71(i) | Mandatory | Test all autoclave PLC programs, calibrate gauges/thermocouples, and verify sterilization efficacy using biological indicators while maintaining temperatures above 121°C or 134°C. | Yes |  |  |  | Steam autoclaves shall be tested for each Program available in the unit's PLC, with effectiveness of decontamination verified having regard to loading factors, the material being decontaminated, and contact time; gauges and thermocouples shall be calibrated, and biological indicators (preferred over chemical indicators, as they directly monitor process lethality) shall be used to confirm sterilisation, with chamber temperature maintained above the validated set point (121°C or 134°C, as applicable) throughout the cycle.
R-404 | Facility design must incorporate structural and access provisions to enable mandatory annual re-validation of critical containment systems without breaching containment. | 98 | 8.72(i) | Mandatory | Design adequate access panels, test ports, and maintenance corridors to enable accredited annual re-validation of airflow, HEPA filters, BSCs, autoclaves, and containment integrity. | Yes |  |  |  | The design shall incorporate provisions facilitating the mandatory annual re-validation of the facility once operational, covering directional airflow, air velocity, air-change rate, AHU performance, HEPA filter integrity, biological safety cabinet certification, autoclave efficacy, particle count, and room-perimeter (containment) integrity — each re-validated by an appropriately accredited testing organisation. Structural provisions for commissioning and re-validation access — adequate access panels, test ports, and maintenance corridors, clearly marked — shall be designed to allow safe access to all critical systems (HEPA housings, dampers, AHU components) without breaching containment.
R-405 | The Consultant must structure design and handover documentation to support national BSL-3 certification, including preparing the certification application and supporting technical dossiers. | 98 | 8.73(i) | Mandatory | Prepare and compile the BSL-3 certification application and technical documentation including commissioning records, validation reports, as-built drawings, SOPs, and risk assessments. | No — check |  |  |  | The Consultant shall structure the design and handover documentation to directly support the facility's application for certification under the applicable national mechanism for BSL-3 facilities, including preparation of the certification application and all supporting technical documentation (commissioning records, validation reports, as-built drawings, SOPs, and risk-assessment documentation).
R-406 | Containment-critical systems, equipment, and utilities must incorporate permanent provisions for commissioning, qualification, validation, certification, and re-validation from the earliest design stage. | 99 | 8.73(ii) | Mandatory | Incorporate permanent test ports, injection/sampling points, access panels, calibrated interfaces, alarms, and redundancy into all containment-critical systems from early design. | Yes |  |  |  | From the earliest design stage, every containment-critical system, equipment item and supporting utility shall include permanent provisions for commissioning, qualification, independent Validation, certification, routine maintenance and annual revalidation. These provisions shall include safe access, test ports, aerosol-injection and sampling points, isolation and decontamination arrangements, calibrated instrumentation interfaces, removable access panels, recordable alarms, trend data, documented acceptance criteria and traceable records.
R-407 | Safety equipment, containment devices, utilities, and controls must be designed with fail-safe and fault-tolerant architecture to eliminate single points of failure compromising biocontainment or trapping personnel. | 99 | 8.73(iii) | Mandatory | Perform and document criticality and single-failure analyses, providing redundancy, safe-state controls, emergency power, manual overrides, and alarms. | Yes |  |  |  | Safety equipment, containment devices, utilities, controls and emergency-response systems shall be designed so that no single equipment failure, utility interruption, control-system malfunction or reasonably foreseeable operator error can compromise critical bio containment or trap personnel. This shall be achieved through documented criticality and single-failure analysis, appropriate redundancy, automatic safe-state control, alarms and event logging, emergency power, manual override, safe egress, validated emergency procedures, independent verification and periodic testing; no single protective measure shall be relied upon in isolation.
R-408 | All discipline-specific technical requirements must be integrated into complete drawing, BIM, CFD, specification, and acceptance deliverables. | 100 | 8.74(i) | Mandatory | Incorporate all discipline technical requirements into drawings, BIM models, CFD analyses, specifications, and commissioning/handover deliverables. | Yes |  |  |  | All discipline-specific technical requirements shall be incorporated into the complete drawing, BIM, CFD, specification, testing, commissioning, independent-Validation, digital-handover and acceptance deliverables.
R-409 | Phase-I drawings must be issued as coordinated Good-for-Tender documents. | 100 | 8.74(ii) | Mandatory | Issue Phase-I drawings as coordinated Good-for-Tender documents. | Yes |  |  |  | Phase-I drawings shall be issued as coordinated Good-for-Tender documents.
R-410 | The Consultant must prepare a coordinated BOQ, abstract cost estimate, and item-wise rate analysis traceable to drawings, specifications, schedules, and measurement rules. | 100 | 8.75(i) | Mandatory | Prepare coordinated BOQ, cost estimates, and item-wise rate analyses detailing capacities, accessories, installation, testing, commissioning, spares, and interface works for major equipment. | Yes |  |  |  | The Consultant shall prepare a coordinated BOQ, abstract cost estimate and item-wise rate analysis traceable to the drawings, specifications, equipment/utility schedules and measurement rules. Major equipment and systems—including transformer(s), DG, UPS, HVAC plant, HEPA systems, BMS/EMS, EDS/ETP, autoclave, barrier systems and laboratory equipment—shall include capacity, accessories, installation, testing, commissioning, spares, civil/interface works and the stated basis of rate.
R-411 | The cost estimate must identify long-lead items, imported/proprietary exposure, taxes/duties, market assumptions, escalation exclusions, contingencies, lifecycle costs, and BIM take-off reconciliation. | 100 | 8.75(ii) | Mandatory | Detail long-lead items, proprietary exposures, taxes, O&M implications, and reconcile BIM quantity take-offs with the final BOQ without using undefined lumped items. | Yes |  |  |  | The estimate shall identify long-lead items, imported/proprietary exposure, taxes/duties and market assumptions, escalation exclusions, contingencies if permitted by the controlling commercial document, lifecycle/O&M implications and reconciliation of BIM quantity take-off with the final BOQ. Lumped or undefined items shall not be used where the scope can reasonably be measured and specified.
R-412 | The Laboratory Equipment Planning and Integration Specialist must maintain the master equipment list and associated layout and utility matrices. | 100 | 8.76(i) | Mandatory | Maintain master equipment list, layouts, utility matrices, loads, biosafety interfaces, FAT/SAT requirements, and BOQ coordination under controlled user approval. | Yes |  |  |  | The Laboratory Equipment Planning and Integration Specialist shall maintain the master equipment list, room-wise equipment layouts, installation/replacement route, utility matrix, heat/electrical/process-gas loads, clearances, vibration/noise criteria, biosafety interfaces, FAT/SAT needs and BOQ/specification coordination. The list is a design baseline and shall be updated only through controlled user approval.
R-413 | The Consultant must author design-stage models, calculations, specifications, review field information for design intent, update the record model, and compile certification/handover dossiers. | 100 | 8.77(ii) | Mandatory | Author and coordinate design models/specifications, review works agency field records, update coordinated record models, and compile certification/handover dossiers. | Yes |  |  |  | The Consultant shall author and coordinate design-stage models, calculations, specifications and acceptance criteria; the Works Agency and vendors shall prepare source installation and fabrication records; the PMC shall verify day-to-day field records; and the Consultant shall review field information for design intent, update the coordinated record model and compile the certification and handover dossier.
R-414 | The Consultant must submit a documented option appraisal for AIIMS Patna's written decision whenever compliant design alternatives differ materially in cost, reliability, containment, or maintainability. | 101 | 8.78(i) | Mandatory | Submit documented option appraisals detailing design basis, compliance, CAPEX, OPEX, lifecycle cost, supply chain, and recommendations for AIIMS Patna's approval. | Yes |  |  |  | Whenever compliant alternatives differ materially in containment assurance, reliability, capital cost, recurring cost, maintainability, energy use, space or procurement dependency, the Consultant shall submit a documented option appraisal stating the design basis, assumptions, compliance and biosafety effects, Validation and certification implications, CAPEX, OPEX, lifecycle cost, supply-chain availability, proprietary dependency, maintainability and reasoned recommendation for AIIMS Patna’s written decision.
R-415 | The Consultant must provide a preliminary estimate of annual recurring Operation & Maintenance costs as part of the DPR. | 101 | 8.78(v) | Mandatory | Include in the DPR a preliminary estimate of annual recurring O&M costs covering energy, water, consumables, critical system AMCs, and filter/component replacements. | Yes |  |  |  | The Consultant shall provide, as part of the DPR, a preliminary estimate of the annual recurring Operation & Maintenance cost of the proposed facility (energy, water, consumables, AMC of critical systems, and anticipated filter/component replacement cycle), to enable AIIMS Patna to plan for sustainable long-term operation.
R-416 | Provide all technical, documentary, and professional support to make the BSL-3 Laboratory operationally ready, maintainable, testable, validatable, and certification-ready, coordinating deliverables with the Biosafety Expert and other specialists. | 102 | 8.79 | Mandatory | Provide required technical, documentary, and professional support, coordinate deliverables with the Biosafety Expert and relevant specialists, and remain professionally responsible for their completeness, consistency, technical adequacy, and suitability. | Yes |  |  |  | In addition to preparing the architectural and engineering design, the A&E Consultant shall provide all technical, documentary and professional support necessary to make the BSL-3 Laboratory operationally ready, maintainable, testable, validatable and certification-ready.
R-417 | Provide technical, documentary, and presentation support to AIIMS Patna for coordination with the Institutional Biosafety Committee (IBSC) and other regulatory bodies. | 102 | 8.79(i)(a) | Mandatory | Prepare and submit drawings, design notes, biosafety justifications, compliance matrices, risk assessment inputs, commissioning/validation documents, and responses to observations for IBSC review and approval. | Yes |  |  |  | The A&E Consultant shall provide necessary technical, documentary and presentation support to AIIMS Patna for coordination with the Institutional Biosafety Committee (IBSC) and other competent institutional / regulatory bodies, wherever required. The Consultant shall prepare and submit drawings, design notes, biosafety justifications, compliance matrices, risk assessment inputs, commissioning / validation documents and responses to observations required for IBSC review and approval.
R-418 | Attend meetings with IBSC or other review bodies as directed and incorporate observations and recommendations into design and project documents. | 102 | 8.79(i)(b) | Mandatory | Attend meetings with IBSC or other review bodies as directed by AIIMS Patna and incorporate their observations/recommendations in relevant design and project documents. | Yes |  |  |  | The Consultant shall attend meetings with IBSC or other review bodies, as directed by AIIMS Patna, and shall incorporate the observations / recommendations of such bodies in the relevant design and project documents.
R-419 | Prepare a separate Biosafety Design Basis Report / Containment Philosophy Report for the BSL-3 Laboratory in consultation with the approved Biosafety Expert / Consultant. | 102 | 8.80 | Mandatory | Prepare a separate Biosafety Design Basis Report / Containment Philosophy Report defining biosafety design intent, containment philosophy, zoning, airflow, flows, decontamination, access control, biosecurity, emergency provisions, equipment, and validation-by-design, and submit to AIIMS Patna for review. | Yes |  |  |  | The A&E Consultant shall prepare a separate Biosafety Design Basis Report / Containment Philosophy Report for the BSL-3 Laboratory. The report shall define the biosafety design intent, containment philosophy, facility zoning, pressure cascade, directional airflow, personnel / material / sample / waste flow, decontamination strategy, access control philosophy, biosecurity considerations, emergency provisions, biosafety-critical equipment requirements and validation-by-design approach.
R-420 | Prepare a Certification, Validation and Regulatory Approval Strategy Plan for the BSL-3 Laboratory. | 103 | 8.81 | Mandatory | Prepare and submit a Certification, Validation and Regulatory Approval Strategy Plan identifying approvals, certification requirements, validation requirements, inspection requirements, testing agencies, documentation, responsibility matrix, timelines, and readiness criteria. | Yes |  |  |  | The A&E Consultant shall prepare a Certification, Validation and Regulatory Approval Strategy Plan for the BSL-3 Laboratory. The plan shall identify applicable approvals, certification requirements, validation requirements, inspection requirements, testing agencies, documentation requirements, responsibility matrix, tentative timelines and readiness criteria for successful commissioning, validation, certification and operational approval of the facility.
R-421 | Prepare staff training modules and mock training protocols for operational readiness of the BSL-3 Laboratory. | 103 | 8.82 | Mandatory | Prepare staff training modules and mock training protocols with inputs from the Biosafety Expert / Consultant covering entry/exit, PPE, emergency response, decontamination, waste handling, access control, alarm response, equipment safety, BSC operation, and incident reporting. | Yes |  |  |  | The A&E Consultant shall prepare staff training modules and mock training protocols required for operational readiness of the BSL-3 Laboratory. The training material shall cover facility entry and exit protocol, PPE donning and doffing, emergency response, decontamination procedures, waste handling, access control, alarm response, equipment safety, biosafety cabinet operation interfaces, incident reporting and other facility-specific biosafety procedures.
R-422 | Prepare an AMC Strategy and Lifecycle Maintenance Plan for all biosafety-critical systems, utilities, and equipment. | 103 | 8.83 | Mandatory | Prepare an AMC Strategy and Lifecycle Maintenance Plan detailing preventive maintenance, maintenance frequency, consumables and spares, filter replacement schedules, calibration, annual testing, recertification, agency qualifications, and lifecycle obligations. | Yes |  |  |  | The A&E Consultant shall prepare an AMC Strategy and Lifecycle Maintenance Plan for all biosafety-critical systems, utilities and equipment. The plan shall include preventive maintenance requirements, recommended maintenance frequency, consumables and spares, filter replacement schedule, calibration requirements, annual testing requirements, recertification requirements, agency qualification requirements and lifecycle maintenance obligations.
R-423 | Prepare facility-specific cleaning, disinfection, and decontamination protocols for the BSL-3 Laboratory. | 103 | 8.84 | Mandatory | Prepare facility-specific cleaning, disinfection, and decontamination protocols in consultation with the Biosafety Expert / Consultant defining zones, frequency, disinfectants, contact time, surface compatibility, spill response, fumigation, waste handling, emergency decontamination, and records. | Yes |  |  |  | The A&E Consultant shall prepare facility-specific cleaning, disinfection and decontamination protocol for the BSL-3 Laboratory. The protocol shall define cleaning zones, frequency, approved disinfectants, contact time, surface compatibility, spill response, fumigation / room decontamination strategy, waste handling procedure, emergency decontamination procedure and records to be maintained.
R-424 | Specify the HEPA filter integrity testing methodology for supply and exhaust HEPA filters. | 104 | 8.85(i) | Mandatory | Define the HEPA test method (including PAO / DEHS aerosol challenge testing or approved equivalent), acceptance criteria, testing frequency, access requirements, scanning requirements, documentation format, certification requirements, and testing responsibilities. | Yes |  |  |  | The A&E Consultant shall specify the HEPA filter integrity testing methodology for supply and exhaust HEPA filters, including PAO / DEHS aerosol challenge testing or any other approved equivalent method as per applicable standards and regulatory requirements. The Consultant shall define the test method, acceptance criteria, testing frequency, access requirements, scanning requirements, documentation format, certification requirements and responsibilities for testing.
R-425 | Ensure HEPA housings, ducts, access panels, BIBO arrangements, and associated systems are designed for safe and effective testing, certification, maintenance, and replacement. | 104 | 8.85(ii) | Mandatory | Design HEPA housings, ducts, access panels, BIBO arrangements, and associated systems to allow safe testing, certification, maintenance, and replacement without compromising containment integrity. | Yes |  |  |  | The design shall ensure that HEPA housings, ducts, access panels, BIBO arrangements and associated systems are suitable for safe and effective testing, certification, maintenance and replacement without compromising containment integrity.
R-426 | Integrate operational readiness deliverables into the main architectural, engineering, tender, commissioning, validation, and handover documents. | 104 | 8.86(i) | Mandatory | Integrate all specified operational readiness deliverables into main project documents, taking full responsibility for preparation, coordination, submission, and approval while obtaining required inputs, comments, and concurrence from the approved Biosafety Expert / Consultant. | Yes |  |  |  | All deliverables specified for operational readiness shall be integrated into the main architectural, engineering, tender, commissioning, validation and handover documents. The A&E Consultant shall remain fully responsible for preparation, coordination, submission and approval of these deliverables, while obtaining necessary inputs, review comments and concurrence from the approved Biosafety Expert / Consultant wherever biosafety-critical matters are involved.
R-427 | Conduct an Inception Meeting with AIIMS Patna immediately upon award of work / issuance of Notice to Proceed, with mandatory participation of the Biosafety Expert / Consultant. | 105 | 9.1 | Mandatory | Conduct an Inception Meeting upon award/Notice to Proceed to confirm project scope, deliverables, timelines, communication protocol, and key technical requirements, ensuring mandatory participation of the approved Biosafety Expert / Consultant. | Yes |  |  |  | Immediately upon award of work / issuance of Notice to Proceed, the A&E Consultant shall conduct an Inception Meeting with AIIMS Patna to confirm the project scope, deliverables, timelines, communication protocol and key technical requirements for establishment of the BSL-3 Laboratory. Participation of the approved Biosafety Expert / Consultant shall be mandatory at this stage.
R-428 | Submit an Inception Report covering project understanding, methodology, work plan, deliverable schedule, and other foundational planning elements. | 105 | 9.1(i) | Mandatory | Submit an Inception Report covering project understanding, methodology, work plan, deliverable schedule, design responsibility matrix, role of the Biosafety Expert / Consultant, site verification plan, document submission protocol, preliminary risk areas, and required decisions/information. | Yes |  |  |  | The A&E Consultant shall submit an Inception Report covering project understanding, methodology, work plan, deliverable schedule, design responsibility matrix, role of the Biosafety Expert / Consultant, site verification plan, document submission protocol, preliminary risk areas and information / decisions required from AIIMS Patna.
R-429 | Nominate a Project Director/Single Point of Contact and an authorised alternate at inception. | 105 | 9.1(ii) | Mandatory | Nominate a Project Director/Single Point of Contact and an authorised alternate to channel all formal instructions, decisions, submissions, comment registers, and interface escalations. | Yes |  |  |  | At inception the Consultant shall nominate a Project Director/Single Point of Contact and an authorised alternate. All formal instructions, decisions, submissions, comment registers and interface escalations shall pass through the agreed communication protocol; nomination of a single point shall not reduce the responsibility of any discipline lead or Key Personnel.
R-430 | Include a named meeting-attendance and sign-off matrix in the Inception Report, ensure prescribed personnel attend reviews, and adhere to personnel substitution rules. | 105 | 9.1(iii) | Mandatory | Include a named meeting-attendance and sign-off matrix in the Inception Report, ensure mandatory attendance and sign-offs by key personnel, record detailed minutes, and obtain prior written approval from AIIMS Patna before substituting or absenting any named person. | Yes |  |  |  | The Inception Report shall include a named meeting-attendance and sign-off matrix. The Project Director and Biosafety Expert shall attend all prescribed core reviews; the BIM Manager or BIM Architect, Equipment Planning and Integration Specialist, Environmental and Statutory Compliance Expert and relevant discipline leads shall attend and sign the meetings and deliverables concerning their scope. Minutes shall record names, roles, attendance mode, decisions, actions, owner and due date. No named person may be substituted or remain absent from a required review without prior written approval of AIIMS Patna, except in a demonstrable emergency. Any replacement shall have qualifications and experience not lower than the approved person, complete a documented handover and cause no additional cost, delay or reduction in specialist input.
R-431 | Carry out all necessary surveys, measurements, site verifications, and investigations of the existing building and utilities. | 105 | 9.2 | Mandatory | Perform comprehensive surveys and investigations including architectural layout, structural condition, dimensional verification, electrical, UPS/DG, HVAC, water, drainage, ETP/EDS, fire safety, access routes, equipment movement, shafts, penetrations, roof utility locations, and vibration/noise issues. | Yes |  |  |  | The A&E Consultant shall carry out all surveys, measurements, site verification and investigations required to assess the suitability of the existing building and utilities for establishment of certification ready BSL-3 Laboratory. This shall include architectural layout, structural condition, dimensional verification, electrical supply, UPS / DG feasibility, HVAC feasibility, water supply, drainage, ETP / EDS feasibility, fire safety provisions, access routes, equipment movement, service shafts, penetrations, roof / terrace utility locations, vibration / noise issues and other site constraints affecting design or execution.
R-432 | Submit a Survey and Investigation Report assessing existing building and utilities suitability and outlining deficiencies and modification requirements. | 106 | 9.2(i) | Mandatory | Submit a Survey and Investigation Report stating site conditions, deficiencies, constraints, risks, augmentation requirements, limitations, approvals, design implications, and suitability/retrofit needs for the BSL-3 Laboratory. | Yes |  |  |  | The A&E Consultant shall submit a Survey and Investigation Report clearly identifying site conditions, deficiencies, constraints, risks, utility augmentation requirements, structural / service limitations, statutory approval requirements and design implications. The report shall clearly state whether the existing building and utilities are suitable for the proposed BSL-3 Laboratory or require strengthening, modification, additional services, re-routing, retrofitting or regulatory approvals.
R-433 | Prepare and submit the Concept Design for the BSL-3 Laboratory vetted by the Biosafety Expert / Consultant. | 106 | 9.3 & 9.3(i) | Mandatory | Prepare and submit the Concept Design Report and drawings (including layouts, zoning, flow diagrams, room schedule, equipment/utility matrix, biosafety philosophy, and broad engineering concepts) reviewed and vetted by the approved Biosafety Expert / Consultant. | Yes |  |  |  | The Concept Design submission shall include conceptual layouts, zoning diagrams, flow diagrams, preliminary room schedule, preliminary equipment and utility matrix, biosafety design philosophy, preliminary risk considerations, broad engineering concepts and identification of major design decisions requiring approval of AIIMS Patna. The approved Biosafety Expert / Consultant shall review and vet the Concept Design from biosafety, biosecurity, containment, workflow, commissioning, validation and certification perspective. The A&E Consultant shall submit the Concept Design Report and drawings to AIIMS Patna.
R-434 | Develop the approved Concept Design into a Schematic Design package and obtain AIIMS Patna approval before proceeding to detailed design. | 106 | 9.4 & 9.4(i) | Mandatory | Submit the Schematic Design Report, drawings, biosafety review comments, and Action Taken Report (covering schematic drawings, room data sheets, design calculations, schematics, P&IDs, equipment utility matrix, preliminary BOQ/cost estimate, compliance matrix, and risk register) for approval after vetting by the Biosafety Expert. | Yes |  |  |  | The Schematic Design submission shall include schematic drawings, room data sheets, preliminary design calculations, system schematics, P&IDs wherever applicable, preliminary equipment utility matrix, preliminary BOQ/cost estimate, design compliance matrix and updated risk register. The approved Biosafety Expert / Consultant shall review and vet all biosafety-critical components, including layout, HVAC containment, pressure zoning, BSC integration, ETP/EDS, decontamination, waste flow, access control and validation requirements. The A&E Consultant shall submit the Schematic Design Report, drawings, biosafety review comments and Action Taken Report to AIIMS Patna for approval before proceeding to detailed design.
R-435 | Develop the approved Schematic Design into a complete, coordinated, and technically adequate Detailed Design package. | 106 | 9.5 | Mandatory | Prepare a comprehensive Detailed Design package covering architectural, structural, HVAC containment, electrical, ELV, fire safety, plumbing, ETP/EDS, BMS, access control, security, utility systems, equipment interfaces, penetrations, and decontamination systems. | Yes |  |  |  | The A&E Consultant shall develop the approved Schematic Design into a complete, coordinated and technically adequate Detailed Design package for the BSL-3 Laboratory. The Detailed Design shall cover architectural, structural, HVAC containment, electrical, ELV, fire safety, plumbing, ETP/EDS, BMS, access control, security, utility systems, biosafety-critical equipment interfaces, service penetrations, decontamination systems and all other
R-436 | Detailed Design submission must include coordinated drawings, calculations, room data sheets, matrices, specifications, and risk registers demonstrating compliance with BSL-3 standards. | 107 | Clause 9.5(i) | Mandatory | Prepare and submit the Detailed Design package with coordinated drawings, design calculations, room data sheets, equipment utility matrix, P&IDs, technical/material specifications, design compliance matrix, updated risk register, commissioning and validation requirements, testing criteria, preliminary BOQ, and cost estimate complying with BSL-3 standards. | Yes |  |  |  | The Detailed Design submission shall include coordinated drawings, design calculations, room data sheets, equipment utility matrix, P&IDs, technical specifications, material specifications, design compliance matrix, updated risk register, commissioning requirements, validation requirements, testing criteria, preliminary BOQ and cost estimate. The design shall clearly demonstrate compliance with the approved Biosafety Design Basis Report, pressure cascade philosophy, workflow requirements, containment strategy and applicable BSL-3 standards/guidelines.
R-437 | Biosafety Expert must review and vet all biosafety-critical drawings and documents, and Consultant must submit an Action Taken Report. | 107 | Clause 9.5(ii) | Mandatory | Ensure the approved Biosafety Expert reviews and vets all biosafety-critical drawings and documents, and submit the Detailed Design package with review comments and Action Taken Report without conditional or incomplete submissions. | Yes |  |  |  | The approved Biosafety Expert / Consultant shall review and vet all biosafety-critical drawings and documents, including layout, pressure zoning, HVAC containment, BSC integration, ETP/EDS, decontamination provisions, access control, waste flow, emergency provisions and validation requirements. The A&E Consultant shall submit the Detailed Design package along with biosafety review comments and Action Taken Report to AIIMS Patna. Conditional or incomplete submission of drawings/documents shall not be accepted.
R-438 | Consultant must prepare a separate procurement package for the Project Management Consultant (PMC). | 107 | Clause 9.6 | Mandatory | Draft and prepare a separate PMC procurement package defining construction-management scope, staffing, reporting, quality, safety, testing, commissioning coordination, document control, and interface responsibilities. | Yes |  |  |  | The Consultant shall prepare a separate PMC procurement package defining construction-management scope, staffing, reporting, quality, safety, measurement, testing, terms and conditions, commissioning coordination, document control and interface responsibilities. The PMC package shall not transfer the Consultant’s design responsibility or create overlapping authority.
R-439 | Consultant must prepare tender documents for the engagement of a Construction Agency. | 107 | Clause 9.7 | Mandatory | Prepare and draft detailed tender documents for engaging a construction agency and establish an interface schedule distinguishing responsibilities. | Yes |  |  |  | Construction Agency is proposed separately from the PMC, the Consultant shall prepare and draft detailed tender documents for engagement of construction agency and support a clear interface schedule distinguishing design-intent review, day-to-day supervision, safety administration, measurement, progress control, contractor instructions, testing coordination and as-built compilation.
R-440 | Consultant must prepare a complete, non-proprietary Good-for-Tender package specifying at least three established brands for each item. | 107 | Clause 9.8 | Mandatory | Prepare a procurement-ready Good-for-Tender package with drawings, performance specifications, final BOQ, and nominate at least three established compliant makes/brands per item, or provide detailed justification and obtain prior AIIMS Patna approval if fewer exist. | Yes |  |  |  | The Consultant shall prepare a complete, coordinated, non-proprietary and procurement-ready Good-for-Tender package. It shall include drawings; objective and measurable performance specifications; final BOQ and rate-analysis basis; equipment and utility schedules; at least three established compliant makes or brands (This nomination of brand name criteria at least three establish brand shall be applicable in all cases related in this RFP whether it is expressly written or not) for each specified item where reasonably available; detailed justification, market assessment and prior AIIMS Patna approval wherever fewer than three suitable makes exist; construction security and O&M-access requirements; statutory-clearance responsibility schedule; quality and barrier-inspection requirements; Master Inspection, Testing and Commissioning Control Plan; risk-based FAT, SAT and IST; independent-Validation support; training; handover-takeover; and Defect Liability obligations.
R-441 | BOQ must be linked to drawings and specifications, use approved rates, and include consistency documentation. | 108 | Clause 9.8 | Mandatory | Link the BOQ to drawings and specifications, utilize approved rate sources, include rate analysis for non-schedule items, and support it with quantity sheets and a consistency certificate. | Yes |  |  |  | The BOQ shall be linked to the drawings and specifications, use approved rate sources, include rate analysis for non-schedule items, and be supported by quantity sheets and a consistency certificate.
R-442 | Consultant must ensure procurement package integration, perform cross-package contradiction review, and submit a signed interface-completeness certificate. | 108 | Clause 9.9 | Mandatory | Align Construction Agency and PMC/CMA procurement packages to the same design baseline and submit a signed interface-completeness certificate following a cross-package contradiction review. | Yes |  |  |  | The Construction Agency and PMC/CMA procurement packages shall use the same approved design baseline, terminology, interface matrix, submission workflow, hold-points, test responsibilities, record requirements and handover gates. The Consultant shall conduct a cross-package contradiction review before issue and submit a signed interface-completeness certificate.
R-443 | Consultant must provide bid assistance to AIIMS Patna during the selection of construction, maintenance, and project management agencies. | 108 | Clause 9.10 | Mandatory | Support AIIMS Patna during pre-bid meetings, site visits, technical query responses, corrigenda preparation, and technical clarifications. | Yes |  |  |  | The A&E Consultant shall provide complete technical assistance to AIIMS Patna during the bidding process for selection of the construction & maintenance agency and project management agency for establishment of the BSL-3 Laboratory. The Consultant shall support AIIMS Patna in pre-bid meetings, site visits by prospective bidders, preparation of replies to technical queries, review of bidder requests, preparation of corrigendum / addendum, clarification of drawings, specifications, BOQ, technical conditions, commissioning requirements, validation requirements and biosafety-critical provisions.
R-444 | Consultant and Biosafety Expert must review technical bids and assist AIIMS Patna with bid evaluations. | 108 | Clause 9.10(i) | Mandatory | Review bidder technical submissions, prepare evaluation notes, highlight deviations, and provide reasoned technical recommendations involving the Biosafety Expert for containment and biosafety matters. | Yes |  |  |  | The A&E Consultant shall review the technical submissions of bidders, assist in preparation of technical evaluation notes, identify deviations / deficiencies / ambiguities, and provide reasoned technical recommendations to AIIMS Patna. The approved Biosafety Expert / Consultant shall be involved wherever bidder queries or submissions relate to biosafety, containment, HVAC pressure cascade, BSC integration, ETP/EDS, decontamination, HEPA testing, commissioning, validation or certification requirements. All responses and recommendations shall be clear, non-ambiguous, technically justified and consistent with the approved tender documents.
R-445 | Consultant must furnish pre-design deliverables as a distinct package prior to finalizing Concept Design. | 109 | Clause 10.2(i) | Mandatory | Prepare and submit an Inception Report, Site Verification Report, User Requirement Confirmation Report, Biosafety Risk Assessment Report, Biosafety Basis of Design and Containment Philosophy Report, and Personnel/Material/Sample/Waste Flow Report as a separate package prior to finalizing Concept Design. | Yes |  |  |  | The Deliverable Matrix and the design-stage drawing work therefore presuppose that the following pre-design deliverables have been completed and accepted by the Institute; the Consultant shall furnish these as a distinct, separately reviewable package before the Concept Design is finalized, and not retrospectively as part of the Concept submission. The Consultant shall prepare and submit: (a) An Inception Report setting out the Consultant’s understanding of the assignment, work plan, and team deployment (b) A Site Verification Report, recording the as-existing structural, services, and spatial condition of the identified location and the Consultant’s assessment of its suitability (or the modifications required) to host a BSL-3 facility (c) A User Requirement / Need Confirmation Report, recording the intended use, throughput, and operational requirements of the facility as confirmed with the Laboratory In-charge and the Institute (d) A Biosafety Risk Assessment Report, identifying the biological agents and procedures the facility is intended to accommodate and the resulting containment requirements, prepared with the Institutional Biosafety Committee (IBSC) and forming the technical basis for the engineering, administrative, work-practice, and PPE controls selected in subsequent design stages (e) A Biosafety Basis of Design Report and Containment Philosophy and Pressure Cascade Report, recording the pressure-cascade strategy, zoning logic, and engineering-control philosophy that the subsequent drawings, CFD report and technical specifications shall implement. (f) A Personnel / Material / Sample / Waste Flow Report, mapping clean-to-dirty movement and segregation for personnel, samples, materials, and waste, to be reflected in the zoning drawings.
R-446 | Consultant must prepare and submit a Regulatory and Certification Strategy Note. | 110 | Clause 10.2(i)(g) | Mandatory | Submit a Regulatory and Certification Strategy Note mapping statutory approvals and clearances from IBSC/RCGM/DBT/Ministry. | Yes |  |  |  | A Regulatory and Certification Strategy Note, identifying the statutory approvals and IBSC/RCGM/DBT/Ministry clearances applicable to the facility and the stage at which each is to be pursued, consistent with the applicable certification pathway.
R-447 | Written approval of the complete pre-design package by AIIMS Patna must be obtained within the sixty-day Phase-I period prior to Concept Design commencement. | 110 | Clause 10.2(i)(h) | Mandatory | Secure written approval of the complete pre-design package from AIIMS Patna within the official 60-day Phase-I period as a mandatory precondition to starting Concept Design. | Yes |  |  |  | AIIMS Patna’s written approval of the complete pre-design package is a precondition to commencement of Concept Design. The pre-design package shall include the verified site and existing-building visit, approved User Requirements, Biosafety Risk Assessment, Basis of Design, equipment and utility matrix, workflow and zoning, initial cost plan, risk and interface registers and identified AIIMS decisions. The Consultant shall complete this approval process within the official sixty-day Phase-I period.
R-448 | Consultant must incorporate every deliverable matrix row into its Program and complete it within Phase-I or post-design milestones without omission. | 111 | Clause 10.3(ii) | Mandatory | Include every row of the deliverable matrix in the detailed Program, assign completion dates and responsible specialists, and finish each within the Day 1–Day 60 Phase-I period or applicable event-linked post-design timeframe. | Yes |  |  |  | Every row of the deliverable matrix is a binding minimum. The Consultant shall place each row in its detailed Program, assign a completion date and responsible specialist, and complete it within the official Day 1–Day 60 Phase-I period or the applicable event-linked post-design period. No row may be omitted, deferred without written approval or treated as a separate payment event merely because it also appears in another technical requirement.
R-449 | Consultant must provide a minimum prescribed set of drawings progressively culminating in the complete Good-for-Tender package. | 111 | Clause 10.4(ii) | Mandatory | Submit drawing deliverables including site layout/zoning, floor plans for each level, reflected ceiling plans, sectional drawings through the containment envelope, and architectural finishing schedules. | Yes |  |  |  | At minimum, the drawing set shall include: (a) Site layout and zoning drawings indicating the containment perimeter, access control points, and material/personnel flow segregation (b) Floor plans for each level, distinguishing BSL-3 core zones, anterooms, airlocks, and support/clean corridors (c) Reflected ceiling plans showing HEPA filter housings, light fittings, and service penetrations (d) Sectional drawings through the containment envelope showing wall, floor, and ceiling sealing details (e) Architectural finishing schedules (door, window, ironmongery, and surface-finish schedules) appropriate to a sealed, decontaminable environment
R-450 | Drawings must be developed to a complete level of constructability, and any drawings found deficient during review must be revised at no additional cost. | 112 | Clause (i) | Mandatory | Develop fully constructible drawings and revise any deficient drawings at no additional cost. | Yes |  |  |  | The Consultant is expected to develop drawings to a level of constructability that a contracting agency can execute without requiring the Consultant to issue clarifications at site for matters that ought to have been resolved at design stage. Drawings found deficient in this respect during review shall be revised at no additional cost.
R-451 | HVAC documentation must include an airflow single-line schematic and coordinated double-line layouts with complete specifications, without using single-line and double-line terminology interchangeably. | 112 | Clause (iii) | Mandatory | Provide detailed HVAC documentation including single-line schematics and coordinated double-line supply and exhaust duct layouts. | Yes |  |  |  | HVAC documentation shall include an overall airflow/single-line schematic and coordinated double-line supply and exhaust duct layouts showing sizes, elevations, pressure zones, dampers, HEPA housings, BIBO access, test ports, sensors, fire interfaces, supports and maintenance clearances. The terminology ‘single-line’ and ‘double-line’ shall not be used interchangeably.
R-452 | Electrical documentation must encompass single-line diagrams, power distribution architecture, load/panel schedules, earthing layouts, protection philosophy, emergency-power segregation, and connection schedules. | 112 | Clause (iv) | Mandatory | Submit comprehensive electrical documentation covering power distribution, panel schedules, earthing, emergency power, and coordinated builder-work requirements. | Yes |  |  |  | Electrical documentation shall include the main single-line diagram, transformer/DG/UPS and distribution architecture, load and panel schedules, cable and earthing layouts, protection philosophy, emergency-power segregation, equipment connection schedule and coordinated builder-work requirements.
R-453 | Instrumentation and controls documentation must provide complete field-device lists, I/O schedules, alarm/trend schedules, interlock matrices, control narratives, and network architecture. | 112 | Clause (v) | Mandatory | Furnish complete instrumentation, ELV, and BMS/EMS documentation including point schedules, interlock matrices, and network architecture. | Yes |  |  |  | Instrumentation and controls documentation shall include the complete field-device and input/output list for electrical, ELV and BMS/EMS systems, AI/AO/DI/DO point schedule, alarm and trend schedule, cause-and-effect/interlock matrix, control narrative, network architecture and interface responsibility for every connected instrument and equipment item.
R-454 | CFD outputs must be submitted in report form with supporting visualizations and must be resubmitted if the HVAC design is materially revised. | 113 | Clause 10.5(i)(e) | Mandatory | Submit CFD reports with contour plots, vector plots, and pressure charts, and revise/resubmit if HVAC design changes. | Yes |  |  |  | CFD outputs shall be furnished in report form with supporting visualization (contour plots, vector plots, pressure profile charts) and shall be revisited and resubmitted if the HVAC design is materially revised after the initial CFD run.
R-455 | CFD analysis must include simulations under normal conditions, door-opening scenarios, and maximum personnel and equipment load. | 113 | Clause 10.5(i)(f) | Mandatory | Conduct CFD simulations demonstrating airflow direction, pressure recovery, containment integrity, temperature distribution, air velocity, and absence of stagnant zones or reverse airflow under all specified operational scenarios. | Yes |  |  |  | The CFD analysis and outputs shall include simulations under normal operating conditions, door-opening scenarios and maximum anticipated personnel and equipment load within the laboratory. The results shall demonstrate airflow direction, pressure recovery, containment integrity, temperature distribution, air velocity and the absence of stagnant zones or reverse airflow.
R-456 | Specifications for materials and equipment must be non-proprietary and identify at least three established compliant makes based on documented market assessment. | 113 | Clause 10.6(i)(b) | Mandatory | Perform a market assessment and recommend at least three reputed compliant makes for each material and equipment category. | Yes |  |  |  | For each material/equipment category the Consultant shall, after documented market assessment, identify at least three established standard/reputed makes that comply fully with the same objective specification.
R-457 | Proprietary items or categories with fewer than three makes require justification, prior approval, and conflict-of-interest disclosure. | 114 | Clause 10.6(i)(b) | Mandatory | Provide technical justification, market and lifecycle assessment, disclosure of financial interest, and obtain AIIMS Patna approval before proposing items with fewer than three makes. | No — check |  |  |  | A genuinely proprietary item or category with fewer than three compliant makes may be proposed only with technical justification, market-availability and lifecycle-support assessment, conflict-of-interest disclosure and prior approval of AIIMS Patna. The Consultant, its JV members, experts and connected persons shall disclose and avoid any direct or indirect financial or commercial interest in a recommended make/vendor.
R-458 | The specification and BOQ package must include an auditable abstract estimate and rate-analysis dossier for major items. | 114 | Clause 10.6(ii) | Mandatory | Submit an auditable abstract estimate and rate-analysis dossier detailing data sources, wastage, labor, accessories, testing, spares, taxes, and reconciliation with BIM take-offs. | Yes |  |  |  | The specification/BOQ package shall include an auditable abstract estimate and rate-analysis dossier for major civil, HVAC, electrical (including transformer(s), DG, UPS and panels), ETP/EDS, BMS/security, barrier and laboratory-equipment items. The dossier shall state the data source/market basis, quantity and wastage basis, labour/installation, accessories, testing, spares, taxes/duties assumptions and reconciliation with drawings and BIM quantity take-offs.
R-459 | The Consultant must develop a federated multi-disciplinary BIM model and submit a BIM Execution Plan (BEP) at project inception. | 114 | Clause 10.8(i) | Mandatory | Submit a BIM Execution Plan at project inception and develop and maintain a federated BIM model covering all project disciplines. | Yes |  |  |  | The Consultant shall develop and maintain a federated, multi-disciplinary BIM model (Architectural, Structural, HVAC/Containment, Electrical, Plumbing/PHE, Fire) for the project, progressing through defined Levels of Development (LOD) aligned to design stage. A BIM Execution Plan (BEP) shall be submitted at project inception, setting out modeling responsibility, software platform, coordinate system, and model exchange protocol.
R-460 | The Consultant must deliver LOD 300–350 BIM modeling for Phase-I design and review LOD 400 and LOD 500 models prepared by the works contractor. | 115 | Clause 10.9(i) | Mandatory | Author BIM models up to LOD 300–350, review LOD 400 submissions for design intent, and coordinate and submit the final accepted LOD 500 record model at handover. | Yes |  |  |  | LOD 300–350 modelling of the containment envelope, airlocks, plant, penetrations and coordinated HVAC/MEP routing is mandatory for the Consultant’s Phase-I design. The Consultant’s design-authoring obligation is capped at LOD 350. LOD 400 fabrication/shop models and the field-updated LOD 500 record model shall be authored by the Works Agency/vendor under the works contract. The Consultant shall review LOD 400 for design intent and shall coordinate, consistency-check and submit the accepted LOD 500 record model as part of handover; such review shall not transfer responsibility for concealed, unauthorised or inaccurately recorded work.
R-461 | A clash detection report identifying hard and soft/clearance clashes must be submitted at LOD 300 and LOD 350 design freezes. | 116 | Clause 10.11(i)(a) | Mandatory | Generate and submit clash detection reports at LOD 300 and LOD 350 milestones identifying physical intersections and clearance clashes. | Yes |  |  |  | A clash detection report at each major coordination milestone (minimum: at LOD 300 freeze and at LOD 350 freeze), identifying hard clashes (physical intersections) and soft/clearance clashes (insufficient maintenance or access clearance)
R-462 | The Consultant must prepare and deliver a Commissioning Plan aligned with the Validation Master Plan. | 116 | Clause 10.12(i) | Mandatory | Deliver a Commissioning Plan identifying each system to be commissioned, testing methods, acceptance criteria, and commissioning sequence. | Yes |  |  |  | A Commissioning Plan identifying each system to be commissioned, the test method and acceptance criteria for each, and the sequence in which systems are to be commissioned, consistent with the Validation Master Plan.
R-463 | Commissioning must be completed and its Deviation and Closure Register closed before independent Validation is initiated. | 117 | Clause 10.12 (ix) | Mandatory | Complete commissioning and close out the Deviation and Closure Register prior to initiating or coordinating independent Validation. | Yes |  |  |  | Commissioning shall be completed and its Deviation and Closure Register shall be closed before independent Validation is initiated; the Consultant shall not proceed to coordinate independent Validation while Commissioning remains open.
R-464 | The Good-for-Tender works package must include a Master Inspection, Testing and Commissioning Control Plan. | 117 | Clause 10.12 (x) | Mandatory | Include a comprehensive Master Inspection, Testing and Commissioning Control Plan covering contractor's ITP, FAT/SAT/IST applicability, prerequisites, test criteria, and non-conformity routes in the Good-for-Tender works package. | Yes |  |  |  | The Good-for-Tender works package shall include a Master Inspection, Testing and Commissioning Control Plan that identifies for each system the contractor’s ITP, FAT/SAT/IST applicability, prerequisites, method statement, calibrated instrument, sample size, hold/witness/review point, acceptance criterion, record, responsible agency, non-conformity route and retest/closure requirement.
R-465 | A Barrier Integrity Inspection Plan defining mock-ups and hold-points must be prepared and executed. | 117 | Clause 10.12 (xii) | Mandatory | Prepare a Barrier Integrity Inspection Plan defining mock-ups and hold-points for all containment envelope components and participate in inspections and final sign-off. | Yes |  |  |  | A Barrier Integrity Inspection Plan shall define mock-ups and hold-points for walls, floors, ceilings, coving, doors, glazing, service penetrations, sleeves, dampers, HEPA housings, pass-through equipment and the barrier autoclave.
R-466 | The Consultant must prepare and deliver a Validation Master Plan. | 118 | Clause 10.13(i)(a) | Mandatory | Develop and deliver a Validation Master Plan detailing testing sequence, responsibilities, protocols, criteria, and agency participation. | Yes |  |  |  | A Validation Master Plan identifying the complete sequence of Testing, Commissioning and independent Validation for every facility system, together with prerequisites, responsibilities, calibrated instruments, test protocols, acceptance criteria, hold and witness points, deviation and CAPA control, retesting, records and the required participation of the Works Agency, PMC, Consultant, Laboratory In-charge, Biosafety Officer, IBSC and Expert Committee.
R-467 | Validation must be arranged through an ISO/IEC 17025-accredited organization in the presence of the Expert Committee. | 118 | Clause 10.13(i)(b) | Mandatory | Arrange facility validation by an ISO/IEC 17025-accredited organization, witnessed by the Expert Committee and in liaison with facility officers. | Yes |  |  |  | Arrangement of Validation by a qualified, competent ISO/IEC 17025-accredited organization, conducted in the presence of the Expert Committee constituted for the purpose (comprising scientists experienced in establishing/working in BSL-3 laboratories, engineers experienced in establishing/maintaining BSL-3 laboratories, and a representative of the Central/State Pollution Control Board), and in liaison with the Laboratory In-charge and Biosafety Officer.
R-468 | The Consultant must coordinate performance-based validation tests and compile the Validation Report. | 118 | Clause 10.13(i)(c) | Mandatory | Coordinate cleanroom validation, air balancing, negative pressure, particle count, and other guideline tests, and compile results into a Validation Report. | Yes |  |  |  | Coordination of the performance-based tests required at Validation (clean room validation, air balancing test, room negative pressure test, particle count test, temperature and relative humidity test, light level test, spore strip test, and other tests as prescribed in the Guidelines), and compilation of the test results into a Validation Report.
R-469 | The Consultant must verify all applicable statutory approvals prior to/during validation. | 118 | Clause 10.13(i)(d) | Mandatory | Verify alongside the validating agency that all statutory approvals (fire safety, municipal, pollution board, electrical, etc.) and IBSC/RCGM/DBT approvals are obtained. | Yes |  |  |  | Verification, alongside the validating agency, that all statutory approvals applicable to the facility (fire safety, municipal corporation, pollution control board, electrical inspector, natural climatic safety, boiler inspection authority, as applicable) are in place, and that approvals from IBSC/RCGM/DBT/the Controlling Ministry have been obtained.
R-470 | A Validation Readiness Checklist confirming commissioning closure and required facility documentation must be prepared and presented. | 118 | Clause 10.13(i)(g) | Mandatory | Prepare and present the Validation Readiness Checklist confirming closure of Commissioning deviations and availability of all required facility documentation to the validating agency and Expert Committee. | Yes |  |  |  | A Validation Readiness Checklist confirming closure of Commissioning and its Deviation and Closure Register and confirming availability of: the document describing the laboratory mandate and features; the technical and operation manual for engineering systems and biosafety; the biosafety manual; personnel training and competence records; approved facility operating SOPs; and documented evidence of completed mock drills. The Checklist shall be presented to the independent Validation
R-471 | Independent Validation is a mandatory prerequisite to statutory Certification. | 119 | Clause 10.13(i)(h) | Mandatory | Do not prepare or submit any certification application while independent Validation remains open. | Yes |  |  |  | Independent Validation is a precondition to statutory Certification; no certification application shall be prepared or submitted while Validation remains open.
R-472 | The Consultant must prepare the certification application under the Guidelines on behalf of AIIMS Patna. | 119 | Clause 10.14(i)(a) | Mandatory | Complete the prescribed certification application for AIIMS Patna's signature and submission. | Yes |  |  |  | The certification application in the prescribed format under the Guidelines, completed on AIIMS Patna’s behalf for the Institute’s signature and submission.
R-473 | A compliance traceability matrix mapping all guideline requirements must be prepared. | 119 | Clause 10.14(i)(c) | Mandatory | Map every requirement of the Guidelines to the corresponding drawing, calculation, report, or record demonstrating compliance. | Yes |  |  |  | A compliance traceability matrix mapping every applicable requirement of the Guidelines, including facility design and construction, SOPs, training and competency, documentation and biosafety risk assessment, to the specific drawing, calculation, report or record that demonstrates compliance.
R-474 | The Consultant must submit the certification-ready dossier, respond to observations, and close Consultant-attributable deficiencies without additional fee. | 120 | Clause 10.14(i)(h) | Mandatory | Support the certification process, provide clarifications, attend inspections, and resolve deficiencies until the certificate of compliance is issued, without charging additional fees. | Yes |  |  |  | Preparation of the certification application, compilation and authentication of supporting documentation, responses to observations, assistance during review and inspection and closure of Consultant-attributable deficiencies are distinct Consultant obligations. These obligations continue until the applicable certificate of compliance is issued and the facility is ready for final operational handover, without additional fee beyond the accepted Contract Price.
R-475 | Training must be delivered in two distinct stages (pre-validation readiness and final O&M handover). | 121 | Clause 10.15(i) | Mandatory | Conduct Stage 1 pre-Validation training before formal Validation, and deliver Stage 2 final operational and handover training prior to final facility handover. | Yes |  |  |  | Training shall be provided in two stages because personnel training, competence records and mock-drill evidence are required for Validation and certification readiness. Stage one (pre-Validation readiness training) shall be completed sufficiently before formal Validation. Stage two (final operational, O&M and handover training) shall be delivered after completion of Commissioning and availability of substantially complete as-built and O&M information, but before final operational handover.
R-476 | The Consultant must provide SOP outlines, competence-record formats, and mock-drill documentation templates for Stage 1 training. | 121 | Clause 10.16 | Mandatory | Furnish biosafety-relevant engineering SOP outlines, competence-record formats, and mock-drill templates sufficiently in advance of Validation. | Yes |  |  |  | A standard operating procedure outline for facility-level biosafety-relevant operations (airlock use, decontamination cycle operation, filter change-out procedure) — recognizing that detailed biosafety SOPs are the Institute’s responsibility, but the engineering basis for these SOPs is a Consultant output — furnished sufficiently in advance of Validation so that the Institute can finalize SOPs and complete personnel competence assessment before the Validation Readiness Checklist is presented.
R-477 | The Consultant must deliver O&M manuals, training sessions, and a field-verified LOD 500 record model package under Stage 2. | 121 | Clause 10.17 | Mandatory | Prepare O&M manuals, conduct hands-on orientation sessions on operations and emergency procedures, and provide an updated, field-verified LOD 500 record model and digital package. | Yes |  |  |  | The final field-verified LOD 500 record model and digital package shall be authored or updated from Works Agency and vendor field information, reviewed and coordinated by the Consultant and handed over for ongoing facility-management use.
R-478 | The deadline for the complete Good-for-Tender package is Day 60 from the Notice to Proceed. | 121 | Clause 10.18(i) | Submission logistics | Submit the complete Phase I Good-for-Tender design and tender-readiness package by Day 60 from the Notice to Proceed. | Yes |  |  |  | The official deadline for the complete Good-for-Tender package is Day 60 from the Notice to Proceed. Day 61 to Day 75 is not an additional design period and may be used only for exceptional correction, clarification and closure of consolidated AIIMS Patna comments
R-479 | The Consultant shall not freeze the next design stage, issue procurement or construction documents, or permit construction to proceed without written approval. | 123 | 10.19 (i) | Mandatory | Refrain from freezing the next design stage, issuing procurement/construction documents, or permitting construction to proceed without obtaining written approval. | Yes |  |  |  | Where comments are overdue, the Consultant may continue non-prejudicial preparatory coordination at its own risk after written notice, but shall not freeze the next design stage, issue a procurement/construction document or permit construction to proceed without the required written approval.
R-480 | Draft DPR technical specifications must include at least three reputed and available brand names. | 123 | 10.19 | Mandatory | Specify at least three reputed and available brand names in the technical specifications for Milestone M-7. | Yes |  |  |  | technical specifications with at least three reputed and available brand name for the specifications,
R-481 | Under Milestone M-9, the Consultant must support pre-bid activities including providing technical replies, participating in meetings, clarifying requirements, and preparing corrigenda/addenda. | 123 | 10.20 | Mandatory | Prepare technical replies to pre-bid queries, attend the pre-bid meeting, clarify drawings and specifications, and prepare technical corrigenda/addenda. | Yes |  |  |  | Prepare and provide technical replies to pre-bid queries; participate in the pre-bid meeting; clarify drawings, BOQ, specifications, testing, commissioning, validation and biosafety requirements; and prepare required technical corrigenda/addenda.
R-482 | Under Milestone M-10, the Consultant must provide technical bid evaluation assistance and submit recommendations for award. | 123 | 10.20 | Mandatory | Provide technical bid-evaluation assistance, analyse deviations/clarifications, respond to evaluation queries, and submit reasoned technical recommendations. | Yes |  |  |  | Provide technical bid-evaluation assistance, analyse deviations and clarifications, respond to evaluation queries and submit reasoned technical recommendations required for award of the relevant contract.
R-483 | Under Milestone M-11, the Consultant must submit the construction-support mobilisation package, review containment-critical submissions, and complete the initial site-compliance review without performing day-to-day supervision. | 124 | 10.20 | Mandatory | Submit mobilisation package, review containment-critical shop/vendor submissions for design intent and biosafety, complete first site-compliance review, and abstain from day-to-day construction supervision. | Yes |  |  |  | Submit the construction-support mobilisation package; review the first consolidated batch of containment-critical shop/vendor submissions for design intent and biosafety; and complete the first prescribed site-compliance review. The Consultant shall not exercise day-to-day construction supervision.
R-484 | Under Milestone M-13, the Consultant must update and submit the Commissioning Plan, Validation Master Plan, testing protocols, acceptance criteria, SOP package, and training program. | 124 | 10.20 | Mandatory | Update and submit the Commissioning Plan, Validation Master Plan, testing/qualification protocols, acceptance criteria, commissioning/validation matrices, SOP package, and training Program. | Yes |  |  |  | Update and submit the Commissioning Plan, Validation Master Plan, testing/qualification protocols, acceptance criteria, commissioning/validation matrices, SOP package and training Program based on the constructed facility and available as-built information.
R-485 | Under Milestone M-15, the Consultant must complete operational/O&M training and submit final as-built drawings, field-verified BIM model, editable files, O&M documentation, SOPs, records, and compliance dossier. | 124 | 10.20 | Mandatory | Conduct final operational/O&M training and compile/submit final as-built drawings, field-verified BIM model, digital files, O&M documentation, SOPs, records, and compliance dossier prior to handover. | Yes |  |  |  | Complete final operational/O&M training before final operational handover; review and submit final as-built drawings, field-verified BIM model, native/editable/digital files, O&M documentation, SOPs, training records, asset information and the final compliance dossier.
R-486 | The Consultant must remain available without additional fee for clarification, inspection support, and correction of deficiencies until the certificate of compliance is issued. | 125 | 10.20 | Mandatory | Provide ongoing clarification, inspection support, and deficiency correction without claiming additional fees until the certificate of compliance is issued. | Yes |  |  |  | The Consultant shall remain available without additional fee for subsequent clarification, inspection support and correction of Consultant-attributable deficiencies until issuance of the certificate of compliance.
R-487 | Milestone numbering M-1 to M-16 must be used consistently across all technical and payment documentation. | 125 | 10.20 (i) | Mandatory | Apply milestone designations M-1 through M-16 consistently in all technical and payment submissions. | Yes |  |  |  | Milestone numbering M-1 to M-16 shall be used consistently in the technical and payment documentation.
R-488 | The Consultant must submit each deliverable with a transmittal note identifying changes made since the prior submission. | 125 | 10.21 (i)(a) | Submission logistics | Include a transmittal note highlighting changes since the last submission with every submitted deliverable. | Yes |  |  |  | Consultant submits the deliverable with a transmittal note identifying what has changed since the last submission of that deliverable, if any
R-489 | The Consultant must resubmit deliverables with a comment-disposition log explaining how each comment was addressed or the technical justification for disagreement. | 126 | 10.21 (i)(e) | Submission logistics | Provide a comment-disposition log with resubmissions detailing how each comment was resolved or outlining technical rationale for any disagreement. | Yes |  |  |  | Consultant resubmits with a comment-disposition log showing how each comment has been addressed, or, where the Consultant disagrees with a comment, the technical basis for that position
R-490 | Any deviation from an approved deliverable identified at a later stage must be flagged to the Institute before proceeding. | 126 | 10.22 (v) | Mandatory | Notify the Institute of any deviations from previously approved deliverables prior to proceeding with work. | Yes |  |  |  | Any deviation from an approved deliverable, identified at a later stage, shall be flagged by the Consultant to the Institute before proceeding, rather than carried forward silently.
R-491 | Construction-stage drawings must bear evidence of approval under the prescribed workflow before being acted upon by a contracting agency. | 126 | 10.22 (vi) | Mandatory | Ensure that construction-stage drawings have documented evidence of approval before implementation. | Yes |  |  |  | No construction-stage drawing shall be acted upon by a contracting agency unless it bears evidence of approval under this workflow.
R-492 | Deliverables must be submitted in the specified format and completeness, including BIM/CAD native files where specified rather than PDF alone. | 127 | 10.23(e) | Mandatory | Submit deliverables in the specified format and completeness, including native BIM/CAD files where required. | Yes |  |  |  | (e) Format and completeness — submission in the format and completeness specified for that deliverable type, including native files where BIM/CAD native files are a specified part of the deliverable, not PDF alone.
R-493 | Each relevant milestone deliverable must include measurable room-wise and system-wise BSL-3 acceptance data traceable to drawings, calculations, specifications, and validation protocols. | 127 | 10.24(i) | Mandatory | Submit measurable room-wise and system-wise acceptance data traceable to drawings, calculations, specifications, and validation protocols for each relevant milestone. | Yes |  |  |  | In addition to the general acceptance criteria, each relevant milestone shall include measurable room-wise and system-wise acceptance data. At minimum, the following shall be submitted and traceable to drawings, calculations, specifications and validation protocols:
R-494 | The Consultant must define use cases, information structure, asset identifiers, update responsibility, and minimum data for a maintainable digital representation of containment-critical and maintainable assets. | 127 | 10.25(i) | Mandatory | Define use cases, information structure, asset identifiers, update responsibilities, and minimum data needed for the digital twin within the BIM Execution Plan. | Yes |  |  |  | The Consultant shall define the use cases, information structure, asset identifiers, update responsibility and minimum data needed for a maintainable digital representation of containment-critical and maintainable assets.
R-495 | The Consultant must not withhold project data or passwords/configuration records required for accepted facility systems and ensure no proprietary software prevents AIIMS Patna from accessing or operating the facility data. | 128 | 10.25(ii) | Mandatory | Provide open/interoperable formats, source/native files, passwords, and configuration records, ensuring AIIMS Patna can access, operate, maintain, test, revalidate, or modify facility data without proprietary software dependency. | Yes |  |  |  | The Consultant is not required to transfer its general corporate licences, but shall not withhold project data or passwords/configuration records needed for the accepted facility systems.
R-496 | A controlled Common Data Environment (CDE) must be utilized for submissions, reviews, version control, approval status, transmittals, and audit trail in accordance with the BIM Execution Plan. | 128 | 10.26(i) | Mandatory | Use a controlled CDE for submissions, reviews, versioning, transmittals, and approvals with agreed folder structure, access rights, and workflows. | Yes |  |  |  | A controlled CDE shall be used for submissions, reviews, version control, approval status, transmittals and audit trail. Folder structure, naming, access rights, retention, backup and approval workflow shall be agreed at inception in accordance with the approved BIM Execution Plan.
R-497 | COBie or approved equivalent structured asset-data format must be delivered for maintainable assets at agreed project stages. | 128 | 10.27(i) | Mandatory | Provide COBie or approved equivalent structured asset-data format containing asset identifiers, locations, make/model, warranty, maintenance, calibration, spares, manuals, and linked document references. | Yes |  |  |  | COBie or an approved equivalent structured asset-data format shall be provided for maintainable assets at the agreed stages, including asset identifier, location, make/model when available, warranty, maintenance, calibration, spares, manuals and linked document references.
R-498 | Each stage submission must contain quality assurance deliverables including discipline check, coordination check, biosafety review, traceability update, and signed stage-completeness certificate. | 128 | 10.28(i) | Mandatory | Include all specified quality assurance checks, registers, clash/interface status reports, and a signed stage-completeness certificate with each stage submission. | Yes |  |  |  | Each stage submission shall include a discipline check, interdisciplinary coordination check, biosafety review, requirement-traceability update, comment-disposition register, revision history, clash/interface status and signed stage-completeness certificate.
R-499 | Biosafety deliverables must include risk assessments, Basis of Design, zoning/workflow/pressure matrices, failure-mode matrix, decontamination strategy, commissioning/validation matrix, and certification-support dossier index. | 128 | 10.29(i) | Mandatory | Submit all mandatory biosafety documentation deliverables as specified in the clause. | Yes |  |  |  | Biosafety deliverables shall include the risk assessment, Basis of Design, zoning/workflow and pressure matrices, biosafety comment register, failure-mode matrix, decontamination strategy, commissioning/validation matrix, compliance matrix, certification-support dossier index and annual-revalidation access plan.
R-500 | Phase-I Milestones M-1 to M-8 must be completed within 60 days from Notice to Proceed/LoA. | 129 | 11.2(i) | Mandatory | Complete all Phase-I Milestones M-1 to M-8 culminating in the accepted Final DPR and tender packages within 60 days of NTP/LoA. | Yes |  |  |  | Time is the essence of Contract: Milestones M-1 to M-8 shall collectively be completed within sixty (60) days from the Notice to Proceed/LoA, culminating in the accepted Final DPR and complete Good-for-Tender packages for the Works Agency and PMC/CMA.
R-501 | Bidders must submit a preliminary dependency-linked Day 1 to Day 60 Work Program in stage-wise tabular format on letterhead as part of the Technical Bid. | 129 | 11.2(ii) | Submission logistics | Submit a preliminary dependency-linked Day 1-Day 60 Work Program on letterhead in tabular format with the Technical Bid, showing stage durations, start/completion days, specialist deployment dates, review gates, and completion of M-8 by Day 60. | Yes |  |  |  | The Bidder shall submit, as part of its Technical Bid and on its letterhead, a preliminary dependency-linked Day 1-Day 60 Work Program in a stage-wise tabular format. For each stage and sub-stage, the Program shall state the duration and the proposed start and completion days reckoned from the Notice to Proceed.
R-502 | The Consultant must refine and submit the final dependency-linked Day 1 to Day 60 Work Program within 5 days from Notice to Proceed. | 129 | 11.2(iii) | Mandatory | Refine and submit the final Day 1-Day 60 Work Program within 5 days of receiving the Notice to Proceed. | Yes |  |  |  | Within five (5) days from the Notice to Proceed, the Consultant shall refine and submit the final dependency-linked Day 1-Day 60 Work Program, consistent with the Program submitted in its accepted Technical Bid and without dilution of any bid commitment, mandatory deliverable or completion requirement.
R-503 | The Consultant must execute each triggered Phase-II service within the timeframe prescribed in the accepted Program, written instruction, or contract. | 130 | 11.3(ii) | Mandatory | Perform each event-triggered Phase-II service within the prescribed schedule. | Yes |  |  |  | The Consultant shall perform each triggered service within the period expressly prescribed in the accepted Program, written instruction or controlling Contract.
R-504 | The Consultant must submit and implement a time-bound Recovery Program at no additional cost within 3 working days of awareness or direction regarding schedule slippage. | 130 | 11.3(iii) | Mandatory | Submit and implement a detailed, time-bound Recovery Program within 3 working days of noticing progress slippage or receiving direction from AIIMS Patna. | Yes |  |  |  | Where actual or forecast progress indicates slippage likely to affect completion of Milestone M-8 or timely performance of any event-linked service relating to tender support, construction-stage technical support, commissioning, independent validation, certification support, handover or Defect Liability Support, the Consultant shall, within three (3) working days of AIIMS Patna's direction or of becoming aware of the slippage, whichever is earlier, submit and implement a time-bound Recovery Program at no additional cost.
R-505 | The Consultant must prepare and submit the certification-ready dossier, address observations, authenticate documents, and close all Consultant-attributable deficiencies for Certification-Support Completion. | 130 | 11.4(i) | Mandatory | Complete and submit the certification-ready dossier, respond to review observations, and authenticate professional deliverables. | Yes |  |  |  | The Consultant shall complete and submit the certification-ready dossier, respond to all observations communicated and capable of performance, revise and authenticate its professional documents and close every Consultant-attributable deficiency required for Certification-Support Completion.
R-506 | The Consultant must continue to provide all necessary technical and documentary certification support at no additional fee until the certificate of compliance is issued. | 130 | 11.4(ii) | Mandatory | Provide continuing technical and documentary support within the Contract Price, including attending inspections and meetings, addressing queries, and revising drawings until final compliance certification is achieved. | Yes |  |  |  | After acceptance of the certification-ready dossier and release of Milestone M-16, the Consultant shall, within the accepted Contract Price and without additional fee, continue to provide all technical and documentary support reasonably required for completion of the certification process to the extent arising from or connected with its design, drawings, calculations, specifications, coordination, testing and commissioning plans, validation-support documents, certification dossier or other professional Services.
R-507 | A&E Consultant must complete M-1 to M-8 and Good-for-Tender packages within 60 days, provide construction-stage reviews, prepare testing and commissioning control plans, support validation, and prepare handover deliverables. | 132 | 12.1 (iv) | Mandatory | Complete M-1 to M-8 and Good-for-Tender packages within 60 days of Phase-I, provide reviews and attendance at hold-points, prepare Commissioning and Testing Control Plans, support validation, and prepare certification dossier and handover deliverables. | Yes |  |  |  | A&E Consultant—completes M-1 to M-8 and the Good-for-Tender packages within the 60-day Phase-I period; thereafter provides periodic construction-stage design-intent and biosafety review, shop/vendor submission review, design clarification and prescribed hold-point attendance without undertaking continuous supervision, measurement or site administration. It prepares the Commissioning and Testing Control Plans, coordinates/reviews critical testing and commissioning executed by the Works Agency under PMC day-to-day coordination, supports independent Validation by the agency appointed/approved by AIIMS Patna, and prepares the certification-ready dossier and handover deliverables. It retains responsibility for its own design, coordination, advice and Consultant-attributable corrections.
R-508 | Consultant must nominate a Project Director/Single Point of Contact, authorised alternate, and named discipline/specialist leads (on payroll except Biosafety Expert). | 133 | 12.3 (i) | Mandatory | Nominate a Project Director/SPOC, alternate, and required specialist leads on payroll (except Biosafety Expert) covering all listed disciplines. | Yes |  |  |  | The Consultant shall nominate a Project Director/Single Point of Contact, authorised alternate and named discipline/specialist leads sufficient for the scope. The specialist team (on payroll except Biosafety Expert) shall include, as applicable, the Biosafety Expert, Laboratory Equipment Planning and Integration Specialist, BIM Manager/BIM Architect, Environmental/Statutory Compliance Expert, HVAC/Containment Lead, Electrical Lead, Fire/Life-Safety Lead, Structural Lead and Commissioning/Validation Coordinator.
R-509 | Every person proposed as Key Personnel must be on the bidder's regular payroll, substantiated by a Chartered Accountant certificate or acceptable supporting document, and external specialists must be fully disclosed. | 133 | 12.3 (ii) | Mandatory | Submit a Chartered Accountant certificate or acceptable independent document proving Key Personnel are on regular payroll, and fully disclose any external specialist/sub-consultant with required declarations. | Yes |  |  |  | Every person proposed as Key Personnel shall be on the Bidder’s regular payroll or rolls, and the Bidder shall establish that status through a Chartered Accountant certificate or another independent supporting document acceptable to AIIMS Patna. Any external specialist or Sub-consultant shall be fully disclosed with its proposed scope, legal and professional relationship, conflict-of-interest declaration and responsibility allocation and shall be deployed only after written approval where required.
R-510 | The named lead must personally review and sign discipline deliverables, evidenced by minutes, review comments, signed technical notes, and stage certificates. | 133 | 12.3 (iii) | Mandatory | Ensure the named discipline lead personally reviews, signs, and participates in deliverables and reviews, evidencing attendance through signed documentation. | Yes |  |  |  | The named lead shall personally review and sign the deliverables within that discipline. Attendance and sign-off shall be evidenced through minutes, review comments, signed technical notes and stage certificates; use of support staff shall not substitute the required participation of the named lead.
R-511 | Named personnel shall not be withdrawn or replaced without prior written approval of AIIMS Patna, and replacements must meet equivalent qualifications and complete a documented handover. | 133 | 12.3 (iv) | Mandatory | Obtain written approval prior to replacing any named personnel, propose replacements with equal or higher qualifications, and submit credentials and documented handovers without cost to AIIMS Patna. | Yes |  |  |  | No named person shall be withdrawn or replaced without the prior written approval of AIIMS Patna, except where immediate temporary substitution is necessary because of death, serious illness or another circumstance demonstrably beyond the Consultant's control. Every proposed replacement shall possess qualifications, experience and competence not lower than those of the person being replaced, shall be deployed only after submission of supporting credentials and written approval, and shall complete a documented handover of all pending responsibilities, records, decisions and risks.
R-512 | As part of Milestone M-1, Consultant must submit a Project Delivery, Governance and Interface Plan along with a Procurement Package Matrix. | 134 | 12.4 (i) | Mandatory | Submit Project Delivery, Governance and Interface Plan and Procurement Package Matrix as part of M-1 covering all specified elements. | Yes |  |  |  | As part of M-1, the Consultant shall submit a Project Delivery, Governance and Interface Plan. It shall include the organisation chart; single-point communication protocol; RACI (Responsible, Accountable, Consulted, and Informed)/responsibility matrix; decision and approval matrix; meeting calendar and named attendance; document/submittal register; escalation route; and change-control workflow. Further, the Consultant shall submit a Procurement Package Matrix identifying each proposed procurement package, its scope, interfaces, estimated value, tender document responsibility and target issue date. At minimum, the Matrix shall address the Works Contract, PMC, independent validation/qualification, separate laboratory equipment packages, specialized systems and any O&M/AMC support package required by AIIMS Patna
R-513 | Consultant must include a live design and delivery risk register and an interface register in the Project Delivery Plan. | 134 | 12.4 (ii) | Mandatory | Include a live risk register covering risk attributes and a separate interface register covering discipline, user, agency, PMC, validation, statutory, and utility interfaces. | Yes |  |  |  | The Plan shall include a live design and delivery risk register recording each risk, cause, consequence, probability/impact, biosafety and cost effect, owner, mitigation, trigger, residual risk, target date and closure evidence. A separate interface register shall cover discipline, AIIMS-user, Works Agency, PMC, validation, statutory and utility interfaces.
R-514 | Consultant must issue a decision log and updated risks and interfaces at each formal review. | 134 | 12.4 (iv) | Mandatory | Issue a decision log along with updated risks and interfaces at every formal review. | Yes |  |  |  | At each formal review the Consultant shall issue a decision log and updated risks/interfaces.
R-515 | Consultant must prepare a tender-level Handover–Takeover Plan for procurement packages and update it at M-13, M-15, and final close-out. | 134 | 12.5 (i) | Mandatory | Prepare and include a Handover-Takeover Plan in works and PMC tender packages, and update it at milestones M-13, M-15, and close-out. | Yes |  |  |  | The Consultant shall prepare a tender-level Handover–Takeover Plan for inclusion in the Works Agency and PMC procurement packages and shall update it at M-13, M-15 and final close-out. The Plan shall allocate preparation, verification, review, acceptance and custody of physical assets, rooms/keys/access credentials, spares, consumables, warranties, source as-builts, BIM/COBie data, O&M manuals, SOP/engineering inputs, training records, testing/commissioning/validation records, statutory clearances, punch lists and defect registers.
R-516 | Consultant must identify all statutory, environmental, and safety clearances, prepare technical documentation and applications, attend meetings/inspections, and revise documents. | 135 | 12.6 (i) | Mandatory | Identify applicable clearances, prepare schedules, drawings, calculations, forms, technical replies, attend meetings/inspections, and promptly revise documents. | Yes |  |  |  | The Consultant shall identify all applicable statutory, environmental, pollution-control, biomedical-waste, fire/life-safety, electrical, lift, boiler or other approvals/clearances; prepare the compliance schedule, designs, calculations, drawings, forms and technical replies; attend inspections/meetings when required; and promptly revise its documents to close technical observations within its scope.
R-517 | Consultant must provide full and timely technical assistance for statutory applications without disclaiming support. | 135 | 12.6 (iii) | Mandatory | Provide full and timely technical assistance for statutory and clearance applications. | Yes |  |  |  | The Consultant shall provide full and timely technical assistance and shall not disclaim support on the ground that the Works Agency submits the application.
R-518 | Good-for-Tender package must prescribe a Construction Security and Biosecurity Plan. | 135 | 12.7 (i) | Mandatory | Incorporate a Construction Security and Biosecurity Plan in the Good-for-Tender package addressing all specified security and containment controls. | Yes |  |  |  | The Good-for-Tender package shall prescribe a Construction Security and Biosecurity Plan covering authorised personnel, identity and background/site induction as applicable, access zones, key/card control, escorting, material/equipment entry and removal, photography/data control, temporary IT/BMS access, after-hours work, incident reporting, housekeeping, pest/vector control, protection of installed containment systems and emergency coordination with AIIMS Patna.
R-519 | The Master Inspection, Testing and Commissioning Control Plan and Barrier Integrity Inspection Plan must be included in the Good-for-Tender works package. | 136 | 12.7 (iii) | Mandatory | Include the Master Inspection, Testing and Commissioning Control Plan and Barrier Integrity Inspection Plan in the Good-for-Tender works package defining all required inspection controls. | Yes |  |  |  | The Master Inspection, Testing and Commissioning Control Plan and the Barrier Integrity Inspection Plan shall be included in the Good-for-Tender works package and maintained throughout construction. The plans shall define inspection stages, hold and witness points, responsible parties, prerequisites, calibrated instruments, acceptance criteria, photographic and test records, deviation control, written release and retesting.
R-520 | Bidder legal entity eligibility requirements: must be a Proprietorship, Partnership, LLP, Company, Society under Indian law, or a Government Organization/PSU/Autonomous Body, or a registered Joint Venture. | 137 | 13.1(i) | Eligibility criteria | Ensure the bidder is an eligible legal entity (Proprietorship, Partnership, LLP, Company, Society, Government Organization/PSU, or registered Joint Venture) under applicable Indian laws. | Yes |  |  |  | The bidder shall be a Proprietorship Firm /Partnership Firm / Limited Liability Partnership (LLP) /Company/ Society, duly registered or formed under the applicable laws in India, or a Government Organization, including Public Sector Undertakings (PSUs)/ Autonomous Bodies/ and Government-owned/ controlled institutions, or a duly registered Joint Venture (JV) constituted as a legal entity under applicable laws in India or a Joint Venture duly constituted through a registered Joint Venture Agreement.
R-521 | The bidder (including JV partners) must have valid registrations for GSTIN, PAN, EPF, ESI, and applicable Labour Laws. | 137 | 13.1(ii) | Mandatory | Submit valid registration certificates for GSTIN, PAN, EPF, ESI, and applicable Labour Laws. | Yes |  |  |  | The bidder should have valid registrations regarding GSTIN, PAN, EPF, ESI, applicable Labour Law registrations, or equivalent registration certificate (as applicable) issued by the concerned authority/government as applicable to the subject Services. The same shall be applicable for JV also.
R-522 | Key Personnel must possess requisite qualifications, experience, and certifications. Lead Architect must be registered with the Council of Architecture (CoA), India, and submit declaration in the prescribed format with documentary proof. Submit documentary evidence of Key Personnel credentials with Technical Bid. | 137 | 13.1(iii) | Eligibility criteria | Submit declaration in the prescribed Annexure format along with documentary evidence of valid CoA registration for the Lead Architect, and submit documentary evidence of qualifications, experience, registrations, certifications, and professional memberships of proposed Key Personnel with the Technical Bid. | Yes |  |  |  | In addition to the above, the Bidder’s “Lead Architect” shall be registered with the Council of Architecture (CoA), India, as amended and applicable, and a declaration to this effect shall be submitted in the prescribed format provided in the Annexure, along with documentary evidence of valid CoA registration. Other domain experts as required for this project shall possess relevant qualifications, experience, and professional memberships / certifications, as and where applicable. The Bidder shall submit documentary evidence in support of the qualifications, experience, registrations, certifications and professional memberships of the proposed Key Personnel along with the Technical Bid.
R-523 | Bidder must not be insolvent, bankrupt, in liquidation, or subject to legal proceedings that materially affect ability to perform. | 137 | 13.1(iv) | Eligibility criteria | Ensure and confirm that the bidder is not insolvent, bankrupt, under liquidation/receivership, or undergoing winding up or suspension of business. | Yes |  |  |  | The Bidder shall not be insolvent, bankrupt, or under liquidation or receivership, nor be in the process of being wound up, nor have its affairs administered by a court or judicial authority, nor have its business activities suspended, nor be subject to any legal proceedings relating to the foregoing or otherwise which may materially affect its ability to perform the assignment under this RFP.
R-524 | Bidder and affiliates/subsidiaries must not be debarred, blacklisted, convicted under PCA or IPC/BNS, or deemed a national security risk, nor have changed its name or created a new Allied Entity following debarment. | 138 | 13.1(v) | Eligibility criteria | Confirm bidder and affiliates/subsidiaries are not blacklisted, debarred, convicted of moral turpitude or IPC/BNS offenses, considered a security risk, or formed as an allied entity post-debarment. | Yes |  |  |  | The bidder, including its affiliates and subsidiaries, shall not, as on the last date of submission of the bid: (a) Stand declared ineligible/ blacklisted/ banned/ debarred by a Procuring Organisation or its Ministry/ Department or as the case may be from participation in its procurement processes; and/ or (b) Convicted (within three years preceding the last date of bid submission) or stand declared ineligible/ suspended/ blacklisted/ banned/ debarred by appropriate agencies of the Government of India from participation in procurement processes of all its entities, for: (c) offences involving moral turpitude in business dealings under the Prevention of Corruption Act, 1988 or any other law; and/or (d) offences under the Indian Penal Code/Bharatiya Nyaya Sanhita, 2023 (BNS), or any other law for causing any loss of life/ limbs/ property or endangering Public Health during the execution of a public procurement contract/ or any other similar contract; and/ or (e) Suspected to be or of doubtful loyalty to the Country or a National Security risk as determined by appropriate agencies of the Government of India. (f) Not have changed its name or created a new “Allied Entity”, consequent to having declared ineligible/ suspended/ blacklisted/ banned/ debarred as above.
R-525 | Bidder must not have an association with a retired Gazetted officer without completion/waiver of the 1-year cooling-off period, or with near relatives of AIIMS Patna officials involved in the procurement. | 138 | 13.1(vi) | Eligibility criteria | Ensure no prohibited association exists with un-cleared retired Gazetted officers within the 1-year cooling-off period or near relatives of AIIMS Patna officials involved in the procurement. | Yes |  |  |  | Not have any association- as a bidder/ partner/ director/ employee in any capacity: (a) With a retired employee of Gazetted rank of the Central or State Government or its Public Sector Undertakings, who has not completed the prescribed cooling-off period of one (1) year (or such other period as stipulated by the concerned employer) from the date of retirement; provided that this restriction shall not apply where such person has obtained a valid waiver of the cooling-off period from their former organisation. (b) Whether direct or indirect, with the near relatives of any officer/official of AIIMS Patna who is involved, or is likely to be involved, in any stage of this procurement process, including preparation, evaluation, approval, or implementation.
R-526 | Bidder must not have a conflict of interest or attempt to induce other bidders to restrict competition under Competition Commission of India guidelines. | 138 | 13.1(vii) | Eligibility criteria | Comply with conflict of interest restrictions and Competition Commission of India guidelines. | Yes |  |  |  | Not have a conflict of interest as defined in the bid document, which substantially affects fair competition. No attempt should be made to induce any other bidder to submit or not to submit a bid to restrict competition as per applicable Competition commission of India guidelines.
R-527 | Qualifying architectural consultancy experience: successfully completed in last 7 financial years at least 2 architectural consultancy assignments for BSL-3/ABSL-3 labs or at least 1 for BSL-4/ABSL-4 labs in Government or reputed private organizations. | 139 | 13.1(viii) | Eligibility criteria | Furnish complete details of qualifying BSL-3/ABSL-3 or BSL-4/ABSL-4 consultancy assignments in the prescribed Annexure format, accompanied by performance/completion certificates and work orders. | Yes |  |  |  | *Qualifying architectural consultancy experience- The bidder shall have successfully completed, during the last seven (7) financial years, either: (a) At least two (02) architectural consultancy assignments/ services involving architectural & engineering design of BSL-3/ABSL-3 laboratory facilities (including modular or mobile laboratories); OR (b) At least one (01) architectural consultancy assignments/services involving architectural & engineering design of BSL-4/ABSL-4 laboratory facilities (including dedicated building BSL-4/ABSL-4 laboratories).
R-528 | Ongoing projects considered for pre-eligibility only if architectural design deliverables are fully completed and physical construction has started; requires mandatory performance and completion certificate for design services with work order. | 139 | 13.1(viii) Note (a) | Eligibility criteria | Submit a performance and completion certificate for design services supported with work order issued by the client along with the bid submission if claiming an ongoing project. | Yes |  |  |  | Experience from ongoing projects shall not be considered for pre-eligibility evaluation/assessment. However, those projects may be considered where architectural design deliverables have been fully completed and the project has progressed for the physical construction stage. In such cases, it is mandatory to submit a performance and completion certificate for the design services supported with work order, duly issued by the client (service recipient), along with the bid submission.
R-529 | Bidder must furnish complete details of each qualifying BSL-3/ABSL-3 or BSL-4/ABSL-4 assignment in the prescribed format at Annexure. | 139 | 13.1(viii) Note (b) | Mandatory | Fill out and submit the prescribed format at Annexure of the RFP for each claimed assignment. | Yes |  |  |  | The Bidder shall furnish complete details of each BSL-3/ABSL-3 and/or BSL-4/ABSL-4 architectural & engineering consultancy assignment claimed under this eligibility criterion in the prescribed format at Annexure of this RFP.
R-530 | Average annual turnover of not less than ₹50,00,000/- from architectural & engineering consultancy services during FY 2022-23, 2023-24, and 2024-25, supported by CA certificate with UDIN or audited balance sheets with UDIN. | 139 | 13.1(ix) | Eligibility criteria | Submit documentary evidence along with the Technical Bid, either as a CA certificate certifying turnover from architectural consultancy services with UDIN and firm details, OR audited balance sheets/financial statements certified by a CA bearing UDIN. | Yes |  |  |  | *Average annual turnover: The Bidder shall have an annual turnover of not less than ₹50,00,000/- from architectural & engineering consultancy services during these three financial years 2022-23, 2023-24 and 2024-25, and shall submit documentary evidence in support of the same along with the Technical Bid, either in the form of (i) A certificate issued by a Chartered Accountant clearly certifying the annual turnover from architectural consultancy services for the said financial years, duly mentioning the UDIN number & firm details. OR (ii) Audited balance sheets / financial statements for the said financial years duly certified by a Chartered Accountant and bearing UDIN number, wherever applicable.
R-531 | Bidder must confirm proposed Key Personnel with designations, brief profiles, time commitment, and suitability, along with supporting qualification/registration documents and a prescribed undertaking. | 140 | 13.1(x) | Mandatory | Provide Key Personnel details in the prescribed Annexure, submit supporting documents for qualifications/experience/certifications, and submit an undertaking confirming qualifications and experience along with the Technical Bid. | Yes |  |  |  | ***The Bidder shall provide and confirm, along with the Technical Bid, the names of proposed Key Personnel with their positions / designations intended for the assignment, along with brief profiles indicating their educational qualifications, professional experience, specific role assigned, proposed time commitment and suitability for the assignment, as per the prescribed Annexure. Further, the Bidder shall also submit complete supporting documents in respect of the qualifications, experience, registrations, certifications and professional memberships of the proposed Key Personnel, wherever applicable. The Bidder shall further submit an undertaking confirming that the proposed personnel possess the relevant qualifications and experience required for the assignment and that any misrepresentation, substitution without approval, or failure to substantiate such claims may result in rejection of the Proposal or other action as per the provisions of this RFP.
R-532 | Mandatory engagement of a Biosafety Expert / Consultant with consultancy/advisory experience in at least 2 BSL-3 labs or 1 BSL-4 lab in the last 7 financial years, with supporting documentary evidence. | 140 | 13.1(xi) | Eligibility criteria | Engage a Biosafety Expert/Consultant meeting the criteria and submit work orders, agreements, client certificates, completion certificates, or testimonials establishing their role and experience. | Yes |  |  |  | Engagement/Involvement of a qualified Biosafety Expert / Consultant shall be mandatory in this by the bidder. The proposed Biosafety Expert / Consultant must have relevant experience in biosafety, biosecurity, containment laboratory planning, design, review, commissioning, validation, certification support, and shall have successfully provided consultancy/advisory services relating for at least two (02) BSL-3 laboratories or one (01) BSL-4 laboratory in last seven financial years. The Bidder shall submit supporting documents such as work order, agreement, client certificate, completion certificate, testimonial, or any other documentary evidence clearly establishing the role and experience of the proposed Biosafety Expert / Consultant. Failure to meet this minimum requirement shall render the Proposal liable to be treated as non-responsive.
R-533 | Bidder must submit client references/testimonials for completed or substantially completed BSL-3 and/or BSL-4 laboratory projects as an additional document to the technical bid. | 140 | 13.1(x) | Mandatory | Submit client references and/or testimonials including client name, project title, scope, location, completion year, project value, consultancy fees charged, and client official email and telephone number. | Yes |  |  |  | The Bidder shall submit client references and/or testimonials in respect of completed or substantially completed Biosafety Level-3 (BSL-3) and/or Biosafety Level-4 (BSL-4) laboratory projects undertaken by the Bidder, as an additional document to technical bid. The details shall include name of the institution/client, project title, scope of services performed, project location, year of completion, project value, consultancy charged for that particular project, and contact details of the client representative, including official email ID and telephone number.
R-534 | Bidder must provide detailed case studies of previous BSL-3/BSL-4 projects and details of CAD, BIM, and analytical simulation tools (e.g., CFD). | 141 | 13.1(xi) | Mandatory | Provide detailed case studies covering project description, design philosophy, technical innovations, timeline, and validation/certification results, plus details of CAD systems, BIM capability, and simulation tools. | Yes |  |  |  | The firm should provide detailed case studies of previous BSL-3/BSL-4 projects, including: (a) Project description and scope; (b) Design approach and philosophy; (c) Technical innovations and features; (d) Construction timeline and final elements; (e) commissioning, validation and certification results. The bidder shall provide the details of availability of computer-aided design (CAD) systems (such as AutoCAD or equivalent), Building Information Modelling (BIM) capability, and analytical tools for simulation and performance assessment (including, where applicable, Computational Fluid Dynamics (CFD) analysis), or access to the same through in-house arrangements or formally established associations.
R-535 | Bidder must submit details of infrastructure, software, and technical resources including their deployment in similar assignments. | 141 | 13.1(xii) | Mandatory | Submit details of infrastructure, software, and technical resources deployed in similar assignments. | Yes |  |  |  | The bidder shall submit details of such infrastructure, software, and technical resources, including their deployment in similar assignments, to establish their capability to deliver the required services. Lack of adequate infrastructure and technical capability shall render the bid liable to be treated as non-responsive.
R-536 | Bidder may submit additional documents, information, or credentials demonstrating eligibility and technical capability. | 141 | 13.1(xiii) | Desirable | Optionally submit additional documents or credentials demonstrating technical capability and suitability. | Yes |  |  |  | The bidder may submit any additional documents, information, or credentials which, in its opinion, are relevant to demonstrate its eligibility, technical capability, and suitability for undertaking the proposed assignment.
R-537 | Copies of all relevant documents must be submitted duly self-attested and sealed along with application in the prescribed format. | 141 | 13.1 Note:- (i) | Submission logistics | Submit all relevant document copies duly self-attested and with official seal in the provided format. | Yes |  |  |  | The applicant must submit copies of all relevant documents only in accordance with bid requirements, duly self-attested & seal along with application wherein the format provided herewith.
R-538 | No exemption or relaxation in prior turnover or prior experience will be given to MSMEs or Start-ups for this project. | 141 | 13.1 Note:- (iii) | Eligibility criteria | MSMEs and Start-ups must meet full prior turnover and prior experience criteria without exemption. | Yes |  |  |  | *There shall be no exemption or relaxation in respect of prior turnover or prior experience at any stage of this BSL-3 establishment at AIIMS Patna for MSMEs or Start-ups, considering the critical nature of the services involved in public health. This is in accordance with the Department of Expenditure, Government of India Office Memorandum No. F.20/2/2014-PPD(Pt.) dated 20th September 2016.
R-539 | Bidder must clearly identify and nominate the specific project(s) relied upon for meeting BSL-3/BSL-4 experience, citing exact supporting document and page reference. | 141 | 13.1 Note:- (iv) | Submission logistics | Clearly identify and nominate specific qualifying projects with exact document names and page references in the bid submission. | Yes |  |  |  | Identification of qualifying experience: The bidder shall clearly identify and nominate the specific project(s) relied upon for meeting the prescribed BSL-3/BSL-4 experience requirement, together with the exact supporting document and page reference.
R-540 | Bidder must submit experience certificates and supporting documents issued by client organizations and signed by an authorized representative for all assignments claimed for eligibility or technical evaluation. | 142 | Clause (v)(a) | Eligibility criteria | Submit client-issued and authorized-signatory-signed experience certificates and supporting documents with the Technical Bid. | Yes |  |  |  | The Bidder shall submit, along with its Technical Bid, experience certificates and supporting documents for all assignments claimed towards eligibility and / or technical evaluation. Such certificates shall be issued by the client organization and signed by an authorized representative. Certificates issued by private individuals not authorized to sign shall not be accepted.
R-541 | Experience certificates must detail work name, client name, scope of services, facility type, bidder's design role for BSL-3/BSL-4, assignment value, award and completion dates, completion status, satisfactory performance, and signatory authority proof. | 142 | Clause (v)(b) | Eligibility criteria | Ensure experience certificates contain all specified details and attach documentary proof of signatory authority where applicable. | Yes |  |  |  | The experience certificate shall clearly indicate the name of work, client name, scope of services, type of laboratory / facility, role of the Bidder as designing the BSL-3/BSL-4 facility, value of consultancy assignment, date of award, date of completion of design services, completion status and satisfactory performance. Documentary proof of the signatory’s authority shall be submitted wherever applicable.
R-542 | For each private sector assignment claimed (related to BSL-3/BSL-4), bidder must mandatorily submit work order/agreement, completion certificate, tax invoices, payment proof, TDS/Form 26AS/AIS extract, proof of authorized signatory, and client contact details. | 142 | Clause (vi) | Eligibility criteria | Submit the full suite of required supporting documents for each private sector BSL-3/BSL-4 assignment along with the Technical Bid. | Yes |  |  |  | For each private sector assignment claimed towards eligibility or technical evaluation, the Bidder shall mandatorily submit the following documents along with the Technical Bid (it should be related to BSL-3/BSL-4): (a) work order / letter of award / agreement; (b) completion / performance certificate indicating scope, facility type, role, value, dates and satisfactory performance; (c) tax invoice(s) raised for the assignment; (d) proof of payment received against such invoice(s); (e) TDS certificate / Form 26AS / AIS extract / other applicable tax deduction evidence, wherever applicable; (f) proof that the certificate was issued by an authorized official of the client organization; and (g) name, designation, official email ID, contact number and office address of the client representative for verification.
R-543 | Completion/performance certificates should be on official letterhead with reference number, date, seal/stamp, and name, designation, and signature of issuing authority. | 143 | Clause (vii) | Mandatory | Provide client certificates featuring letterhead, reference number, date, stamp/seal, and authorized signatory details; avoid personal emails, unsigned certificates, or unverified private individuals. | Yes |  |  |  | The completion/performance certificate submitted by the Bidder shall preferably be issued on the official letterhead of the client organization and shall contain reference number, date, seal / stamp, name, designation and signature of the issuing authority. Certificates issued from personal email IDs, unsigned certificates, certificates without designation, certificates without contact details, or certificates issued by private individuals shall not be accepted.
R-544 | Bidder must ensure cooperation of the client organization in case AIIMS Patna conducts independent verification of private sector experience. | 143 | Clause (viii) | Mandatory | Ensure that issuing client organizations cooperate with independent verification by AIIMS Patna. | Yes |  |  |  | The Bidder shall ensure that the client organization cooperates with such verification, if required.
R-545 | All submitted work orders, completion certificates, invoices, payment proofs, tax records, and client confirmations must be consistent across client name, work description, value, period, scope, and role. | 143 | Clause (x) | Mandatory | Verify consistency across all submitted contractual and financial documents to avoid discrepancy or rejection. | Yes |  |  |  | The work order, completion certificate, invoice, payment proof, TDS / tax record and client confirmation must be broadly consistent with each other in respect of client name, work description, work value, period of assignment, scope of services and role of the Bidder.
R-546 | Bidder must submit an undertaking certifying that all experience documents are genuine, accurate, and issued by competent authority, accepting consequences of false documentation. | 143 | Clause (xii) | Mandatory | Submit the prescribed undertaking on the genuineness and accuracy of experience documents as per the attached format. | Yes |  |  |  | The Bidder shall submit an undertaking that all experience documents submitted by it are genuine, accurate and issued by competent authority of the respective client organization as per format attached. The undertaking shall further state that AIIMS Patna may verify the documents independently and may reject the Proposal, forfeit applicable security / invoke Bid Security Declaration, cancel the award, terminate the contract, debar / blacklist the Bidder and initiate any other action permissible under law if any document is found false, fabricated, forged, misleading or unverifiable.
R-547 | Bidder must propose Key Personnel with requisite qualifications, experience, registrations, and certifications, providing supporting documentary evidence in the Technical Bid. | 144 | Clause (xiv)(a) | Eligibility criteria | Submit details and supporting evidence for qualifications, experience, registrations, and certifications of proposed Key Personnel with the Technical Bid. | Yes |  |  |  | The Bidder shall propose only such Key Personnel who possess the requisite qualifications, experience, registrations, certifications and domain expertise relevant to the assignment. The Bidder shall submit, along with the Technical Bid, the details and documentary evidence in support of the qualifications, experience, registrations, certifications and professional memberships of the proposed Key Personnel, wherever applicable.
R-548 | Bidder must ensure availability of proposed Key Personnel for deployment and clearly state their proposed role, responsibility, and position. | 144 | Clause (xiv)(b) | Mandatory | Indicate proposed role, responsibility, and team position, and ensure Key Personnel availability. | Yes |  |  |  | The Bidder shall ensure that the proposed Key Personnel are available for deployment on the assignment and shall clearly indicate their proposed role, responsibility and position in the project team.
R-549 | Key Personnel evaluated in the Technical Bid must be deployed on the assignment and cannot be replaced without prior written approval of AIIMS Patna, with any approved replacement having equal or higher credentials. | 144 | Clause (xiv)(c) | Mandatory | Deploy evaluated Key Personnel and obtain prior written approval with equivalent or higher qualified replacements if substitution is necessary. | Yes |  |  |  | The Key Personnel proposed and evaluated as part of the Technical Bid shall be deployed for the assignment and shall not be replaced without the prior written approval of AIIMS Patna. Any replacement, if approved, shall possess qualifications and experience equal to or higher than those of the originally proposed personnel.
R-550 | Proposed Key Personnel must be on the bidder's regular payroll as of the Bid Due Date, substantiated by a Chartered Accountant Certificate based on payroll and banking records. | 144 | Clause (xiv)(e) | Eligibility criteria | Submit a CA Certificate certifying that each proposed Key Personnel is on regular payroll as on the Bid Due Date, paid through banking channels, detailing name, designation, and start date. | Yes |  |  |  | The Bidder shall propose only such Key Personnel who are on its regular rolls/payrolls as on the Bid Due Date. In support thereof, the Bidder shall submit a Certificate issued by a Chartered Accountant (CA), certifying, based on verification of the Bidder's payroll records and bank payment records, that each proposed Key Personnel is on the regular rolls/payrolls of the Bidder. The Certificate shall indicate the name, designation and the date from which the Key Personnel has been on the regular rolls/payrolls of the Bidder, and shall confirm that remuneration is being paid through the banking channel.
R-551 | Joint Ventures must consist of no more than two entities registered in India engaged in High containment Lab designing consultancy under a registered JV Agreement executed prior to the bid submission end date; Lead member must hold at least 51% participation and the other member at least 30%. | 145 | Clause 13.2(i) | Eligibility criteria | Form a JV of maximum two members with at least 51% Lead Member share and minimum 30% second member share via a registered JV Agreement prior to the bid submission deadline. | Yes |  |  |  | In cases where the bidder is a Joint Venture (JV), such JV shall consist only of entities in the form of firms or companies (including Partnership Firms, Limited Liability Partnerships, or Companies) or a Joint Venture duly constituted through a registered Joint Venture Agreement before the due bid submission end date who are engaged in High containment Lab designing architectural & engineering consultancy services, duly registered or incorporated under applicable laws in India (hereinafter referred to as ‘JV’), and shall comply with the following conditions: (a) Members should not be more than two (02). (b) The Lead member must have at least 51% participation. (c) The other member, who shall have a minimum participation of thirty percent (30%) in the Joint Venture, will be considered a substantial member. (d) In case the Bidder is a Joint Venture, the participation of the member other than the Lead Member shall not be less than thirty percent (30%). Any Joint Venture not complying with this requirement shall be treated as non-responsive.
R-552 | JV member participation shares must strictly commensurate with assigned scope, technical responsibility, and financial entitlement, clearly specified in the JV Agreement. | 145 | Clause 13.2(ii) | Mandatory | Ensure JV Agreement clearly defines commensurate scope, technical responsibility, and financial entitlement for each member. | Yes |  |  |  | The participation share of each member in the Joint Venture shall strictly commensurate with its assigned scope of work, technical responsibility, and financial entitlement, and shall be clearly defined in the JV Agreement. Any disproportionate, artificial, or token participation without corresponding responsibility shall render the application liable for rejection.
R-553 | A copy of the JV Agreement must be provided with the Technical Bid, specifying scope allocation, fee distribution aligned with participation, and a responsibility matrix. | 145 | Clause 13.2(iii) | Mandatory | Submit a copy of the JV Agreement with the Technical Bid containing detailed scope, fee distribution, and responsibility matrix. | Yes |  |  |  | The JV Agreement shall mandatorily provide for detailed scope allocation, fee/consideration distribution aligned with participation share, and a clear responsibility matrix covering design, coordination, compliance, and deliverables. Failure to establish a clear linkage between participation, scope, and fee shall render the application non-responsive. The copy of the JV agreement shall be provided with the technical bid.
R-554 | All contract payments shall be made to a single bank account in the name of the Joint Venture, with internal distribution proportional to declared participation. | 145 | Clause 13.2(iv) | Mandatory | Maintain and provide a single JV bank account for receiving contract payments. | Yes |  |  |  | All payments under the contract shall be made to a single bank account in the name of the Joint Venture. Internal distribution of payments shall be in proportion to the declared participation share, unless otherwise expressly approved by AIIMS Patna.
R-555 | JV members must submit a binding undertaking confirming genuine participation, absence of side agreements, proportionate consideration, and maintenance of the declared structure throughout the contract. | 145 | Clause 13.2(v) | Mandatory | Submit the required binding undertaking signed by all JV members. | Yes |  |  |  | The JV members shall submit a binding undertaking confirming that the declared participation reflects actual involvement that no side agreement exists altering the financial or technical arrangement, that no member shall receive consideration disproportionate to its participation share, and that the declared JV structure shall be maintained throughout the contract period.
R-556 | The Lead Member of a JV is prohibited from assigning, transferring, sub-contracting, or delegating core design responsibilities, or entering into back-to-back/proxy arrangements. | 146 | Clause 13.2(vi) | Mandatory | Ensure the Lead Member directly executes core design responsibilities without delegation or subcontracting. | Yes |  |  |  | The Lead Member shall not assign, transfer, sub-contract, or otherwise delegate the core design responsibilities, nor enter into any back-to-back or proxy arrangement with any member or third party in a manner that defeats the declared JV structure. Any such arrangement shall constitute a material breach of contract.
R-557 | All members of a Joint Venture shall be jointly and severally liable for contract performance, design accuracy/integrity, and statutory/biosafety compliance. | 146 | Clause 13.2(vii) | Mandatory | Accept joint and several liability across all JV members for project performance and liabilities. | Yes |  |  |  | All members of the Joint Venture shall be jointly and severally liable for the performance of the assignment, accuracy and integrity of design, and compliance with all biosafety, statutory, and contractual requirements. AIIMS Patna shall have the right to recover any dues, damages, or losses from any one or all members, irrespective of their participation share.
R-558 | Participation share, roles, and responsibilities of JV members must remain unchanged throughout the contract period unless prior written approval is granted. | 146 | Clause 13.2(x) | Mandatory | Maintain JV participation shares, roles, and responsibilities without modification during the contract term. | Yes |  |  |  | The participation share, roles, and responsibilities of the Joint Venture members shall remain unchanged throughout the contract period. Any change without prior written approval of AIIMS Patna shall be treated as a breach of contract.
R-559 | For a Joint Venture bidder, both members must independently possess relevant design experience, with each having designed at least one completed BSL-3/ABSL-3 or higher level laboratory as Architect/Design Consultant. | 146 | Clause 13.2(xii) | Eligibility criteria | Ensure each JV member independently proves experience of having designed at least one completed BSL-3/ABSL-3 or higher laboratory in the capacity of Architect/Design Consultant. | Yes |  |  |  | The essential experience requirement of designing either two (02) BSL- 3/ABSL-3 or one (01) BSL-4/ABSL-4 laboratory (higher lab) shall be assessed as follows: in case the Bidder is a Joint Venture (JV), both members shall independently possess relevant design experience, and the requirement shall be equitably distributed between the two members. Accordingly, each member shall have designed at least one (01) BSL-3/ABSL-3 or higher level laboratory. All such projects shall be completed, distinct, and executed in the capacity of Architect/Design Consultant as prescribed and similar to the architectural services referred in this bid document, and experience limited to execution, supply, or supervision without design responsibility shall not be considered.
R-560 | In case of a Joint Venture, the composition, member details, roles, responsibilities, participation share, and identification of the Lead Member must be specified in the prescribed Annexure submitted with the bid. | 147 | (xiii) | Submission logistics | Submit the prescribed Annexure detailing the JV composition, member roles, responsibilities, participation shares, and Lead Member identification with the bid. | Yes |  |  |  | In case of a Joint Venture, the composition of the JV, including details of all members, their respective roles, responsibilities, and participation share, along with identification of the Lead Member, shall be clearly specified in the prescribed Annexure to be submitted with the bid.
R-561 | The Lead Member of a Joint Venture must be authorized through a valid Power of Attorney executed by the JV members. | 147 | (xiv) | Mandatory | Furnish a valid Power of Attorney from JV members authorizing the Lead Member to represent the JV and act as single point of contact. | Yes |  |  |  | The Lead Member shall be duly authorized by the JV members through a valid Power of Attorney to represent the JV for all purposes of this bid, and shall act as the single point of contact for AIIMS Patna.
R-562 | Sub-contracting or sub-consultancy of any part of the Assignment is prohibited, except for expressly permitted specialist experts such as Biosafety Experts. | 147 | (xv) | Mandatory | Ensure all services are performed directly by the Bidder or its JV members without unauthorized sub-contracting or sub-consultancy. | Yes |  |  |  | Sub-contracting or sub-consultancy of any part of the Assignment shall not be permitted under this Bid. The Services shall be carried out exclusively by the Bidder or, in case of a Joint Venture (JV), by its constituent members. However, this restriction shall not apply to such specialist experts, agencies or services as are expressly permitted elsewhere in this RFP, including, but not limited to, the engagement of Biosafety Experts, subject to the terms and conditions specified herein.
R-563 | A bidder shall submit only one application, and no entity may participate both individually and as a JV member, or in multiple JVs for the same bid. | 147 | (xvi) | Eligibility criteria | Submit only one application and ensure the entity does not participate across multiple bids or Joint Ventures. | Yes |  |  |  | A bidder shall submit only one application under this bid. An entity participating individually shall not be permitted to participate as a member of any Joint Venture, and an entity participating as a member of a Joint Venture shall not be permitted to participate either individually or as a member of any other Joint Venture for the same bid.
R-564 | If bidding as a JV, all members must submit audited financial statements meeting aggregate financial criteria of Rs. 50,00,000/- and provide a CA Certificate certifying combined financial capacity. | 147 | (xviii) | Eligibility criteria | Submit respective financial statements for all JV members and a CA certificate verifying and confirming the combined financial capacity meets the minimum requirement. | Yes |  |  |  | In case the Bidder is a Joint Venture (JV), all members of the JV shall submit their respective financial statements, and the financial capacity of the JV shall be assessed on a combined basis by aggregating the financial credentials of all members. However, the aggregate financial capacity of the JV must meet the minimum financial eligibility criteria prescribed for an individual applicant under this RFP (as applicable i.e. Rs. 50,00,000/-). In addition, the Bidder shall submit a Certificate issued by a Chartered Accountant (CA), certifying, based on verification of the audited financial statements and books of accounts of the respective JV members, the combined financial capacity of the JV and confirming that it satisfies the prescribed minimum financial eligibility criterion.
R-565 | For a Joint Venture to qualify, the Lead Member must independently meet at least 51% and the other member must independently meet at least 30% of the minimum financial eligibility criteria. | 148 | (xix) | Eligibility criteria | Ensure the Lead Member meets at least 51% and the other JV member meets at least 30% of the individual financial eligibility criteria. | Yes |  |  |  | Notwithstanding the above, for the JV to qualify, the Lead Member shall independently meet at least fifty-one percent (51%) of the minimum financial eligibility criteria prescribed for an individual applicant, and the other member shall independently meet at least thirty percent (30%) of such criteria.
R-566 | Bidders, affiliates, associates, sub-consultants, and personnel must not have any actual, potential, or perceived conflict of interest. | 148 | 13.3(i) | Eligibility criteria | Ensure no actual, potential, or perceived conflict of interest exists that could affect fair competition, impartiality, or proper performance. | No — check |  |  |  | The Bidder, including its Affiliates, Associates, Sub- consultants, Key Personnel, Experts, agents and representatives, shall not have any actual, potential or perceived conflict of interest that may affect fair competition, independent professional judgment, impartiality, transparency, or the proper performance of the Assignment.
R-567 | Bidders must disclose in their proposal any actual, potential, or perceived conflict of interest, and promptly disclose any conflict arising during procurement or contract execution. | 150 | 13.3(iv) | Mandatory | Disclose any actual, potential, or perceived conflict of interest in the proposal and report any newly arising conflicts immediately. | Yes |  |  |  | The bidder shall disclose in its proposal any actual, potential, or perceived conflict of interest that may affect its eligibility, qualification, independence, objectivity, or performance under the contract. The bidder shall also promptly disclose any such conflict arising during the procurement process or execution of the Contract.
R-568 | An entity is restricted from participating in more than one proposal in any capacity (including Bidder, Associate, Sub-consultant, Key Personnel provider, or technical collaborator). | 150 | 13.4(i) | Eligibility criteria | Refrain from participating in more than one proposal in any supporting or primary capacity. | Yes |  |  |  | Participation by the same entity in more than one Proposal, whether as Bidder, Associate, Sub-consultant, Key Personnel provider, technical collaborator, or in any other supporting capacity, shall not be permitted.
R-569 | A bidder and any of its affiliates are prohibited from participating in more than one proposal in any capacity. | 150 | 13.5(i) | Eligibility criteria | Ensure the bidder and its affiliates do not submit or participate in multiple proposals. | Yes |  |  |  | If a Bidder and any of its Affiliates participate in more than one Proposal, whether individually, as Sub-consultant, Associate, technical collaborator, or in any other capacity, all such Proposals may be rejected as non-responsive.
R-570 | The selected Consultant and its affiliates/sub-consultants are debarred from participating in subsequent procurement for execution of works, equipment supply, construction, or related services for this assignment. | 151 | 13.6(i) | Mandatory | Comply with restrictions barring participation in downstream works, equipment supply, validation, or construction contracts arising from this consultancy. | Yes |  |  |  | The Consultant, its Affiliates, Associates and Sub-consultants shall not be eligible to participate, directly or indirectly, in any subsequent procurement for execution of works, supply of equipment, supply of systems, construction, installation, validation, certification, testing, operation, maintenance, or any other services arising from or directly related to the Services performed under this Contract, unless expressly permitted by AIIMS Patna in writing and subject to applicable rules.
R-571 | Entities already engaged in execution of works, equipment supply, validation, or maintenance for the assignment are ineligible to participate in this procurement. | 151 | 13.6(ii) | Eligibility criteria | Do not bid if already engaged in project-related works, equipment supply, validation, or maintenance for the same Assignment. | Yes |  |  |  | Similarly, any entity already engaged in execution of works, supply of equipment, validation, certification, operation, maintenance, or other project- related activities for the same Assignment shall not be eligible to participate in this procurement where such participation may result in conflict of interest or unfair competitive advantage.
R-572 | Acceptance of rebates, discounts, commissions, referral fees, or brokerages in connection with procurement advisory is strictly prohibited and any benefit received must be disclosed and accrued to AIIMS Patna. | 151 | 13.7(ii) | Mandatory | Refrain from receiving commissions, rebates, or referral fees, and immediately disclose and surrender any such benefits to AIIMS Patna. | Yes |  |  |  | Any rebate, discount, commission, referral fee, incentive, gratuity, brokerage or similar benefit received or receivable by the Consultant, its Affiliates, Associates, Sub-consultants, Key Personnel, Experts, agents or representatives in connection with such procurement shall be strictly prohibited. If any such benefit is received, it shall be immediately disclosed and shall accrue exclusively to AIIMS Patna, without prejudice to AIIMS Patna’s right to take further action.
R-573 | Bidders have a continuing obligation to disclose in writing any conflict of interest arising or discovered after proposal submission or contract award. | 151 | 13.8(i) | Mandatory | Promptly disclose in writing to AIIMS Patna any conflict of interest that arises or becomes known after proposal submission or contract award. | Yes |  |  |  | If any conflict of interest arises or becomes known after submission of the Proposal or after award of Contract, the Bidder/Consultant shall promptly disclose the same to AIIMS Patna in writing. AIIMS Patna may require the Bidder/Consultant to remove, mitigate or resolve such conflict in a manner acceptable to AIIMS Patna.
R-574 | Bidders must submit an undertaking confirming compliance with the latest applicable version of the Public Procurement (Preference to Make in India) Order, 2017. | 152 | 13.10(ii) | Mandatory | Submit an undertaking confirming compliance with the latest applicable version of the Public Procurement (Preference to Make in India) Order, 2017. | Yes |  |  |  | Bidders must apprise themselves of the latest applicable version of the said Order and shall submit an undertaking confirming compliance with the same.
R-575 | Bidders from countries sharing a land border with India must be registered with DPIIT's Registration Committee and submit an undertaking to that effect with the proposal. | 152 | 13.10(iv) | Eligibility criteria | Ensure registration with DPIIT Registration Committee if from a land-border sharing country (unless exempt), and submit an undertaking to this effect along with the proposal. | Yes |  |  |  | Any Bidder from a country that shares a land border with India, excluding countries to which the Government of India has extended lines of credit or in which the Government of India is engaged in development projects, as listed on the website of the Ministry of External Affairs, hereinafter referred to as “Restricted Countries”, shall be eligible to participate in this Tender only if such Bidder is registered with the Registration Committee constituted by the Department for Promotion of Industry and Internal Trade (DPIIT).The Bidder shall submit an undertaking to this effect along with its Proposal.
R-576 | Consultants are prohibited from sub-contracting any part of the Architectural and Engineering Consultancy Services, except for the specialized Biosafety Expert / Biosafety Consultant for the BSL-3 laboratory component. | 153 | 13.11(i) | Mandatory | Refrain from sub-contracting any portion of the services other than the permitted exception for a specialized Biosafety Expert / Consultant. | Yes |  |  |  | The Bidder/Consultant shall not sub-contract the whole or any part of the Architectural and Engineering Consultancy Services, except to the limited extent expressly permitted under this clause.
R-577 | The A&E Consultant must mandatorily engage or have access to a qualified Biosafety Expert/Consultant and document their credentials and experience w.r.t BSL-3/BSL-4 as part of the bid submission. | 153 | 13.11(ii) Note (a) | Mandatory | Mandatorily engage or have access to a qualified Bio-safety Expert/Consultant and demonstrate and document their credentials and experience with respect to BSL-3/BSL-4 in the bid submission. | Yes |  |  |  | The A&E Consultant shall mandatorily engage or have access to a qualified Bio-safety Expert/Consultant for this project. The Bio-safety Expert may be an in-house employee or an external consultant, provided they possess the requisite qualifications and relevant experience. The Consultant shall clearly demonstrate and document the Bio-safety Expert's credentials and experience as part of the submission w.r.t BSL-3/BSL-4.
R-578 | No scope item or deliverable other than the Biosafety/Biosecurity Containment Expert may be sub-contracted without prior written approval from AIIMS Patna. | 154 | 14.1(i) | Mandatory | Obtain prior written approval from AIIMS Patna before sub-contracting any other discipline, scope item, or deliverable. | Yes |  |  |  | No other discipline, scope item, or deliverable under this RFP (architectural, structural, MEP detailed engineering, project management, construction-stage technical support and design-intent compliance review, etc.) may be sub-contracted, in whole or in part, without the prior written approval of AIIMS Patna.
R-579 | The bidder must disclose at the proposal stage whether the Biosafety Expert is engaged through sub-contracting or on-roll, and submit specified supporting documentation. | 155 | 14.2(vi) | Mandatory | Disclose engagement details of the Biosafety Expert/Consultant and submit items (a) through (j) including name, legal status, contact details, CVs, credentials, consented scope, involvement stages, commitment proof, and letter of consent. | Yes |  |  |  | The Bidder shall clearly disclose in its Proposal whether it proposes to engage a Biosafety Expert / Consultant through sub-contracting or otherwise i.e. on roll etc. Where such Biosafety Expert / Consultant is proposed, the Bidder shall submit the following details along with the Proposal: (a) name and legal status of the Biosafety Expert / Consultant; (b) office address and contact details; (c) the lead biosafety expert and team details (if any); (d) qualifications and professional experience; (e) relevant BSL-3/BSL-4/ABSL-3/ABSL-4 or high-containment laboratory experience; (f) proposed scope of services duly consented by the bio safety expert; (g) stage-wise involvement in the Assignment duly consented by the biosafety expert; (h) CVs of proposed biosafety experts; (i) documentary evidence of availability and commitment; and (j) letter of consent / willingness from the proposed Biosafety Expert / Consultant.
R-580 | The Consultant must ensure active and documented involvement of the Biosafety Expert throughout all biosafety/designing-critical stages of the assignment. | 155 | 14.2(viii) | Mandatory | Ensure active, meaningful, and documented involvement of the approved Biosafety Expert / Consultant across all critical stages. | Yes |  |  |  | The Bidder/Consultant shall ensure active, meaningful and documented involvement of the approved Biosafety Expert / Consultant throughout all biosafety/designing-critical stages of the Assignment.
R-581 | The Consultant must ensure participation of the Biosafety Expert in all biosafety-critical meetings, design reviews, and workshops either physically or online. | 156 | 14.2(xi) | Mandatory | Ensure the Biosafety Expert/Consultant participates in all biosafety-critical meetings, design reviews, and workshops. | Yes |  |  |  | The Consultant shall ensure participation of the approved Biosafety Expert / Consultant in all biosafety-critical meetings, design reviews and workshops. Participation may be through physical presence or video conferencing, as required for assignment.
R-582 | The Consultant must obtain written review comments signed by the Biosafety Expert on all biosafety-critical deliverables and submit them to AIIMS Patna as a Review Comment Sheet / Design Review Note / Compliance Note. | 156 | 14.2(xii)(a) | Mandatory | Submit written review comments signed by the Biosafety Expert with each respective deliverable in the specified note format. | Yes |  |  |  | Such review comments shall be submitted to AIIMS Patna along with the respective deliverable in the form of a Review Comment Sheet / Design Review Note / Compliance Note, along with all deliverable should be signed by the bio-safety expert.
R-583 | The Consultant must submit an Action Taken Report detailing how the Biosafety Expert's comments have been incorporated, along with technical justifications for any omitted comments. | 156 | 14.2(xii)(b) | Mandatory | Submit an Action Taken Report on the incorporation of Biosafety Expert's comments, providing technical justifications if any comments are not incorporated. | Yes |  |  |  | The Consultant shall also submit an Action Taken Report showing how the Biosafety Expert / Consultant’s comments have been incorporated. If any comment is not incorporated, the Consultant shall provide clear technical justification for the same and place the matter before AIIMS Patna for reference.
R-584 | Prior written approval is required from AIIMS Patna for engaging, replacing, removing, substituting, or changing the role or scope of the Biosafety Expert / Consultant. | 157 | 14.2 (xvii) | Mandatory | Obtain prior written approval from AIIMS Patna before engaging, replacing, removing, substituting, or making any material change in role, scope, duration, or responsibility of the Biosafety Expert / Consultant. | Yes |  |  |  | No Biosafety Expert / Consultant shall be engaged, replaced, removed, substituted, or assigned any material change in role, scope, duration, or responsibility without prior written approval of AIIMS Patna.
R-585 | The Consultant must not reduce the approved scope or involvement of the Biosafety Expert / Consultant without prior written approval. | 157 | 14.2 (xvii)(a) | Mandatory | Obtain prior written approval of AIIMS Patna before reducing the approved scope or involvement of the Biosafety Expert / Consultant. | Yes |  |  |  | The Consultant shall not reduce the approved scope or involvement of the Biosafety Expert / Consultant without prior written approval of AIIMS Patna.
R-586 | The Consultant must provide the Biosafety Expert / Consultant timely access to all project information needed for technical review. | 158 | 14.2 (xviii) | Mandatory | Provide timely access to site information, layouts, drawings, design documents, HVAC details, MEP drawings, equipment specifications, commissioning documents, validation documents, meeting minutes, and relevant submissions to the approved Biosafety Expert / Consultant. | Yes |  |  |  | The Consultant shall provide the approved Biosafety Expert / Consultant timely access to all project information necessary for proper technical review, including site information, layouts, drawings, design documents, HVAC details, MEP drawings, equipment specifications, commissioning documents, validation documents, meeting minutes and other relevant submissions.
R-587 | The Biosafety Expert / Consultant must have no conflict of interest, and any actual, potential, or perceived conflict must be disclosed immediately to AIIMS Patna. | 158 | 14.2 (xix) | Mandatory | Ensure the Biosafety Expert / Consultant has no conflict of interest with any project-connected entity, and disclose immediately any actual, potential, or perceived conflict of interest to AIIMS Patna. | Yes |  |  |  | The Biosafety Expert / Consultant shall not have any conflict of interest with any contractor, supplier, vendor, equipment manufacturer, testing agency, validation agency, certification agency, or any other entity connected with the Assignment. Any actual, potential, or perceived conflict of interest shall be immediately disclosed to AIIMS Patna.
R-588 | The Bidder's financial quote must be inclusive of the fee/remuneration of the Biosafety Expert / Consultant. | 158 | 14.2 (xxi) | Mandatory | Include the fee/remuneration of the Biosafety Expert / Consultant in the financial quote without expecting separate or additional payment from AIIMS Patna. | Yes |  |  |  | The Bidder’s financial quote shall be inclusive of the fee/remuneration of the Biosafety Expert / Consultant. AIIMS Patna shall not make any separate or additional payment to such Biosafety Expert / Consultant in any form.
R-589 | At bid submission, the Bidder must name the specific Biosafety Sub-Consultant firm, submit its company profile, references of comparable BSL-3/ABSL-3 projects, and CVs of named individual experts who will deliver the milestones. | 158 | 14.3 (i) | Submission logistics | Submit at bid stage the name of the Biosafety Sub-Consultant firm, company profile, reference list of comparable BSL-3/ABSL-3 projects with verifiable client contact details, and CVs of the specific named individual experts who will personally deliver each milestone. | Yes |  |  |  | The Bidder shall, at the time of bid submission, name the specific Biosafety Sub-Consultant firm proposed to be engaged, along with complete company profile, a reference list of comparable BSL-3/ABSL-3 projects (minimum eligibility references of similar scale, with current and verifiable client contact details), and CVs of the specific named individual experts who will be personally responsible for and personally deliver each milestone not merely CVs of senior personnel of the firm who will not be actively assigned to this project.
R-590 | The Bidder must disclose the internal commercial/contractual arrangement with the Biosafety Sub-Consultant in a separate signed annexure; pure per-sitting/per-diem structures without milestone obligations will be rejected. | 159 | 14.3 (ii) | Submission logistics | Submit a separate signed annexure disclosing the internal commercial/contractual arrangement proposed with the Biosafety Sub-Consultant, ensuring it is structured on milestone deliverables rather than a pure per-sitting/per-diem basis. | Yes |  |  |  | The Bidder shall additionally disclose, in a separate signed annexure, the exact internal commercial/contractual arrangement proposed between the Bidder (or its lead engineering partner) and the Biosafety Sub-Consultant — including whether the Sub-Consultant is engaged on a lump-sum milestone basis or on a per-sitting/per-diem/per-visit basis (no full disclosure of amount payable is required to be disclosed). Engagement of the Biosafety Sub-Consultant on a pure per-sitting/per-diem basis, without milestone-linked deliverable obligations binding on the Sub-Consultant, shall not be accepted, and bids structured this way shall be treated as non-responsive, since such an arrangement creates a financial incentive to minimize the Sub-Consultant's actual sittings/involvement while retaining their name for bid qualification purposes.
R-591 | The named Biosafety Sub-Consultant firm and individual experts must be deployed throughout the project, attend the kick-off workshop and site-visits, and sign deliverables personally. | 159 | 14.4 (i) | Mandatory | Deploy the named entity and experts throughout the project, ensure named experts personally attend kick-off and site-visits, and ensure they personally sign all design briefs, layout sketches, Review Comment Forms, and SOPs. | Yes |  |  |  | The Biosafety Sub-Consultant named at bid stage shall be the entity and the named individual experts actually deployed throughout the project. The named individual experts shall personally attend the kick-off workshop and all site-visits, and shall personally sign all design briefs, layout sketches, Review Comment Forms, and SOPs issued under their name.
R-592 | Substitution of the named Sub-Consultant firm or individual expert requires prior approval, equal or better qualifications, and deployment within 15 calendar days. | 159 | 14.4 (ii) | Mandatory | Obtain prior written approval from AIIMS Patna for any substitution, ensure replacement has equal or exceeding qualifications and experience, and deploy the approved replacement within 15 calendar days of approval. | Yes |  |  |  | Substitution of the named firm, or of any named individual expert, shall require prior written approval of AIIMS Patna and shall be permitted only where the replacement possesses qualifications and experience equal to or exceeding those of the originally named expert. Any approved replacement must be deployed and operational within fifteen (15) calendar days of AIIMS Patna's approval; this transition period shall not, by itself, justify any extension of the milestone deadlines.
R-593 | The lead engineering firm must not restrict, filter, or delay direct communication between AIIMS Patna and the Biosafety Sub-Consultant. | 160 | 14.5 (iv) | Mandatory | Maintain unrestricted direct access and communication between AIIMS Patna and the Biosafety Sub-Consultant. | Yes |  |  |  | The Bidder/lead engineering firm shall not restrict, filter, delay, or otherwise interpose itself between AIIMS Patna and the Biosafety Sub-Consultant in a manner that limits AIIMS Patna's direct access as described above.
R-594 | The Biosafety Sub-Consultant must participate in all project coordination meetings at least remotely/virtually at no extra cost. | 160 | 14.5 (v) | Mandatory | Ensure the Biosafety Sub-Consultant participates (at minimum remotely/virtually) in all project coordination meetings without charging additional fees. | Yes |  |  |  | The Biosafety Sub-Consultant's participation in all project-related coordination meetings (at minimum, remotely/virtually) is mandatory and shall not be optional or chargeable as an extra, having already been priced as per the assignment.
R-595 | A minimum of two physical site-visits by the Biosafety Sub-Consultant are mandatory. | 160 | 14.6 (i) | Mandatory | Arrange and conduct a minimum of two physical site visits (one before concept approval and the second considering AIIMS Patna certification requirement and readiness). | Yes |  |  |  | Physical site-visits - minimum two (2): (a) Visit 1: Before concept approval, to verify existing conditions and establish the containment strategy and biosafety design criteria. (b) Visit 2: As suggest by Bio-safety Expert considering AIIMS Patna certification requirement and readiness. (c) These are floor requirements; the Bidder may propose additional physical visits, but shall not propose fewer than two.
R-596 | For each deliverable, the Biosafety Sub-Consultant's named experts must conduct at least one review meeting in addition to submitting the written Review Comment Form. | 160 | 14.7 (i) | Mandatory | Ensure the Biosafety Sub-Consultant's named experts conduct at least one review meeting with AIIMS Patna and the lead engineering firm and issue a written Review Comment Form before each deliverable is completed. | Yes |  |  |  | For each deliverable listed herein, the Biosafety Sub-Consultant's named experts shall conduct at minimum one (1) or as required for that deliverables a review meeting with AIIMS Patna and the lead engineering firm, in addition to the written Review Comment Form, prior to that deliverables being marked complete.
R-597 | The Bidder must submit with its technical proposal a calendar with proposed dates/windows for the two physical visits and review meetings. | 160 | 14.7 (iii) | Submission logistics | Submit a calendar with proposed dates/windows for the two mandatory physical visits and review meetings as part of the technical proposal. | Yes |  |  |  | The Bidder shall submit, with its technical proposal, a calendar indicating proposed dates/windows for the two mandatory physical visits and the review meetings.
R-598 | Minutes of kick-off workshop, site visits, and milestone review meetings must be prepared by the consultant within three working days and circulated to all parties. | 160 | 14.8 (i) | Mandatory | Prepare and circulate minutes within three working days of every kick-off workshop, site-visit, and milestone review meeting to AIIMS Patna, the lead engineering firm, and the Biosafety Sub-Consultant. | Yes |  |  |  | Minutes of every kick-off workshop, site-visit, and milestone review meeting shall be prepared within three (3) working days of the meeting and circulated to AIIMS Patna, the lead engineering firm, and the Biosafety Sub-Consultant. The minutes should be prepared by the consultant.
R-599 | Minutes must be co-signed by the attending named individual expert(s) of the Biosafety Sub-Consultant. | 160 | 14.8 (ii) | Mandatory | Obtain co-signatures from the attending named individual expert(s) of the Biosafety Sub-Consultant on meeting minutes. | Yes |  |  |  | Minutes shall be co-signed by the named individual expert(s) of the Biosafety Sub-Consultant who attended, and not merely by a representative of the lead engineering/architectural firm on the Sub-Consultant's behalf.
R-600 | Milestone payments require deliverable submission, holding and minuting of the review meeting, and co-signature of minutes by the Biosafety Sub-Consultant's named expert. | 161 | 14.9 (i) | Mandatory | Submit the relevant deliverable, conduct and minute the review meeting, and ensure minutes are co-signed by the Biosafety Sub-Consultant's named expert before seeking milestone payment release. | Yes |  |  |  | No milestone payment shall be released unless, for that milestone: (i) the relevant deliverable has been submitted, (ii) the review meeting has been held and minuted, and (iii) the minutes have been co-signed by the Biosafety Sub-Consultant's named expert under Clause 14.22(ii).
R-601 | The Bidder must not attribute deliverables produced by the lead firm or junior personnel to the named Biosafety Sub-Consultant firm. | 161 | 14.13 | Mandatory | Ensure that the named Biosafety Sub-Consultant firm and experts genuinely produce and review the biosafety deliverables rather than rubber-stamping work produced by the lead firm or junior personnel. | Yes |  |  |  | The Bidder shall not represent, in its bid or at any subsequent stage that the named Biosafety Sub-Consultant firm is responsible for deliverables that are, in substance, produced by the lead engineering/architectural firm or by junior/unnamed personnel of the Sub-Consultant firm.
R-602 | No discipline other than Biosafety Expert/Specialist may be sub-contracted without prior written approval, and the prime Consultant remains fully responsible. | 162 | 14.15(i) | Mandatory | Ensure no other discipline is sub-contracted without prior written approval, and take full responsibility for all services, integration, schedule, quality, and acts/omissions of the Biosafety Expert. | Yes |  |  |  | The foregoing clauses are the sole governing sub-consulting provisions. No other discipline may be sub-contracted without prior written approval. The prime Consultant remains fully responsible for all services, integration, schedule, quality and acts/omissions of the Biosafety Expert.
R-603 | The Consultant, its JV members, affiliates, sub-consultants, and Key Personnel are prohibited from participating as contractor, supplier, or independent validation agency in subsequent procurement arising from their design/specifications without express AIIMS Patna permission. | 162 | 14.15(iii) | Mandatory | Refrain from participating as a contractor, supplier, or independent validation agency in any subsequent procurement arising from own design/specifications unless expressly permitted by AIIMS Patna after conflict-of-interest review. | Yes |  |  |  | The Consultant, its JV members, affiliates, sub-consultants and Key Personnel shall not participate as contractor, supplier or independent validation agency in a subsequent procurement arising from their own design/specifications unless AIIMS Patna expressly permits the role after a documented conflict-of-interest review.
R-604 | Bids must be submitted online through CPPP under a Two Bid system (Part I: Techno commercial bid & Part II: Financial Bid); manual bids will not be accepted. | 164 | 15.1 | Submission logistics | Submit electronic online bids via CPPP under the Two Bid system; do not submit manual bids. | Yes |  |  |  | The Executive Director, AIIMS Patna, through the Dean Research, AIIMS Patna, invites electronic online bids ( e-Tender) through Central Public Procurement Portal (CPPP) at https://eprocure.gov.in/eprocure/app and website of AIIMS, Patna at https://aiimspatna.edu.in/tender/ (for ref. only) under Two Bid system (Part I: Techno commercial bid & Part II: Financial Bid) from reputed, eligible and qualified Architectural & Engineering Consultancy firms/service providers for providing Architectural & Engineering Consultancy Services as defined herein for establishment of the BSL-3 Laboratory at AIIMS Patna. Manual bids shall not be accepted.
R-605 | All proposals, correspondences, and documents must be in English, or accompanied by an authenticated English translation if in another language. | 164 | 15.2(i) | Mandatory | Submit all bid documents and communications in English, and provide authenticated English translations for any documents in another language. | Yes |  |  |  | The Proposal/Bid submitted by the Bidder and all subsequent correspondences, communications, clarifications, documents, reports, and submissions exchanged between the Bidder and AIIMS Patna shall be written in English (the “Bid Language”). Any printed literature, supporting document, technical publication, certificate, brochure, or document furnished by the Bidder in any language other than English shall be accompanied by an authenticated English translation. For the purpose of interpretation, evaluation, and contract administration, the English translation shall prevail.
R-606 | Bidders must submit a duly signed Bid Security Declaration as per the prescribed Annexure format. | 164 | 15.2(iii) Table-8 | Mandatory | Submit a duly signed 'Bid Security Declaration' as per the prescribed Annexure format in Table-8. | Yes |  |  |  | The bidder shall submit a duly signed “Bid Security Declaration” as per the format prescribed Annexure.
R-607 | Bid offer validity must be 270 days from the date of bid opening. | 165 | Table-9 b) | Mandatory | Maintain bid validity for 270 days from the date of bid opening. | Yes |  |  |  | Bid offer validity (days from the date of bid opening) 270 days
R-608 | Joint Ventures must be duly registered legal entities or constituted through a registered JV Agreement under applicable law, with documentary evidence submitted; informal MoUs or unregistered agreements are not accepted. | 165 | Table-9 c) Note | Eligibility criteria | Submit documentary evidence of registration of the Joint Venture or registered Joint Venture Agreement under applicable law along with the RFP. | Yes |  |  |  | Joint Ventures formed through an unregistered agreement, Memorandum of Understanding (MoU), letter of intent or any other informal arrangement shall not be accepted. Only duly registered Joint Ventures, constituted as a legal entity or a Joint Venture duly constituted through a registered Joint Venture Agreement under applicable law, shall be eligible to apply. Documentary evidence of such registration shall be submitted along with the RFP.
R-609 | Joint Ventures are limited to a maximum of 2 (two) members. | 165 | Table-9 c) Essential JV parameters | Eligibility criteria | Ensure the Joint Venture does not exceed two members. | Yes |  |  |  | Maximum No of JV Members: 2 (Two)
R-610 | Written queries for the Pre-Bid Conference must be submitted by email at least 48 hours prior to the scheduled date and time of the Pre-Bid Conference. | 166 | Table-9 e) | Submission logistics | Submit pre-bid queries via email to bsl3@aiimspatna.org at least 48 hours before the scheduled Pre-Bid Conference date and time. | Yes |  |  |  | Queries must be submitted by email at least 48 (forty-eight) hours prior to the scheduled date and time of the Pre-Bid Conference. (Email: bsl3@aiimspatna.org)
R-611 | Written requests to attend the Online Pre-Bid Conference must be sent via email at least 24 hours prior to the scheduled meeting. | 166 | Table-9 e) | Submission logistics | Submit participation requests for the online pre-bid conference to bsl3@aiimspatna.org at least 24 hours prior to the scheduled time. | Yes |  |  |  | Bidders shall submit participation requests to email ID bsl3@aiimspatna.org at least 24 (Twenty four) hours prior to the scheduled date and time of the meeting.
R-612 | Bidders intending to attend the offline Pre-Bid Conference must submit a request in writing via email at least 48 hours prior to the scheduled meeting. | 166 | Table-9 e) | Submission logistics | Send an offline Pre-Bid Conference attendance request by email to bsl3@aiimspatna.org at least 48 hours before the meeting. | Yes |  |  |  | Bidders intending to participate in the offline Pre-Bid Conference shall submit their request for attending the pre-bid conference in writing through email at least 48 (forty-eight) hours prior to the scheduled date and time of the meeting. (Email: bsl3@aiimspatna.org)
R-613 | RFP must be addressed to The Executive Director, AIIMS Patna, through The Dean Research, AIIMS Patna. | 166 | Table-9 f) | Submission logistics | Address the RFP submission to The Executive Director, AIIMS Patna, through The Dean Research, AIIMS Patna. | Yes |  |  |  | The Executive Director, AIIMS Patna, through The Dean Research, AIIMS Patna
R-614 | Bidders must submit requests for online participation at least 24 hours prior and requests for physical/offline participation at least 48 hours prior to the Pre-Bid Conference. | 168 | 16.1 (v) | Submission logistics | Submit online participation requests at least 24 hours in advance and physical participation requests at least 48 hours in advance of the Pre-Bid Conference. | Yes |  |  |  | Requests for online participation shall be submitted at least 24 (twenty-four) hours before the scheduled date and time of the Pre-Bid Conference. Requests for physical/offline participation shall be submitted at least 48 (forty-eight) hours before the scheduled date and time of the Pre-Bid Conference.
R-615 | Written queries for the Pre-Bid Conference must be sent via email to bsl3@aiimspatna.org at least 48 hours prior to the conference. | 168 | 16.1 (vi) | Submission logistics | Email written pre-bid queries to bsl3@aiimspatna.org at least 48 hours before the scheduled Pre-Bid Conference. | Yes |  |  |  | Written queries for the Pre-Bid Conference shall be submitted by email to bsl3@aiimspatna.org at least 48 (forty-eight) hours before the scheduled date and time of the Pre-Bid Conference.
R-616 | Representatives attending the Pre-Bid Conference must carry and submit a valid authorization letter issued by the bidder and a valid photo ID proof. | 168 | 16.1 (vii) | Mandatory | Nominate authorized representatives who must carry/submit a valid authorization letter from the bidder and photo identity proof. | Yes |  |  |  | Each Bidder shall nominate authorized representative(s) to attend the Pre-Bid Conference. The representative(s) shall carry / submit a valid authorization letter issued by the Bidder and a valid photo identity proof.
R-617 | Proposals must be submitted online exclusively through CPPP on or before the Proposal Submission end date. | 169 | 16.1 (xiii) | Submission logistics | Submit the proposal online via CPPP prior to the prescribed proposal submission end date. | Yes |  |  |  | Proposals shall be submitted online only through CPPP on or before the Proposal Submission end date as per critical dates.
R-618 | Prospective bidders seeking clarification on any provision of the RFP must submit queries exclusively through CPPP within the timeline in the Critical Date Sheet. | 169 | 16.2 (i) | Submission logistics | Submit formal clarification queries solely through CPPP within the timeline prescribed in the Critical Date Sheet. | Yes |  |  |  | Any prospective Bidder requiring clarification regarding any provision of this RFP, including technical, commercial, contractual, procedural, biosafety, engineering, validation, certification or submission-related requirements, shall submit its queries only through the Central Public Procurement Portal (CPPP) within the timeline specified in Critical Date Sheet published on the Portal.
R-619 | Bidders are required to regularly monitor CPPP and the AIIMS Patna website for any corrigenda, addenda, amendments, or other updates. | 170 | 16.3 (iii) | Mandatory | Monitor CPPP and the AIIMS Patna website regularly to stay updated on tender corrigenda, amendments, and clarifications. | Yes |  |  |  | Bidders shall regularly monitor CPPP and AIIMS Patna website for corrigenda, addenda, amendments, clarifications, extensions of date, revised documents, or any other updates.
R-620 | Bidders must thoroughly review all sections of the RFP and submit their bids in strict compliance with all requirements and corrigenda. | 171 | 17.1 | Mandatory | Carefully review the entire RFP package and submit the bid strictly complying with all stated terms, criteria, and forms. | Yes |  |  |  | Bidders shall carefully examine the complete RFP, including the RFP Data Sheet, eligibility and qualification criteria, scope of services, evaluation criteria, contract conditions, forms, annexures and all subsequent corrigenda or clarifications, and shall prepare and submit their Bids in strict compliance therewith.
R-621 | The bidder must bear all costs related to the preparation, submission, presentation, clarification, and processing of its proposal. | 171 | 17.4 | Mandatory | Bear all financial costs associated with preparing and submitting the proposal. | Yes |  |  |  | The Bidder shall bear all costs relating to preparation, submission, presentation, clarification and processing of its Proposal.
R-622 | Bidders must submit only one proposal in two separate covers (Techno-Commercial Proposal and Financial Proposal); alternative, conditional, or multiple proposals are prohibited. | 171 | 17.5 | Mandatory | Submit a single proposal divided into two separate covers without offering alternative, conditional, or multiple proposals. | Yes |  |  |  | Each Bidder shall submit only one Proposal in two separate covers: Techno-Commercial Proposal and Financial Proposal. Alternative, conditional or multiple proposals shall not be permitted.
R-623 | The Techno-Commercial Proposal must include all requisite documents and credentials and must not contain any financial information. | 171 | 17.5 | Mandatory | Include all required undertakings, qualifications, methodology, and personnel details in the Techno-Commercial cover while strictly omitting financial information. | Yes |  |  |  | The Techno-Commercial Proposal shall contain all required documents, declarations, undertakings, credentials, methodology, work plan, personnel details and supporting information, and shall not contain financial information.
R-624 | The proposal must remain valid for a minimum of 270 days from the bid submission end date. | 171 | 17.6 | Mandatory | Maintain proposal validity for at least 270 days following the bid submission deadline. | Yes |  |  |  | The Proposal shall remain valid for 270 days from the bid submission end date.
R-625 | Bids must be submitted solely through CPPP within the specified deadline; manual, physical, email, or offline submissions will not be accepted. | 171 | 17.7 | Submission logistics | Submit the bid online via CPPP and refrain from submitting physical, manual, or email bids. | Yes |  |  |  | Submission shall be made only through CPPP within the prescribed deadline. No manual, physical, email or offline submission shall be accepted.
R-626 | Bidders are responsible for CPPP portal registration, possessing a valid Digital Signature Certificate (DSC), uploading documents, and ensuring timely submission. | 171 | 17.7 | Submission logistics | Register on CPPP, obtain a valid Digital Signature Certificate, and upload all proposal documents within the deadline. | Yes |  |  |  | The Bidder shall be responsible for CPPP registration, valid Digital Signature Certificate, uploading of documents and timely submission.
R-627 | Bidder must comply with CPPP portal rules, procedures, and technical requirements, including registration and using a valid Digital Signature Certificate (DSC). | 172 | 17.9 | Mandatory | Register on CPPP and use a valid Digital Signature Certificate (DSC) while complying with all applicable portal rules and procedures. | Yes |  |  |  | The Bidder shall comply with the applicable portal rules, procedures and technical requirements, including registration and use of valid Digital Signature Certificate (DSC).
R-628 | All uploaded documents must be clear, legible, complete, and digitally signed by the authorized signatory. | 172 | 17.10 | Mandatory | Digitally sign all uploaded bid documents using a valid DSC and ensure they are clear, legible, complete, and uncorrupted. | Yes |  |  |  | All uploaded documents shall be clear, legible, complete and digitally signed by the authorized signatory.
R-629 | Bidders are prohibited from altering, tampering with, deleting, or modifying any RFP form, BOQ, format, formula, or template. | 172 | 17.11 | Mandatory | Enter required information only without altering, deleting, modifying, or tampering with RFP forms, BOQ, formulas, or templates. | Yes |  |  |  | The Bidder shall not alter, tamper with, delete or modify any RFP form, format, BOQ, formula or template except for entering required information.
R-630 | Bidders must submit a Bid Security Declaration in the prescribed format in lieu of EMD. | 172 | 17.14 | Mandatory | Submit a bid security declaration in the prescribed format as part of the proposal in lieu of EMD. | Yes |  |  |  | The Bidder shall submit a bid security declaration in the prescribed format as part of its Proposal in lieu of No Earnest Money Deposit (EMD).
R-631 | The Bid Security Declaration must remain valid for the entire Proposal Validity Period and any agreed extensions. | 173 | 17.14 | Mandatory | Maintain validity of the Bid Security Declaration across the full Proposal Validity Period and any extended period. | Yes |  |  |  | The Bid Security Declaration shall remain valid for the entire Proposal Validity Period and any extension thereof agreed to by the Bidder.
R-632 | No relaxation in prior turnover, prior experience, eligibility requirements, or purchase preference is admissible to MSMEs or Startups. | 173 | 17.15 | Eligibility criteria | Comply with standard turnover, experience, and eligibility requirements without seeking MSME or Startup exemptions or purchase preferences. | Yes |  |  |  | In view of the specialized and public health-critical nature of the Assignment, no relaxation in prior turnover, prior experience, or eligibility requirements shall be available to MSMEs or Startups, in accordance with Department of Expenditure, Government of India Office Memorandum No. F.20/2/2014-PPD(Pt.) dated 20 September 2016. Accordingly, no purchase preference or any other preferential treatment shall be admissible to MSMEs or Startups.
R-633 | Bidders must comply with Government of India orders regarding land-border sharing countries and reciprocity, submitting requisite declarations and undertakings. | 173 | 17.15 | Mandatory | Submit prescribed declarations, undertakings, and supporting documents proving compliance with land-border restrictions and reciprocity policies. | Yes |  |  |  | Participation in this RFP shall be subject to the applicable policies, orders, and restrictions issued by the Government of India from time to time, including those relating to entities from countries sharing land borders with India and reciprocity requirements. Bidders shall ensure compliance with all such requirements and shall submit the requisite declarations, undertakings, and supporting documents as prescribed under this RFP.
R-634 | Bidder must immediately inform AIIMS Patna in writing of any material changes affecting ownership, eligibility, financial/technical capacity, key personnel, or debarment status. | 173 | 17.15 | Mandatory | Notify AIIMS Patna immediately in writing of any material changes in information, capacity, personnel, or legal/eligibility status. | Yes |  |  |  | The Bidder shall immediately inform AIIMS Patna in writing of any material change in the information, documents, declarations or undertakings submitted as part of its Proposal, including any substantial change in ownership, legal status, eligibility, financial capacity, technical capacity, key personnel, conflict of interest, blacklisting / debarment status, or performance capability.
R-635 | Bidder must submit supporting documents and evidence to verify declarations and commitments made during the EOI stage. | 174 | 17.17 | Mandatory | Furnish supporting evidence and documents required by AIIMS Patna to verify previous EOI submissions and commitments. | Yes |  |  |  | The Bidder shall submit such supporting documents and evidence as may be required by AIIMS Patna to verify the declarations and commitments made under the EOI.
R-636 | Bids must be submitted electronically online via the Central Public Procurement Portal (CPPP) within the prescribed deadline. | 174 | 17.18 | Submission logistics | Submit bids online via CPPP at https://eprocure.gov.in/eprocure/app prior to the closing date and time; do not submit manual/physical bids. | Yes |  |  |  | Bids shall be submitted online only through CPPP within the date and time specified in the RFP Data Sheet / Critical Date Sheet published on CPPP.
R-637 | Manual or physical bid submissions by post, courier, email, fax, or hand delivery are strictly prohibited. | 174 | 17.18 | Submission logistics | Avoid manual, physical, post, courier, hand delivery, email, or fax submission of bids. | Yes |  |  |  | Manual bids, physical bids, bids submitted by post, courier, hand delivery, email, fax, or through any mode other than CPPP shall not be accepted and shall be treated as non-responsive.
R-638 | Bids must be submitted under a Two Bid / Two Cover system: Cover-I (Techno-Commercial Bid) and Cover-II (Financial Bid). | 174 | 17.19 | Submission logistics | Submit proposal in two covers: Cover-I containing techno-commercial details and Cover-II containing the financial bid. | Yes |  |  |  | The Bid shall be submitted under the Two Bid / Two Cover system as follows: (a) Cover-I: Techno-Commercial Bid / Technical Bid; and (b) Cover-II: Financial Bid.
R-639 | The Financial Bid must not be uploaded in Cover-I; any financial indication in Cover-I will cause bid rejection. | 175 | 17.19 | Submission logistics | Ensure Cover-I contains no price, fee, financial quote, percentage, lump sum, commercial offer, or financial condition. | Yes |  |  |  | The Financial Bid shall not be uploaded in Cover-I. Any indication of price, fee, financial quote, percentage, lump sum amount, commercial offer, or financial condition in Cover-I shall render the Bid liable for rejection as non-responsive.
R-640 | The bidder must not modify, alter, delete, overwrite, manipulate, or tamper with the BOQ format. | 175 | 17.19 | Mandatory | Complete the financial bid format / BOQ format without modifying, altering, overwriting, manipulating, or tampering with it. | Yes |  |  |  | The Bidder shall not modify, alter, delete, overwrite, manipulate, or tamper with the financial bid format / BOQ format.
R-641 | Cover-I (Techno-Commercial Bid) must include all required eligibility, qualification, legal, financial, technical, and compliance documents. | 176 | 17.21 | Mandatory | Upload covering letter, bidder legal status, PoA/Board Resolution, Bid Security Declaration, eligibility/experience credentials, financial capability documents (with UDIN), key personnel CVs, technical proposal, DBT-ICMR guideline compliance undertaking, JV docs (if applicable), and all filled annexures in Cover-I. | Yes |  |  |  | The Techno-Commercial Bid shall include, as applicable, the following: (a) Bid covering letter in the prescribed format; (b) Bidder information and legal status documents; (c) Power of Attorney / Board Resolution / authorization in favour of the authorized signatory; (d) Bid Security Declaration in the prescribed format; (e) Eligibility and qualification documents; (f) Declarations relating to blacklisting, debarment, conflict of interest, code of integrity, land-border restrictions, reciprocity restrictions, and other applicable Government of India requirements; (g) Experience credentials, completed assignment details, client certificates, work orders, completion certificates, performance certificates, and supporting documents; (h) Financial capability documents, including turnover, audited financial documents or CA certificates with UDIN No, certificates, declarations, and supporting evidence as prescribed in this RFP; (i) Key personnel details, curriculum vitae, qualifications, professional registrations, deployment commitment, and supporting documents; (j) Technical proposal, project understanding, design approach, methodology, work plan, staffing schedule, quality assurance approach, risk management approach, and coordination plan; (k) Undertaking regarding compliance with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024, as amended from time to time, and other applicable statutory, regulatory, biosafety, biosecurity, engineering, environmental, and institutional requirements; (l) Joint Venture documents, where applicable, including JV agreement, registration documents, participation share, responsibility matrix, authorization of Lead Member, and joint and several liability undertaking; (m) Duly filled annexures, forms, schedules, declarations, checklists, and undertakings prescribed in this RFP; and (n) Any other document required under this RFP.
R-642 | All uploaded documents must be complete, legible, properly scanned, duly filled, signed, stamped, and uploaded in the designated CPPP cover. | 176 | 17.21 | Submission logistics | Ensure all documents are complete, legible, scanned properly, filled, signed, stamped, and uploaded to the proper cover. | Yes |  |  |  | The Bidder shall ensure that all documents are complete, legible, properly scanned, duly filled, signed, stamped, and uploaded in the appropriate cover on CPPP.
R-643 | Information must be submitted strictly in the prescribed formats; generic promotional materials/brochures cannot substitute required documents. | 176 | 17.21 | Mandatory | Submit all information strictly using prescribed formats and avoid submitting general brochures or catalogues in place of required formats. | Yes |  |  |  | Wherever a format has been prescribed in this RFP, the Bidder shall submit the information strictly in the prescribed format. Non-submission of a prescribed format, material deviation from the prescribed format, or submission of incomplete information may render the Bid liable for rejection.
R-644 | The Financial Bid must be submitted strictly in Cover-II using the prescribed financial bid format / BOQ format. | 176 | 17.22 | Submission logistics | Submit the financial bid exclusively in Cover-II using the prescribed format/BOQ. | Yes |  |  |  | The Financial Bid shall be submitted only in Cover-II and strictly in the prescribed financial bid format / BOQ format.
R-645 | The Financial Bid must be unconditional and quote only in Indian Rupees (INR). | 176 | 17.22 | Mandatory | Provide an unconditional financial quote solely in Indian Rupees (INR) without alternative or qualified quotes. | Yes |  |  |  | The Financial Bid shall be unconditional. Conditional quotes, alternative quotes, multiple quotes, incomplete quotes, qualified quotes, or quotes not submitted in the prescribed format shall be liable for rejection.
R-646 | Bidder must quote strictly in Indian Rupees. | 176 | 17.22 | Mandatory | State all pricing and fee quotes in Indian Rupees (INR). | Yes |  |  |  | The Bidder shall quote in Indian Rupees only.
R-647 | Bidder must ensure correct tax classification, GST rate, and statutory treatment in the financial proposal. | 176 | 17.22 | Mandatory | Apply and verify correct tax classification and applicable GST rates within the financial bid. | Yes |  |  |  | The Bidder shall ensure correct tax classification, GST rate, and applicable statutory treatment.
R-648 | All Bid documents must be signed or digitally signed by the authorized signatory of the Bidder. | 177 | 17.23(i) | Submission logistics | Sign or digitally sign all Bid documents by the authorized signatory. | Yes |  |  |  | All Bid documents shall be signed or digitally signed by the authorized signatory of the Bidder.
R-649 | The person signing or digitally signing the bid must be authorized to bind the Bidder, and documentary evidence of authorization must be uploaded with the Techno-Commercial Bid. | 177 | 17.23(ii) | Submission logistics | Upload documentary evidence of authorization (such as Power of Attorney, Board Resolution, partnership authorization, LLP authorization, or equivalent) with the Techno-Commercial Bid. | Yes |  |  |  | The person signing or digitally signing the bid shall be duly authorized to bind the Bidder. Documentary evidence of such authorization, including Power of Attorney, Board Resolution, partnership authorization, LLP authorization, or equivalent document, as applicable, shall be uploaded with the Techno- Commercial Bid.
R-650 | In the case of a Joint Venture, the Bid must be signed or digitally signed by the authorized representative of the Lead Member, supported by a valid Power of Attorney or equivalent authorization from all JV members. | 177 | 17.23(iii) | Submission logistics | Ensure the Joint Venture bid is signed or digitally signed by the authorized representative of the Lead Member, and upload a valid Power of Attorney or equivalent authorization executed by all JV members. | Yes |  |  |  | In case of a Joint Venture, the Bid shall be signed or digitally signed by the authorized representative of the Lead Member, duly authorized by all JV members. Such authorization shall be supported by a valid Power of Attorney or equivalent authorization executed by all JV members.
R-651 | Documents must be uploaded in PDF or other format permitted by CPPP. | 177 | 17.24(i) | Submission logistics | Upload bid documents in PDF or other CPPP-permitted format. | Yes |  |  |  | Documents shall be uploaded in PDF or such other format as may be permitted by CPPP.
R-652 | Scanned documents must be clear, readable, complete, properly oriented, and capable of evaluation. | 177 | 17.24(ii) | Submission logistics | Ensure all scanned documents are clear, readable, complete, properly oriented, and evaluable. | Yes |  |  |  | Scanned documents shall be clear, readable, complete, properly oriented, and capable of evaluation.
R-653 | Uploaded PDF documents must not be password protected unless specifically permitted by AIIMS Patna. | 177 | 17.24(iv) | Submission logistics | Do not password-protect uploaded PDF documents unless specifically permitted. | Yes |  |  |  | Uploaded PDF documents shall not be password protected unless specifically permitted by AIIMS Patna.
R-654 | The Bidder must verify all uploaded documents before final submission. | 177 | 17.24(v) | Submission logistics | Verify all uploaded documents prior to final submission on CPPP. | Yes |  |  |  | The Bidder shall verify all uploaded documents before final submission.
R-655 | Bids must be submitted on CPPP no later than the bid submission closing date and time specified in the RFP Data Sheet / Critical Date Sheet. | 177 | 17.25(i) | Submission logistics | Submit bids on CPPP within the designated deadline specified in the RFP Data Sheet / Critical Date Sheet. | Yes |  |  |  | Bids shall be submitted on CPPP not later than the bid submission closing date and time specified in the RFP Data Sheet / Critical Date Sheet published on CPPP.
R-656 | Bids must remain valid for 270 days from the date of bid opening or as specified in the RFP Data Sheet. | 178 | 17.26(i) | Submission logistics | Maintain bid validity for a minimum of 270 days from the opening date. | Yes |  |  |  | The Bid shall remain valid for a period of 270 days from the date of opening of the Bid or such other date as may be specified in the RFP Data Sheet.
R-657 | A Bidder agreeing to extend bid validity is prohibited from modifying the bid, altering price or technical proposal, substituting key personnel without permission, or adding conditions. | 178 | 17.26(v) | Mandatory | Refrain from modifying the bid, changing quoted prices, altering technical proposals, substituting key personnel, or imposing additional conditions when extending bid validity. | Yes |  |  |  | A Bidder agreeing to extend the validity shall not be permitted to modify its Bid, change its quoted price, alter its technical proposal, substitute key personnel except as expressly permitted by AIIMS Patna, or impose any additional condition.
R-658 | The Bidder must demonstrate in its Techno-Commercial Bid the capability to provide comprehensive Architectural & Engineering Consultancy Services for the BSL-3 Laboratory. | 178 | 17.27(ii) | Mandatory | Demonstrate capability across all specified scopes of work including retrofitting assessment, biosafety risk assessment, containment zoning, MEP design, BIM, CFD analysis, DPR, BOQ, and validation support in the Techno-Commercial Bid. | Yes |  |  |  | The Bidder shall demonstrate, through its Techno-Commercial Bid, its capability to provide comprehensive Architectural & Engineering Consultancy Services for establishment of the BSL-3 Laboratory at AIIMS Patna, including but not limited to retrofitting assessment, site verification, biosafety risk assessment, laboratory workflow planning, containment zoning, architectural planning, engineering design, MEP design, utility planning, BIM, CFD analysis, automation and monitoring systems, DPR, detailed estimates, BOQ, tender assistance, construction-stage technical support, commissioning, validation, biosafety validation, certification support, and as-built documentation.
R-659 | The proposal must align with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024, and applicable statutory and biosafety requirements. | 178 | 17.27(iii) | Mandatory | Ensure the proposal aligns with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024, and all applicable statutory, regulatory, biosafety, biosecurity, engineering, and environmental requirements. | Yes |  |  |  | The Bidder shall ensure that the proposal is aligned with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024, as amended from time to time, and all other applicable statutory, regulatory, biosafety, biosecurity, engineering, environmental, and institutional requirements.
R-660 | The Bidder must disclose any assumptions, exclusions, dependencies, or confirmations required from AIIMS Patna. | 179 | 17.27(vi) | Mandatory | Clearly state all assumptions, exclusions, dependencies, or required confirmations from AIIMS Patna in the bid. | Yes |  |  |  | The Bidder shall clearly disclose any assumptions, exclusions, dependencies, or confirmations required from AIIMS Patna.
R-661 | Information and details provided by AIIMS Patna must be used solely for preparing and submitting the Bid. | 179 | 17.28(i) | Mandatory | Use all drawings, layouts, data, site info, and project details exclusively for bid preparation and submission. | Yes |  |  |  | All information, drawings, layouts, data, institutional inputs, site information, and project details made available to the Bidder in relation to this RFP shall be used only for the purpose of preparing and submitting the Bid.
R-662 | The Bidder must not disclose, publish, circulate, or use RFP information for any other purpose without prior written permission from AIIMS Patna. | 179 | 17.28(ii) | Mandatory | Maintain confidentiality and obtain prior written permission from AIIMS Patna before disclosing or using project information outside of RFP participation. | Yes |  |  |  | The Bidder shall not disclose, publish, circulate, or use such information for any purpose other than participation in this RFP without prior written permission of AIIMS Patna.
R-663 | The Bidder must submit a complete, self-contained bid capable of evaluation based on documents submitted on CPPP. | 181 | 18.2(i)-(ii) | Mandatory | Submit a complete and self-contained bid via CPPP in accordance with the RFP. | Yes |  |  |  | The Bidder shall submit a complete Bid in accordance with this RFP.
R-664 | Any deviation, qualification, condition, reservation or exclusion must be clearly disclosed in the prescribed manner, and bidders must not make assumptions contrary to the RFP. | 182 | 18.3(vii) | Mandatory | Disclose any deviation, qualification, condition, reservation or exclusion in the manner prescribed in the RFP without making assumptions contrary to the RFP. | Yes |  |  |  | Any deviation, qualification, condition, reservation or exclusion shall be clearly disclosed by the Bidder in the manner prescribed in this RFP. The Bidder shall not make any assumption contrary to the RFP.
R-665 | Clarifications or shortfall documents requested by AIIMS Patna must be submitted within the stipulated timeframe. | 182 | 18.4(iv) | Submission logistics | Submit requested clarifications or shortfall documents within the time specified by AIIMS Patna. | Yes |  |  |  | Clarifications shall be submitted within the time specified by AIIMS Patna.
R-666 | Bidders must not contact AIIMS Patna regarding bid evaluation, scoring, ranking, comparison or selection from bid submission until declaration of evaluation results or contract award, except to answer written clarifications. | 183 | 18.6(i) | Mandatory | Refrain from contacting AIIMS Patna concerning the bid evaluation, scoring, or selection process, except in response to a formal written clarification. | Yes |  |  |  | From the submission of Bids until declaration of the evaluation result or award of the Contract, no Bidder shall contact AIIMS Patna regarding its Bid, evaluation, scoring, ranking, comparison or selection, except in response to a written clarification sought by AIIMS Patna.
R-667 | The technical proposal must attain a minimum qualifying score of 60 marks out of 100 to proceed to financial evaluation. | 185 | 19.2(ii) | Evaluation criteria | Score at least 60 marks out of 100 in the technical proposal evaluation. | Yes |  |  |  | The minimum qualifying technical score shall be 60 marks (minimum qualifying score out of 100 marks). Only technically qualified Bidders shall proceed to Financial Evaluation.
R-668 | Bidders must submit actual project documents and achieved results to demonstrate the quality of past design and engineering work in completed BSL-3/BSL-4 assignments. | 185 | 19.3 Sl. No. 1 | Evaluation criteria | Provide project documentation demonstrating quality of design and engineering in completed BSL-3/BSL-4 projects covering laboratory planning, containment HVAC, and one additional area. | Yes |  |  |  | The Bidder shall demonstrate the actual quality of its design and engineering work in completed BSL-3/BSL-4 assignments. The evaluation will cover laboratory planning and movement routes, containment HVAC and room-pressure design, and one additional area of past work selected by the Bidder. Marks will be based on actual project documents and achieved results, and not merely on the number or value of completed projects.
R-669 | Bidders must submit actual records showing design preparation, checking, approval, revision, equipment sizing, and correction of design problems from past BSL-3/BSL-4 projects. | 186 | 19.3 Sl. No. 2 | Evaluation criteria | Submit actual past project records for design checking, approval, revision, equipment sizing, and problem resolution rather than generic procedures or blank formats. | Yes |  |  |  | The Bidder shall submit actual records showing how designs were prepared, checked, approved and revised in past projects. The evaluation will also examine how important equipment and systems were selected or sized, and how design problems that could affect testing, validation, certification or final acceptance were identified and corrected. General company procedures or blank QA/QC formats will not be treated as evidence of past work.
R-670 | Bidders must demonstrate actual biosafety and biocontainment work personally performed by the proposed Biosafety Expert in completed BSL-3/BSL-4 projects. | 186 | 19.3 Sl. No. 4 | Evaluation criteria | Submit evidence of biosafety and biocontainment work personally executed by the proposed Biosafety Expert in completed BSL-3/BSL-4 projects. | Yes |  |  |  | The Bidder shall demonstrate the actual biosafety and biocontainment work personally performed by the proposed Biosafety Expert in completed BSL-3/BSL-4 projects. The evaluation may cover biosafety planning, design and equipment review, construction-stage review, commissioning and validation support, certification support, SOPs, training and operational readiness. Marks will be awarded for the Expert's own work and not merely for the experience of the Bidder or firm.
R-671 | Bidders must provide evidence of independent third-party validation or regulatory certification/operational approval for completed BSL-3/BSL-4 facilities included in the technical proposal. | 186 | 19.3 Sl. No. 6 | Evaluation criteria | Submit proof of complete facility independent third-party validation or competent authority certification/licence/approval for past completed BSL-3/BSL-4 projects. | Yes |  |  |  | The Bidder shall provide evidence that a completed BSL-3/BSL-4 facility included in its Technical Proposal was independently validated by a competent third-party agency and/or received certification, licence, authorisation, operational approval or equivalent permission from the concerned competent authority. Testing of individual equipment or internal validation by the Bidder, consultant or contractor will not be treated as independent validation of the complete facility.
R-672 | The proposed team must present how it will carry out the assignment (covering design, tender documentation, construction support, testing, validation, certification, and maintenance considerations) and answer four technical questions posed to every bidder. | 187 | Clause 19.3 / Sl. No. 7 | Evaluation criteria | Deliver the technical presentation detailing execution methodology and respond to the four standardized technical questions. | Yes |  |  |  | The proposed team shall explain how it will carry out the AIIMS Patna assignment, including design, tender documentation, construction support, testing, validation, certification, and maintenance considerations. The team shall also answer the same four technical questions (on four different topic mentioned herein) asked to every Bidder.
R-673 | For every scoring claim, the bidder must detail the project relied upon, exact role, supporting document, and exact Technical Bid PDF page number using the prescribed format. | 187 | 19.4(ii) | Mandatory | Fill out the format under each technical evaluation parameter specifying the relied assignment, exact role, supporting document, and exact PDF page number. | Yes |  |  |  | For every scoring claim, the Bidder shall mention, in the format provided under the relevant Parameter, the project or assignment relied upon, the Bidder’s or Joint Venture Member’s exact role, the supporting document and the exact Technical Bid PDF page number.
R-674 | Bidders must score a minimum of 60 marks out of 100 in the technical evaluation to qualify for opening of their Financial Proposals. | 188 | 20.1(i) | Evaluation criteria | Achieve a minimum technical score of 60 marks out of 100. | Yes |  |  |  | The Financial Proposals of only technically qualified Bidders, who have score minimum 60 marks out of 100 marks, shall be opened through CPPP on the date and time notified by AIIMS Patna on CPP Portal.
R-675 | The quoted total consultancy fee in the BOQ must be all-inclusive, covering professional fees, GST and applicable taxes, travel, site visits, Biosafety Expert/Sub-Consultant fees, overheads, and incidental expenses. | 188 | 20.2(i) | Mandatory | Quote an all-inclusive consultancy fee in the prescribed BOQ/Financial Proposal incorporating all taxes, site visits, expert fees, and incidental expenses. | Yes |  |  |  | The total consultancy fee quoted in the prescribed BOQ/Financial Proposal shall be treated as the Evaluated Price. It shall include professional fees, GST and other applicable taxes, travel, site visits, Biosafety Expert/Sub-Consultant fees, overheads and all incidental expenses required for completing the Assignment.
R-676 | Final selection is based on QCBS with 70% technical and 30% financial weightage, requiring a minimum technical qualifying score of 60 out of 100 marks. | 189 | 21.1(i) | Evaluation criteria | Obtain at least 60 marks in technical evaluation to be eligible for QCBS financial evaluation. | Yes |  |  |  | Final selection shall be made through Quality and Cost Based Selection (QCBS) with Technical weightage 70% and financial weightage 30%. The Technical Proposal shall be evaluated out of 100 marks. Only bidders meeting the minimum qualifying technical score (i.e. 60 marks out of 100 marks) shall be eligible for Financial Evaluation.
R-677 | Bidders are prohibited from contacting AIIMS Patna or associated evaluation personnel from bid submission until contract award, except through formal written/electronic communication to designated authorities. | 190 | 22.1 | Mandatory | Refrain from contacting AIIMS Patna personnel regarding evaluation except via formal permitted written or electronic communication. | Yes |  |  |  | From the bid submission deadline until completion of evaluation and award of contract, no Bidder shall contact AIIMS Patna, its officers, evaluation committee members or any person associated with the procurement process on any matter relating to evaluation of its Proposal, except through formal written / electronic communication addressed to the designated authority, where permitted under this RFP.
R-678 | Bidders must respond to any clarification sought by AIIMS Patna only in the specified manner and within the stipulated timeline. | 190 | 22.1 | Mandatory | Submit clarifications strictly within the time and in the manner requested by AIIMS Patna. | Yes |  |  |  | Any clarification sought by AIIMS Patna shall be responded to only in the manner and within the time specified by AIIMS Patna.
R-679 | Representations or debriefing requests regarding proposal rejection must be submitted in writing or electronically to the Executive Director, AIIMS Patna, within seven days of the declaration of evaluation results. | 190 | 22.2(i) | Submission logistics | Submit any representation against rejection to the Executive Director, AIIMS Patna, within 7 days from the declaration of results. | Yes |  |  |  | A Bidder shall have the right to submit a representation or seek debriefing regarding the rejection of its proposal, in writing or through electronic means, within seven (07) days from the date of declaration of the Techno-commercial or Financial Evaluation results. Such representations shall be addressed to the Executive Director, AIIMS Patna.
R-680 | The contract/agreement will only be executed after the successful bidder submits the performance bank guarantee. | 191 | 22.3 | Mandatory | Submit the performance bank guarantee prior to the signing of the agreement/contract. | Yes |  |  |  | The signing of agreement/contract will be done only after submission of performance bank guarantee.
R-681 | The successful bidder must acknowledge the Letter of Award, provide the Performance Security, and sign the Contract Agreement. | 191 | 22.4(i) | Mandatory | Acknowledge the LOA, submit the required Performance Security, and execute the contract agreement. | Yes |  |  |  | The Successful Bidder shall acknowledge the Letter of Award, furnish the Performance Security, execute the Contract Agreement.
R-682 | The Consultant must perform services strictly in accordance with the National Guidelines for BSL-3 Containment Facility 2024, WHO Laboratory Biosafety Manual, applicable NABL/ISO standards, National Building Code, Energy Conservation Building Code, and all applicable laws. | 194 | 23.2(i) | Mandatory | Perform services following the prescribed national biosafety guidelines, WHO manual, building codes, and relevant ISO/NABL standards. | Yes |  |  |  | The Consultant shall perform the Services with the skill, care and diligence expected of a competent professional firm experienced in high-containment laboratory design, strictly in accordance with the National Guidelines for the Establishment and Certification of Biosafety Level-3 (BSL-3) Containment Facility, 2024, issued by the Department of Biotechnology in collaboration with the Indian Council of Medical Research, as amended from time to time; the WHO Laboratory Biosafety Manual; applicable NABL and ISO standards; the National Building Code; the Energy Conservation Building Code; and all other Applicable Laws.
R-683 | The Consultant must maintain throughout the contract period every valid registration, licence, approval, and professional authorisation, including valid registration of the Lead Architect with the Council of Architecture. | 194 | 23.3(i) | Mandatory | Maintain all necessary professional registrations and licences throughout the contract, specifically including Council of Architecture registration for the Lead Architect. | Yes |  |  |  | The Consultant shall comply with all Applicable Laws and shall maintain throughout the Contract period every valid registration, licence, approval and professional authorisation required for performance of the Services, including valid registration of the Lead Architect with the Council of Architecture.
R-684 | All notices under the contract must be in writing in English and delivered by hand, registered post, or e-mail. | 194 | 23.5(i) | Mandatory | Deliver all formal notices in writing in English via hand delivery, registered post, or email. | Yes |  |  |  | Every notice under the Contract shall be in writing in English and shall be delivered by hand, registered post or e-mail to the address stated herein or to any replacement address notified in writing.
R-685 | The Consultant must maintain proper and complete records relating to the Services and preserve them for at least three years after contract closure or until final conclusion of audit/judicial/vigilance proceedings. | 194 | 23.6(i) | Mandatory | Keep and preserve all records relating to the services for at least 3 years after contract closure or until any ongoing audit/judicial/vigilance proceedings conclude. | Yes |  |  |  | The Consultant shall maintain proper and complete records relating to the Services and shall preserve them for at least three (3) years after closure of the Contract, or till the final conclusion of audit, judicial, vigilance or any
R-686 | The Consultant is prohibited from assigning the contract or subletting any part of the Services, except for engaging one permitted Biosafety Sub-Consultant. | 195 | 23.7(i) | Mandatory | Do not assign or sub-let the contract services, except for engaging one Biosafety Sub-Consultant if permitted under the RFP. | Yes |  |  |  | The Consultant shall not assign the Contract or sub-let any part of the Services, except that it may engage one Biosafety Sub-Consultant where permitted by the RFP.
R-687 | The Consultant must avoid conflict of interest and must not bid for any construction or supply work arising from its own design for this facility. | 195 | 23.8(i) | Mandatory | Refrain from accepting conflicting work and do not bid for any construction or supply work originating from the consultant's own design for this facility. | Yes |  |  |  | The Consultant shall not accept or undertake any work that conflicts with this Assignment and shall not bid for any construction or supply work arising from its own design for this facility.
R-688 | The successful Bidder must acknowledge and unconditionally accept the Letter of Award within 7 days of its issue. | 196 | 24.2(ii) | Mandatory | Acknowledge and submit unconditional acceptance of the Letter of Award within 7 days of its receipt. | Yes |  |  |  | The successful Bidder shall acknowledge and unconditionally accept the Letter of Award within seven (7) days of its issue.
R-689 | No change in accepted scope, Key Personnel, Biosafety Expert, Technical Proposal, Financial Proposal, or Contract Price is permitted at the contract-signing stage. | 196 | 24.2(iv) | Mandatory | Ensure no modifications are requested or made to accepted scope, personnel, proposals, or price at the contract-signing stage. | Yes |  |  |  | No change in the accepted scope, Key Personnel, Biosafety Expert, Technical Proposal, Financial Proposal or Contract Price shall be permitted at the contract-signing stage.
R-690 | The successful Bidder must submit the signed Contract Agreement along with prescribed Performance Security within 15 working days of receipt of the Letter of Award. | 196 | 24.3(i) | Submission logistics | Submit the duly signed Contract Agreement together with the prescribed Performance Security within 15 working days from receiving the Letter of Award (or shorter period if specified). | Yes |  |  |  | The successful Bidder shall submit the duly signed Contract Agreement together with the prescribed Performance Security within fifteen (15) working days from receipt of the Letter of Award, or within such shorter period expressly specified in the Letter of Award.
R-691 | The Contract Agreement must be signed by the authorised representatives of the Consultant and AIIMS Patna. | 196 | 24.3(iii) | Mandatory | Ensure the Contract Agreement is signed by the Consultant's authorised representative. | Yes |  |  |  | The Contract Agreement shall be signed by the authorised representatives of the Consultant and AIIMS Patna.
R-692 | Before issuance of the Notice to Proceed, the Consultant must submit the valid Performance Security, signed Contract Agreement, mobilisation and Key Personnel deployment confirmation, authorisation of Team Leader and Project Coordinator, confirmation of engagement/availability of approved Biosafety Expert, and commencement registrations/insurance documents. | 197 | 24.4(i) | Mandatory | Submit all prerequisite commencement documents including Performance Security, Contract Agreement, personnel deployments, expert engagements, and insurance documents prior to the issuance of Notice to Proceed. | Yes |  |  |  | Before issuance of the Notice to Proceed, the Consultant shall submit: (a) valid Performance Security; (b) signed Contract Agreement; (c) mobilisation and Key Personnel deployment confirmation; (d) authorisation of the Team Leader and Project Coordinator; (e) confirmation of engagement and availability of the approved Biosafety Expert, whether deployed in-house, through an eligible JV arrangement or through an approved Sub-Consultant; and (f) registrations, insurance documents and other commencement documents required under the Contract.
R-693 | The successful bidder must furnish a Performance Security of 5% of the total Contract Value within 15 working days from receipt of the Letter of Award. | 197 | 24.5(i) | Mandatory | Furnish Performance Security amounting to 5% of the total Contract Value within 15 working days of receiving the Letter of Award. | Yes |  |  |  | The successful Bidder shall furnish Performance Security equal to five per cent (5%) of the total Contract Value within fifteen (15) working days from receipt of the Letter of Award.
R-694 | Performance Security must be furnished in the prescribed format as an e-PBG/PBG or Bank Guarantee issued by a Scheduled Bank in India in favour of The Executive Director, AIIMS Patna. | 197 | 24.5(ii) | Mandatory | Issue the Performance Security as an e-PBG/PBG or Bank Guarantee from a Scheduled Bank in India in favour of 'The Executive Director, All India Institute of Medical Sciences, Patna.' | Yes |  |  |  | The Performance Security shall be furnished in the prescribed format in the form of an e-PBG/PBG or Bank Guarantee issued by a Scheduled Bank in India, in favour of: “The Executive Director, All India Institute of Medical Sciences, Patna.”
R-695 | If a NeSL-based e-PBG is provided, the bidder must ensure it is generated via the NeSL platform and available for verification by AIIMS Patna, remaining valid for the prescribed period including claim period. | 197 | 24.5(iii) | Mandatory | Ensure the e-PBG is generated through NeSL and accessible for verification, with validity covering the required period and claim period. | Yes |  |  |  | Where a NeSL-based e-PBG is furnished, the Bidder shall ensure that the e- PBG is duly generated/issued through the NeSL platform and is available for verification by AIIMS Patna. The Performance Security shall remain valid for the period prescribed in the Bidding Document, including the claim period, wherever applicable
R-696 | For a registered JV constituted as a legal entity, the Performance Security must ordinarily be furnished in the name of the JV entity. | 197 | 24.5(v) | Mandatory | Furnish the Performance Security in the name of the JV entity if operating as a registered JV legal entity. | Yes |  |  |  | Where the Consultant is a registered JV constituted as a legal entity, the Performance Security shall ordinarily be furnished in the name of the JV entity.
R-697 | The Performance Security must initially be valid for 14 months and remain valid throughout the entire Contract Period including construction, commissioning, validation, certification-support, and Defect Liability Support. | 197 | 24.5(vi) | Mandatory | Maintain Performance Security validity initially for 14 months and continuously throughout all phases of the Contract Period. | Yes |  |  |  | The Performance Security shall: (a) initially remain valid for fourteen (14) months; and (b) remain valid throughout the Contract Period, including construction, commissioning, validation, certification-support and Defect Liability Support obligations.
R-698 | If the Contract Period extends beyond existing validity, the Consultant must extend the Performance Security for an additional 12 months or longer as required. | 197 | 24.5(vii) | Mandatory | Extend the Performance Security by 12 months or as required whenever the Contract Period exceeds the existing validity. | Yes |  |  |  | If the Contract Period extends beyond the existing validity of the Performance Security, the Consultant shall extend it for a further period of twelve (12) months or for such longer period as required to maintain the prescribed validity.
R-699 | The extended Performance Security must be submitted at least 30 days prior to the expiration of the existing instrument. | 197 | 24.5(viii) | Submission logistics | Submit the extended Performance Security at least 30 days before the current instrument expires. | Yes |  |  |  | The extended Performance Security shall be submitted at least thirty (30) days before expiry of the existing instrument.
R-700 | If any amount is recovered from the Performance Security, the Consultant must restore it to the original required amount within 15 days of written demand. | 198 | 24.5(xi) | Mandatory | Restore the Performance Security to its original amount within 15 days following written notice of any deduction. | Yes |  |  |  | Where any amount is recovered from the Performance Security during the Contract Period, the Consultant shall restore it to the original required amount within fifteen (15) days of written demand.
R-701 | Phase I of the consultancy must be completed within 60 days from the Notice to Proceed. | 200 | 24.9(i) | Mandatory | Complete all Phase I deliverables and scopes within 60 days of the Notice to Proceed. | Yes |  |  |  | Phase I shall be completed within sixty (60) days from the Notice to Proceed.
R-702 | Consultancy milestones become payable only upon submission of complete deliverables, completion of review, closure of observations, submission of calculations/matrices/editable files/expert sign-offs, and written acceptance by AIIMS Patna. | 201 | 24.13(i) | Mandatory | Fulfill all milestone acceptance criteria including complete deliverable submission, technical/biosafety review completion, observation closures, expert sign-offs, editable files submission, and obtaining written acceptance from AIIMS Patna. | Yes |  |  |  | A milestone shall become payable only after: (b) submission of the complete deliverable; (c) completion of the applicable technical and biosafety review; (d) closure of material review observations; (e) submission of required calculations, matrices, editable files and expert sign-offs; and (f) written acceptance by the nodal officer of AIIMS Patna.
R-703 | Phase-I milestones M-1 to M-8 must collectively be completed within 60 days from the Notice to Proceed. | 203 | (iii) | Mandatory | Complete all Phase-I deliverables (milestones M-1 to M-8) within 60 days from the issuance of the Notice to Proceed. | Yes |  |  |  | All Phase-I milestones from M-1 to M-8 shall collectively be completed within sixty (60) days from the Notice to Proceed. No separate contractual completion day shall apply to M-1 to M-7.
R-704 | The Consultant must submit a dependency-linked Program within 5 days of the Notice to Proceed. | 204 | (iv) | Mandatory | Submit a dependency-linked Program showing proposed sequences and dates for milestones M-1 to M-8, review meetings, Biosafety Expert interventions, and the final Good-for-Tender submission within 5 days from the Notice to Proceed. | Yes |  |  |  | Within five (5) days from the Notice to Proceed, the Consultant shall submit a dependency-linked Program indicating its proposed sequence and dates for M- 1 to M-8, review meetings, Biosafety Expert interventions and final Good-for- Tender submission.
R-705 | Prescribed design-review gates must not be bypassed or combined without prior written approval. | 204 | (iv) | Mandatory | Obtain prior written approval before bypassing or combining any prescribed design-review gate. | Yes |  |  |  | The Consultant may achieve any milestone earlier, but shall not bypass or combine a prescribed design-review gate without prior written approval.
R-706 | The approved Biosafety Expert's first physical visit must be completed before M-2 acceptance. | 204 | (vi) | Mandatory | Conduct and complete the approved Biosafety Expert's first mandatory physical site visit prior to seeking acceptance of Milestone M-2. | Yes |  |  |  | The approved Biosafety Expert’s first mandatory physical visit shall be completed before acceptance of M-2.
R-707 | Invoices may only be submitted after written acceptance of the relevant milestone. | 204 | 24.15(i) | Mandatory | Await written acceptance of a milestone before submitting the corresponding invoice. | Yes |  |  |  | The Consultant may submit an invoice only after written acceptance of the relevant milestone.
R-708 | Invoices must include all mandatory contract, tax, banking, and certification details. | 205 | 24.15(ii) | Mandatory | Ensure every invoice includes contract and milestone references, milestone-acceptance certificate, basic fee claimed, separate GST, valid GSTIN and compliant tax invoice/e-invoice, bank account details, statutory declarations, and authorized signatory certification. | Yes |  |  |  | Each invoice shall include: (a) Contract and milestone reference; (b) milestone-acceptance certificate; (c) Basic Consultancy Fee claimed; (d) GST shown separately; (e) valid GSTIN and compliant tax invoice/e-invoice wherever applicable; (f) bank account and electronic-payment details; (g) statutory declarations or documents required for payment; and (h) certification by the authorized signatory that the claim is in accordance with the Contract.
R-709 | The Consultant must maintain a valid GST registration throughout the contract period. | 205 | 24.16(i) | Mandatory | Maintain active and valid GST registration during the entire period of taxable supplies under the contract. | Yes |  |  |  | The Consultant shall maintain a valid GST registration throughout the period in which taxable supplies are made under the Contract.
R-710 | The Consultant must comply with all GST invoicing, filing, and deposit obligations. | 205 | 24.16(iii) | Mandatory | Mention AIIMS Patna's GSTIN on invoices, report invoices accurately in GST returns, deposit GST within the prescribed timeframe, file applicable returns, and promptly resolve any mismatch or reporting error. | Yes |  |  |  | The Consultant shall: (a) correctly mention the GSTIN of AIIMS Patna and other prescribed particulars on the invoice; (b) report the invoice accurately in its applicable GST return; (c) deposit the collected GST with the Government within the prescribed time; (d) file all applicable GST returns; and (e) rectify any invoice mismatch or reporting error promptly.
R-711 | Any reduction in the applicable GST rate must be passed on to AIIMS Patna. | 205 | 24.16(vii) | Mandatory | Pass on any reduction in the applicable GST rate to AIIMS Patna in subsequent invoicing. | Yes |  |  |  | Any reduction in the applicable GST rate shall be passed on to AIIMS Patna. Any increase shall be considered only where legally applicable and supported by documentary evidence and as per terms of RFP.
R-712 | The Consultant must bear any additional tax, interest, or penalty arising from Consultant-attributable delay or default. | 206 | 24.16(viii) | Mandatory | Absorb and pay any additional tax, interest, or penalty resulting from delays or defaults caused by the Consultant. | Yes |  |  |  | Any additional tax, interest or penalty arising from delay or default attributable to the Consultant shall be borne by the Consultant.
R-713 | Services and deliverables must comply with RFP, DBT-ICMR requirements, statutory norms, and professional standards. | 206 | 24.18(i) | Mandatory | Ensure all services and deliverables strictly conform to RFP terms, applicable DBT-ICMR requirements, statutory requirements, standards, and professional practice. | Yes |  |  |  | The Consultant warrants that all Services and deliverables shall comply with the RFP, applicable DBT-ICMR requirements, statutory provisions, applicable standards and accepted professional practice.
R-714 | Consultant-attributable errors, omissions, inconsistencies, or non-compliances must be rectified without additional cost. | 206 | 24.18(iii) | Mandatory | Perform root-cause identification, revise drawings, BOQ, calculations, or BIM models, engineer corrective measures, provide clarifications, and support re-testing/revalidation without charging additional fees. | Yes |  |  |  | Any error, omission, inconsistency, inadequate coordination or non- compliance attributable to the Consultant shall be corrected without additional cost, including: (a) root-cause identification; (b) revision of drawings, specifications, calculations, BOQ or BIM models; (c) engineering of corrective measures; (d) construction and commissioning clarification; and (e) support for re-testing or revalidation attributable to such error.
R-715 | The Consultant must maintain Professional Indemnity / Errors and Omissions Insurance. | 206 | 24.19(i) | Mandatory | Procure and maintain Professional Indemnity/Errors and Omissions Insurance covering professional negligence, design defects, inadequate specifications, and omissions. | Yes |  |  |  | The Consultant shall maintain Professional Indemnity/Errors and Omissions Insurance covering professional negligence, errors, omissions, defective design, inadequate specifications and failure to exercise due professional care.
R-716 | The sum insured must not be less than the total Basic Consultancy Fee or any higher amount specified in the Letter of Award. | 207 | 24.19(ii) | Mandatory | Ensure the insurance policy covers an amount not less than the total Basic Consultancy Fee or the amount stipulated in the Letter of Award. | Yes |  |  |  | (ii) The sum insured shall not be less than the total Basic Consultancy Fee or such higher amount specified in the Letter of Award.
R-717 | Evidence of insurance must be submitted within fifteen days of receiving the Letter of Award. | 207 | 24.19(iii) | Mandatory | Submit evidence of insurance within 15 days from receipt of the Letter of Award. | Yes |  |  |  | (iii) Evidence of insurance shall be submitted within fifteen (15) days from receipt of the Letter of Award.
R-718 | Insurance must remain valid throughout the Contract Period, including the defect liability period. | 207 | 24.19(iv) | Mandatory | Maintain active insurance validity across the entire Contract Period and defect liability period. | Yes |  |  |  | (iv) The insurance shall remain valid throughout the Contract Period including defect liability period.
R-719 | The Consultant must submit renewal documents prior to the expiry of each insurance policy. | 207 | 24.19(v) | Mandatory | Submit policy renewal documents before any existing insurance policy expires. | Yes |  |  |  | (v) The Consultant shall submit renewal documents before expiry of each policy.
R-720 | The Consultant must provide Defect Liability Support for the entire DLP of the works contract, which must be at least 12 months from commissioning and operational handover. | 207 | 24.20(i) | Mandatory | Provide defect liability support for a minimum of 12 months following commissioning and operational handover. | Yes |  |  |  | (i) The Consultant shall provide Defect Liability Support for the entire Defect Liability Period of the BSL-3 works contract, which shall not be less than twelve (12) months from commissioning and operational handover of the facility.
R-721 | During DLP, critical defects must be acknowledged within 4 hours, initial technical response provided within 1 working day, and site attended within 24-48 hours when directed; major and minor defects must be responded to within 2 and 5 working days respectively. | 207 | 24.20(ii) | Mandatory | Adhere to the prescribed response and site visit timelines for critical, major, and minor defects, and conduct quarterly scheduled DLP review visits. | Yes |  |  |  | (ii) During Defect Liability Support, the Consultant shall acknowledge a Critical defect within four hours, provide an initial technical response within one working day and attend site within 24-48 hours where directed and reasonably necessary. Major and Minor defects shall be responded to within two and five working days respectively. The Contract Price includes every quarter scheduled DLP review visits and all visits required to correct Consultant-attributable errors.
R-722 | The Consultant must execute specified defect liability management tasks and maintain a Defect Liability Support Register. | 207 | 24.20(iv) | Mandatory | Review defects, determine technical causes, advise corrective actions, review proposals, verify closures, obtain Biosafety Expert input for containment-critical issues, and maintain a Defect Liability Support Register. | Yes |  |  |  | (iv) The Consultant shall: (a) review reported defects and performance deficiencies; (b) identify the probable technical cause; (c) advise corrective action; (d) review rectification proposals of the Construction Agency; (e) verify rectification and closure; (f) obtain Biosafety Expert input for containment-critical defects; and (g) maintain a Defect Liability Support Register.
R-723 | The Consultant must promptly notify AIIMS Patna upon learning of any event likely to cause milestone delay. | 208 | 24.23(i) | Mandatory | Issue prompt written notification to AIIMS Patna as soon as any delay event becomes known. | Yes |  |  |  | (i) The Consultant shall promptly notify AIIMS Patna upon becoming aware of any event likely to delay a milestone.
R-724 | An application for Extension of Time must include cause and period of delay, affected activities/milestones, supporting records, mitigation measures, and a revised recovery program. | 208 | 24.23(ii) | Mandatory | Submit an Extension of Time application containing all prescribed particulars, supporting records, mitigation steps, and a revised recovery program. | Yes |  |  |  | (ii) An application for Extension of Time shall state: (a) cause and period of delay; (b) affected activities and milestones; (c) supporting records; (d) mitigation measures undertaken; and (e) revised recovery Program.
R-725 | Final milestone payment processing requires acceptance of deliverables, submission of final as-built/native files, closure of observations, submission of compliance/certification dossier, and settlement of penalties/recoveries. | 208 | 24.24(i) | Mandatory | Complete all payment-linked deliverables, submit final editable/digital files, close technical/biosafety observations, submit final certification dossier, and settle any penalties or LD. | Yes |  |  |  | (i) The final milestone invoice shall be subject to: (a) acceptance of all payment-linked deliverables through the final handover/certification-readiness milestone; (b) submission of final as-built, native, editable and digital files; (c) closure of material technical and biosafety observations; (d) submission of the final compliance and certification-support dossier and related needful; (e) settlement of penalties, LD and recoveries; and
R-726 | Submission of a No-Claim Certificate is required where applicable for final milestone payment processing. | 209 | 24.24(i)(f) | Mandatory | Submit a No-Claim Certificate where required. | Yes |  |  |  | (f) submission of a No-Claim Certificate, where required.
R-727 | All non-public project information must be treated as confidential and used solely for the provision of the Services. | 211 | 25.1(i) | Mandatory | Maintain strict confidentiality over all non-public project information and restrict its use exclusively to the contracted Services. | Yes |  |  |  | (i) Confidential information: All non-public information received, accessed or generated for the RFP, Contract or Services shall be treated as confidential and used only for the Services. It includes drawings and models; containment, pressure-zoning, airflow, HVAC and effluent-treatment concepts; security and access-control arrangements; sample/waste workflows; institutional, research, financial, personnel and operational data; and Project records. For this Section, the Consultant includes its personnel, experts and approved sub- consultants.
R-728 | The Consultant must comply with all applicable statutory requirements and laws concerning confidentiality, data protection, and information security. | 211 | 25.1(ii) | Mandatory | Comply with applicable laws and statutory requirements governing confidentiality, data protection, and information security. | Yes |  |  |  | (ii) Statutory requirement: The Consultant shall also comply with all applicable laws relating to confidentiality, data protection and information security, including any statutory requirements applicable to Government institutions from time to time.
R-729 | Consultant must implement confidentiality controls, bind authorized persons in writing, apply safeguards, and avoid placing project information on unauthorized public clouds or transferring it without AIIMS Patna's prior written approval. | 211 | 25.1(iii) | Mandatory | Restrict confidential disclosures to authorized personnel bound in writing, implement safeguards, and obtain prior written approval before using public cloud storage or transferring data. | Yes |  |  |  | (iii) Confidentiality controls: The Consultant shall disclose confidential information only to authorized persons who need it for the services; bind them in writing to equivalent obligations; apply reasonable technical, physical and organizational safeguards; and not publish, commercialize, transfer or use it for another project. Project information shall not be placed on an unauthorized public cloud or transferred to an unapproved person or location without AIIMS Patna’s prior written approval.
R-730 | The Consultant must notify AIIMS Patna within 24 hours of any actual or suspected security incident, investigate the incident, preserve evidence, and bear reasonable remediation costs attributable to it. | 211 | 25.1(iv) | Mandatory | Notify AIIMS Patna within 24 hours of detecting an actual or suspected security incident, contain and investigate the event, preserve evidence, and cover remediation costs if attributable to the Consultant. | Yes |  |  |  | (iv) Security incident: The Consultant shall promptly, and in any event within twenty-four (24) hours of becoming aware, notify AIIMS Patna of any actual or suspected unauthorized access, loss, disclosure, corruption or misuse of Project information, without prejudice to any shorter statutory reporting period. It shall contain and investigate the incident, preserve evidence, comply with lawful directions and bear the reasonable remediation cost to the extent the incident is attributable to it.
R-731 | The Consultant must keep Project Data accurate, secure, indexed, and recoverable, and submit complete hard copies and editable/native digital formats at milestones, on request, and at close-out. | 212 | (vii) | Mandatory | Maintain and submit Project Data in hard copy and searchable, editable/native and specified digital formats at milestones and close-out. | Yes |  |  |  | The Consultant shall keep it accurate, secure, indexed and recoverable and submit complete hard copies and searchable, editable/native and open or AIIMS-specified digital formats at each applicable milestone, on reasonable request and at close-out.
R-732 | The Consultant must secure equivalent written intellectual property assignments from personnel and sub-consultants, and execute confirmatory documents upon request. | 212 | (viii) | Mandatory | Obtain written assignments from personnel and sub-consultants and execute confirmatory assignment documents when requested. | Yes |  |  |  | The Consultant shall obtain equivalent written assignments from its personnel and sub-consultants and execute confirmatory documents when requested.
R-733 | Third-party material must only be used with prior disclosure, proper licenses, and prior written approval for any restrictions inconsistent with AIIMS Patna's use. | 212 | (ix) | Mandatory | Disclose third-party material, secure necessary licenses, and obtain prior written approval from AIIMS Patna for any usage restrictions. | Yes |  |  |  | Third-party material shall be used only with prior disclosure and all necessary licenses; any restriction inconsistent with AIIMS Patna’s intended use requires its prior written approval.
R-734 | The Consultant must replace or modify infringing material at no additional cost or procure necessary rights to use it. | 212 | (xi) | Mandatory | Replace, modify, or procure usage rights for any infringing material at no extra cost to AIIMS Patna. | Yes |  |  |  | It shall, at no additional cost and without reducing compliance, replace or modify infringing material or procure the right to use it.
R-735 | The Consultant must indemnify AIIMS Patna against losses, liabilities, claims, and legal costs arising from breaches, errors, or negligence, and defend third-party claims at its own cost. | 213 | (xii) | Mandatory | Indemnify AIIMS Patna against claims/losses and defend third-party claims without settling them without prior written consent. | Yes |  |  |  | The Consultant shall indemnify AIIMS Patna, its officers and employees against direct loss, liability, claim and reasonable legal cost to the extent arising from its breach of Contract or law, professional negligence, design error or omission, confidentiality or data-security breach, intellectual-property infringement, bodily injury or property damage, or its employment, tax or sub-consultant claims. On prompt notice, it shall defend a third-party claim at its cost, keep AIIMS Patna informed and not settle a claim that admits liability or imposes an obligation on AIIMS Patna without prior written consent.
R-736 | The Consultant must maintain the insurance coverage required by the RFP. | 213 | (xiii) | Mandatory | Procure and maintain the required insurance coverage as applicable. | Yes |  |  |  | It shall maintain the insurance required by the RFP as applicable.
R-737 | An affected party claiming Force Majeure must notify the other party promptly within seven days with supporting evidence. | 214 | 26.1 ii) | Mandatory | Submit notice of Force Majeure within seven days of awareness, stating details and relief sought, accompanied by supporting evidence. | Yes |  |  |  | The affected Party shall notify the other promptly and, unless prevented by the event, within seven (7) days after becoming aware of it, stating the nature, affected obligations, commencement, likely duration and relief sought, with reasonable supporting evidence.
R-738 | During suspension, the Consultant must stop affected activities, secure work and data, minimize costs, and not reassign Key Personnel without approval. | 215 | 26.1 vii) | Mandatory | Halt affected work, preserve records and models, avoid reassigning Key Personnel without approval, and comply with protective directions. | Yes |  |  |  | The Consultant shall promptly stop only the affected activities; secure and preserve work, records, models and data; minimize cost; maintain essential coordination; and not reassign Key Personnel without approval.
R-739 | Upon written direction to resume after suspension, the Consultant must resume promptly and submit a revised program. | 215 | 26.1 viii) | Mandatory | Resume services promptly and submit a revised work program following written direction from AIIMS Patna. | Yes |  |  |  | On written direction, the Consultant shall resume promptly and submit a revised program.
R-740 | Upon termination of the Contract, the Consultant must halt work, return AIIMS Patna property, hand over all deliverables and Project Data, and provide transition assistance. | 216 | 26.1 xii) | Mandatory | Stop activities, return property, hand over deliverables and editable/native files, and provide transition assistance upon contract termination. | Yes |  |  |  | On any termination, the Consultant shall stop as directed, secure the work, return AIIMS Patna property, and promptly hand over all completed and in-progress deliverables, editable/native files, BIM models, CFD analysis reports, records, licenses and Project Data, together with reasonable transition assistance.
R-741 | During any dispute, the Consultant must continue safe and undisputed Services unless directed otherwise by AIIMS Patna. | 216 | 26.1 xv) | Mandatory | Continue executing safe and undisputed Services while a dispute is being resolved. | Yes |  |  |  | During a dispute, the Consultant shall continue safe and undisputed Services unless the Contract has ended or AIIMS Patna directs otherwise, and AIIMS Patna shall release undisputed amounts.
R-742 | The Bidder and Consultant must observe the Code of Integrity for Public Procurement under the GFR and applicable Government of India instructions throughout the procurement and Contract. | 218 | 27.2 | Mandatory | Observe the Code of Integrity for Public Procurement under the General Financial Rules and Government of India instructions throughout procurement and Contract implementation. | Yes |  |  |  | The Bidder and, after award, the Consultant shall observe the Code of Integrity for Public Procurement under the General Financial Rules and applicable Government of India instructions throughout the procurement and Contract.
R-743 | Bidders and associated entities must refrain from prohibited practices including offering or accepting undue advantage, misrepresentation, collusion, coercion, obstruction of audits, improper influence, and undisclosed conflicts of interest. | 218 | 27.2(i) | Mandatory | Refrain from offering, soliciting, or accepting undue advantage; misrepresenting or concealing facts; colluding; coercing; obstructing investigations; improperly influencing procurement; misusing confidential information; or participating with an undisclosed conflict of interest. | Yes |  |  |  | No such person shall offer, solicit or accept an undue advantage; misrepresent or conceal material facts; collude or impair competition; coerce or threaten any person; obstruct an audit or investigation; improperly influence the procurement; misuse confidential information; or participate while having an undisclosed conflict of interest.
R-744 | The Bidder must disclose with its bid, and promptly update, conflicts of interest, procurement-related agent fees, and integrity transgressions or debarments during the preceding three years. | 218 | 27.2(ii) | Mandatory | Disclose with the bid and promptly update any actual or potential conflict of interest, agent commission or fee, and any relevant conviction, integrity transgression, suspension, or debarment during the preceding three (3) years along with present status. | Yes |  |  |  | The Bidder shall disclose with its bid, and promptly update, any actual or potential conflict of interest; procurement- related agent commission or fee; and relevant conviction, integrity transgression, suspension or debarment during the preceding three (3) years, with its present status.
R-745 | Where prescribed, the Bidder must submit a duly executed prescribed Integrity Pact with the bid and comply with it through contractual completion. | 218 | 27.2(iii) | Mandatory | Submit the duly executed prescribed integrity pact with the bid where prescribed and comply with its terms until completion of all contractual obligations. | Yes |  |  |  | Where the Tender Data or RFP prescribes an Integrity Pact, the Bidder shall submit the duly executed prescribed integrity pact with the bid and shall comply with it until completion of all contractual obligations.
R-746 | All biosafety-critical technical reviews must be conducted exclusively by the designated Biosafety Expert of the A&E Consultant without delegation or substitution. | 222 | 28.1(iv) | Mandatory | Deploy the designated Biosafety Expert to undertake all biosafety-critical technical reviews and ensure these duties are not delegated to PMC, contractor, or any other agency. | Yes |  |  |  | All biosafety-critical technical reviews shall be undertaken by the designated Biosafety Expert of the A&E Consultant. Such biosafety-critical reviews shall not be delegated to or substituted by the PMC, Works Agency/Contractor or any other agency.
R-747 | The A&E Consultant must conduct site visits as per the approved staffing schedule and at mandatory technical hold-points. | 222 | 28.2 | Mandatory | Undertake site visits at scheduled intervals in accordance with the approved deployment and staffing plan and attend mandatory technical hold-points. | Yes |  |  |  | The A&E Consultant shall undertake site visits at the intervals specified in its approved deployment and staffing schedule and additionally at mandatory technical hold-points.
R-748 | The A&E Consultant must issue site-visit reports detailing observations, deviations, risks, corrective actions, and items needing decision by AIIMS Patna. | 223 | 28.2(vii) | Mandatory | Prepare and submit site-visit reports detailing observations, non-compliances, risks, required remedies, and matters requiring decision by AIIMS Patna. | Yes |  |  |  | Issue site-visit reports identifying observations, deviations, risks, required corrective actions and matters requiring decision by AIIMS Patna.
R-749 | The Biosafety Expert must carry out and document biosafety-critical reviews across construction, installation, testing, commissioning, and validation-readiness stages. | 223 | 28.3 | Mandatory | Conduct and formally document reviews of biosafety aspects covering containment zoning, pressure cascades, envelope integrity, airlocks, HVAC, HEPA, EDS, and related systems throughout execution. | Yes |  |  |  | The A&E Consultant’s Biosafety Expert shall undertake and document biosafety-critical reviews throughout construction, installation, testing, commissioning and validation-readiness stages.
R-750 | The A&E Consultant must prepare an inspection and hold-point schedule specifying stages where work cannot proceed without technical review. | 224 | 28.4 | Mandatory | Formulate and issue a construction-stage inspection and hold-point schedule defining mandatory technical and biosafety hold-points. | Yes |  |  |  | The A&E consultant shall prepare a construction-stage inspection and hold-point schedule identifying the stages at which work shall not proceed without the required review.
R-751 | Work at biosafety-critical hold-points must not proceed without written authorization from AIIMS Patna or its authorized representative. | 224 | 28.4(xii)(d) | Mandatory | Halt execution at specified biosafety hold-points until formal written clearance is issued by AIIMS Patna or its representative following PMC verification and Biosafety Expert review. | Yes |  |  |  | The work shall proceed beyond the hold-point only after written authorization by AIIMS Patna or its authorized representative.
R-752 | Any proposed substitution or deviation affecting containment, safety, maintainability, performance, or design intent requires prior written approval from AIIMS Patna based on A&E Consultant recommendation. | 225 | 28.6(iv) | Mandatory | Obtain written approval from AIIMS Patna based on the technical recommendation of the A&E Consultant prior to executing any substitution or deviation affecting performance or containment. | Yes |  |  |  | No substitution, deviation or alternative affecting containment, safety, maintainability, performance or design intent shall be implemented without prior written approval of AIIMS Patna based on the technical recommendation of the A&E Consultant.
R-753 | The A&E Consultant must review the testing and commissioning program and take part in major multidisciplinary and integrated tests. | 226 | 28.7(iii) | Mandatory | Review testing and commissioning procedures/programs and participate in multidisciplinary and integrated testing affecting design performance. | Yes |  |  |  | The A&E Consultant shall review the testing and commissioning Program and participate in major multidisciplinary and integrated tests affecting design performance.
R-754 | The facility must complete thirty consecutive calendar days of integrated trial operation under operating conditions after testing and commissioning readiness confirmation. | 226 | 28.8(i) | Mandatory | Conduct thirty consecutive calendar days of integrated trial operation under intended operating conditions following readiness confirmation by PMC and A&E Consultant. | Yes |  |  |  | After successful completion of individual-system testing and commissioning and confirmation of readiness by the PMC and A&E Consultant, the Facility shall undergo thirty (30) consecutive calendar days of integrated trial operation under its intended operating conditions.
R-755 | Integrated trial operations must not utilize viable pathogenic, high-risk, or genetically engineered organisms, allowing only non-hazardous simulants and approved biological indicators. | 226 | 28.8(ii) | Mandatory | Ensure no viable pathogenic or high-risk organisms are used during trial operations, using only non-hazardous simulants or approved biological indicators as sanctioned by approved protocol. | Yes |  |  |  | The integrated trial shall be carried out without the use of any viable pathogenic, high-risk or genetically engineered organism. Non-hazardous simulants and approved biological indicators may be used only where required under an approved testing or validation protocol.
R-756 | The A&E Consultant must provide independent validation and certification support including reviewing requirements, facility readiness, coordinating technical inputs, participating in meetings, witnessing tests, reviewing findings/closure proposals, and assisting in compilation of the dossier. | 227 | 28.9(i) | Mandatory | Prepare/review validation requirements, review facility readiness, coordinate inputs, witness critical tests, review findings, and assist in compiling the final validation and certification dossier. | Yes |  |  |  | The A&E Consultant shall: (a) Prepare or review the validation and certification requirements, test matrix and acceptance criteria. (b) Review readiness of the Facility before commencement of independent validation. (c) Coordinate technical inputs required by the validating or certifying agency. (d) Participate in opening and closing meetings and witness critical validation tests where required. (e) Review validation findings and advise AIIMS Patna regarding their technical implications. (f) Review corrective-action proposals and verify design-related closure documents. (g) Assist in compilation of the final validation and certification dossier.
R-757 | The A&E Consultant's Biosafety Expert must review all validation findings affecting containment or biosafety performance and advise AIIMS Patna on closure. | 227 | 28.9(ii) | Mandatory | Review validation findings affecting containment/biosafety and advise AIIMS Patna on their satisfactory closure. | Yes |  |  |  | The A&E Consultant’s Biosafety Expert shall review all validation findings affecting containment or biosafety performance and advise AIIMS Patna on their satisfactory closure.
R-758 | No design change, material substitution, system modification, field alteration, or deviation from the approved Basis of Design can be implemented without documented review and written approval. | 227 | 28.10(iii) | Mandatory | Ensure documented review and written approval are obtained prior to implementing any design changes, material substitutions, or deviations from the approved Basis of Design. | Yes |  |  |  | No design change, material substitution, system modification, field alteration or deviation from the approved Basis of Design shall be implemented without documented review and written approval.
R-759 | Biosafety-critical non-conformities must remain open until closure is reviewed by the A&E Consultant's Biosafety Expert and accepted by AIIMS Patna. | 228 | 28.10(iv) | Mandatory | Submit biosafety-critical non-conformity closures for review by the Biosafety Expert and formal acceptance by AIIMS Patna before closing them. | Yes |  |  |  | Biosafety-critical non-conformities shall remain open until their closure has been reviewed by the A&E Consultant’s Biosafety Expert and accepted by AIIMS Patna.
R-760 | The A&E Consultant must submit construction-stage records and deliverables including site-visit reports, review comments, biosafety reports, registers, and completion reports. | 228 | 28.11 | Mandatory | Submit all applicable construction-stage records and deliverables such as site-visit reports, review comments, inspection reports, registers, testing/commissioning review reports, trial operation reports, validation assessments, and final reports. | Yes |  |  |  | The A&E Consultant shall submit, as applicable: (i) Site-visit and design-intent review reports. (ii) Technical review comments on shop drawings, material submissions, method statements and proposed substitutions. (iii) Biosafety-critical inspection reports prepared by its Biosafety Expert. (iv) Hold-point inspection and review records. (v) Updated risk, interface and design-decision registers. (vi) Testing and commissioning review reports. (vii) Integrated trial-operation review report. (viii) Validation-readiness assessment. (ix) Review of validation findings and corrective-action closure. (x) Final review of as-built drawings, O&M manuals and system dossiers. (xi) Certification-support documentation and final technical completion report.
R-761 | The involvement of the A&E Consultant’s Biosafety Expert in biosafety-critical reviews must continue until completion of testing, integrated trial operation, independent validation, certification support, and closure of observations. | 228 | 28.12(iv) | Mandatory | Ensure the continuous involvement of the Biosafety Expert across all biosafety-critical reviews through final certification support and closure of all biosafety-critical observations. | Yes |  |  |  | The mandatory involvement of the A&E Consultant’s Biosafety Expert in biosafety-critical reviews shall continue until completion of testing, integrated trial operation, independent validation, certification support and closure of all biosafety-critical observations.
R-762 | The A&E Consultant must coordinate training, operational-readiness documentation, handover, post-handover design support, close-out, and prepare a handover-takeover plan from the construction agency. | 229 | 29.1 | Mandatory | Coordinate training, operational-readiness documentation, final digital/technical handover, post-handover design support, and prepare a handover takeover plan from the construction agency. | Yes |  |  |  | The A&E Consultant shall coordinate the training, operational-readiness documentation, final technical and digital handover, post-handover design support and contractual close-out required for safe operation, maintenance, annual revalidation and continued compliance of the Facility. In other words, the A&E consultant shall have to prepare handover takeover plan also from construction agency also.
R-763 | The A&E Consultant must coordinate technical handover, explain design intent, prepare/review training and lifecycle documents, review as-built and testing records, and provide DLP design support. | 229 | 29.2(i) | Mandatory | Coordinate overall technical handover, explain engineering systems, review training/O&M/as-built/validation records, and provide design support during the Defect Liability Period. | Yes |  |  |  | The A&E Consultant shall coordinate the overall technical handover; explain the approved design intent and engineering systems; prepare or review facility-specific training and lifecycle- support documents; review the completeness and consistency of as- built, O&M, testing and validation records; and provide design-related support during the Defect Liability Period.
R-764 | The A&E Consultant's Biosafety Expert must lead or review all biosafety-critical training inputs, operational-safety modules, mock-drill protocols, readiness reviews, and closure of biosafety defects. | 229 | 29.2(ii) | Mandatory | Designate the Biosafety Expert to lead or review all biosafety-critical training modules, mock-drill protocols, readiness reviews, and defect closures. | Yes |  |  |  | The designated Biosafety Expert of the A&E Consultant shall lead or review all biosafety-critical training inputs, operational-safety modules, mock-drill protocols, biosafety-readiness reviews and closure of biosafety-critical defects or observations.
R-765 | Training must be delivered in two distinct stages: Pre-validation readiness training and Final operational and O&M training. | 230 | 29.3(i) | Mandatory | Deliver training across the specified two stages covering design intent, workflows, emergency modes, routine operation, maintenance, troubleshooting, calibration, and revalidation. | Yes |  |  |  | Training shall be delivered in the following two stages: (a) Pre-validation readiness training: Before formal validation, covering the approved design intent, containment zoning, laboratory workflows, pressure relationships, engineering controls, alarm philosophy, emergency modes, test readiness and mock-drill requirements. (b) Final operational and O&M training: After completion of commissioning and availability of substantially complete as-built and O&M information, but before final operational handover, covering routine operation, maintenance precautions, troubleshooting, calibration, annual revalidation and emergency shutdown and recovery procedures.
R-766 | Practical training demonstrations must be conducted without viable pathogenic, high-risk, or genetically engineered organisms, using approved non-hazardous simulants or indicators if required. | 230 | 29.3(iii) | Mandatory | Conduct practical training demonstrations strictly without viable pathogenic, high-risk, or genetically engineered organisms, using only approved non-hazardous simulants/indicators. | Yes |  |  |  | Practical demonstrations shall be conducted without viable pathogenic, high-risk or genetically engineered organisms. Approved non-hazardous simulants or indicators may be used where required under the approved training or validation protocol.
R-767 | The A&E Consultant must provide repeat training without additional professional fee if required due to incomplete delivery, material error in training content, or design changes attributable to the consultant. | 231 | 29.3(v) | Mandatory | Provide any required repeat training at no additional fee if caused by incomplete delivery, material error in content, or consultant-attributable design changes. | Yes |  |  |  | Any repeat training required due to incomplete delivery, material error in the training content or a design change attributable to the A&E Consultant shall be provided without additional professional fee.
R-768 | The A&E Consultant must coordinate, review, and submit a consolidated Operational-Readiness and Lifecycle-Support Dossier. | 231 | 29.4(i) | Mandatory | Coordinate, review, and submit the consolidated Operational-Readiness and Lifecycle-Support Dossier containing all final accepted documents required for validation, certification, operation, and revalidation. | Yes |  |  |  | The A&E Consultant shall coordinate, review and submit a consolidated Operational-Readiness and Lifecycle-Support Dossier comprising the final accepted documents required for validation, certification, operation, maintenance and annual revalidation of the Facility.
R-769 | All biosafety-critical portions of the operational-readiness dossier must be reviewed by the Biosafety Expert. | 232 | 29.4(iii) | Mandatory | Ensure the Biosafety Expert reviews all biosafety-critical portions of the dossier. | Yes |  |  |  | All biosafety-critical portions of the dossier shall be reviewed by the Biosafety Expert.
R-770 | The A&E Consultant must coordinate and submit an indexed, searchable, and usable final handover package showing verified as-built conditions. | 232 | 29.5(i) | Mandatory | Coordinate and submit a complete, indexed, searchable, and usable final handover package reflecting the verified as-built condition of the Facility. | Yes |  |  |  | The A&E Consultant shall coordinate and submit a complete, indexed, searchable and usable final handover package reflecting the verified as-built condition of the Facility.
R-771 | The A&E Consultant must review contractor as-built records for design consistency and integrate them into the final handover package. | 233 | 29.5(iii) | Mandatory | Review execution-based as-built records for coordination and consistency with approved designs and incorporate them into the final handover package. | Yes |  |  |  | The A&E Consultant shall review the records for coordination and consistency with the final approved design and incorporate them into the final handover package.
R-772 | Deliverables must be submitted in editable native and non-editable formats, as well as agreed interoperable formats, without withholding project data. | 233 | 29.5(iv) | Mandatory | Submit deliverables in editable native formats, corresponding non-editable formats, and agreed open/interoperable formats without withholding operational/maintenance data. | Yes |  |  |  | Deliverables shall be submitted in editable native formats and corresponding non-editable formats, together with agreed open or interoperable formats. The Consultant shall not be required to transfer its general corporate software licences or proprietary internal tools; however, no project data necessary for operation, maintenance, testing, revalidation or future modification shall be withheld on that ground.
R-773 | Prior to acceptance of the digital handover package, the A&E Consultant must demonstrate file integrity, revision consistency, searchability, and completeness. | 233 | 29.5(v) | Mandatory | Demonstrate that all files open without corruption, carry consistent revisions, provide searchable asset records linked to manuals, include complete folder indexes, and securely transfer credentials. | Yes |  |  |  | Before acceptance, the A&E Consultant shall demonstrate that: (a) All files open correctly and are free from corruption; (b) Drawings, models, registers and schedules carry consistent revision status; (c) Asset records are searchable and linked to applicable manuals and records; (d) Project folders, transmittals and document indexes are complete; (e) Project-specific credentials and access rights have been securely transferred; and (f) The digital package is reasonably usable for operation, maintenance, testing, annual revalidation and future modification.
R-774 | Any deficiency discovered during digital handover verification must be rectified before package acceptance. | 233 | 29.5(vi) | Mandatory | Correct all identified deficiencies prior to acceptance of the digital handover package. | Yes |  |  |  | Any deficiency identified during such verification shall be corrected before acceptance of the digital handover package.
R-775 | The A&E Consultant and Biosafety Expert must provide readiness recommendations prior to operational handover. | 234 | 29.6(ii) | Mandatory | Submit technical-readiness recommendations and documented biosafety-critical readiness recommendations. | Yes |  |  |  | The PMC shall verify physical and documentary completion. The A&E Consultant shall provide its technical-readiness recommendation, and the Biosafety Expert shall provide a documented recommendation on biosafety-critical readiness.
R-776 | The A&E Consultant must provide design clarification, root-cause review, and rectification reviews during the Defect Liability Period. | 234 | 29.7(i) | Mandatory | Provide technical support, design clarification, root-cause review, and rectification review for defects affecting design intent, containment, and system performance during the DLP. | Yes |  |  |  | During the Defect Liability Period of the Works Contract, the A&E Consultant shall provide design clarification, preliminary technical root-cause review and review of proposed rectification for defects affecting its design intent, containment, pressure cascade, HEPA systems, decontamination systems, utilities, monitoring, commissioning, validation or certification status etc.
R-777 | The A&E Consultant must review whether proposed defect rectifications match approved designs and required system performance. | 234 | 29.7(ii)(c) | Mandatory | Review contractor defect rectifications for compliance with approved design and system performance requirements. | Yes |  |  |  | The A&E Consultant shall review whether the proposed rectification is consistent with the approved design and required system performance and the error occurred and found in the work of contractor then such error shall not be due to design faultiness.
R-778 | The Biosafety Expert must review defects and rectifications affecting containment, biosafety, validation, or certification. | 234 | 29.7(ii)(d) | Mandatory | Have the Biosafety Expert review defects and rectifications that affect containment, biosafety, or certification status. | Yes |  |  |  | The Biosafety Expert shall review defects and rectifications affecting containment, biosafety, validation or certification status.
R-779 | The Consultant must meet specific response times for defect notifications based on severity. | 235 | 29.7(iii) | Mandatory | Provide an initial technical response within one working day and attend site within three working days for containment/life safety defects; respond within three working days for other design defects. | Yes |  |  |  | For a reported defect having an immediate or potential effect on containment or life safety, the Consultant shall provide an initial technical response within one working day and attend the site within three working days where site attendance is reasonably required. For other design-related defects, an initial written response shall be provided within three working days or within such other period recorded according to the nature and urgency of the defect.
R-780 | The Consultant must correct its own design errors/omissions and provide redesign, clarification, and revalidation support without additional fees. | 235 | 29.7(iv) | Mandatory | Rectify consultant-originated design errors and provide redesign and revalidation technical support at no additional fee. | Yes |  |  |  | The Consultant shall correct its own design error or omission and provide the related redesign, clarification, review and technical support for re-testing or revalidation without additional professional fee.
R-781 | The A&E Consultant and Biosafety Expert must participate in a consolidated performance review before DLP closure. | 235 | 29.7(vii) | Mandatory | Participate in the consolidated performance review and submit recommendations on outstanding design and biosafety matters prior to DLP closure. | Yes |  |  |  | Before closure of the Defect Liability Period, the A&E Consultant and its Biosafety Expert shall participate in a consolidated performance review and submit their recommendations on outstanding design- related and biosafety-critical matters.
R-782 | The Final Close-Out Dossier must distinctly categorize closed items, transferred actions, warranties, and surviving obligations. | 236 | 29.8(ii) | Mandatory | Submit a Final Close-Out Dossier identifying closed items, transferred actions, ongoing warranties, recertification actions, and surviving obligations. | Yes |  |  |  | The Final Close-Out Dossier shall clearly identify: (a) Items fully closed; (b) Items transferred to the Works Agency/Contractor, OEM, PMC or AIIMS Patna for continuing action; (c) Continuing warranty; (d) Annual revalidation and recertification actions; and (e) Obligations surviving completion of the Contract.
R-783 | Price bid must be submitted online only in the protected BOQ Excel file downloaded from CPPP without any alteration or modification to the file structure. | 238 | NOTE: IMPORTANT CPPP SUBMISSION REQUIREMENT | Submission logistics | Submit the price bid online using the unmodified protected BOQ Excel file downloaded from the CPP Portal, entering data only in permitted cells. | Yes |  |  |  | The price bid shall be submitted online only in the protected BOQ Excel file downloaded from the CPP Portal. The bidder shall enter data only in the permitted cells and shall not modify, replace, recreate, rename internally, delete, insert or alter any row, column, formula, worksheet, file structure or protected portion of the BOQ.
R-784 | Cover-2 must contain the duly filled and digitally signed BOQ Excel file. | 238 | 1.(i) | Submission logistics | Include the completed and digitally signed BOQ Excel file downloaded from CPPP in Cover-2. | Yes |  |  |  | Cover–2 shall contain the duly filled and digitally signed BOQ Excel file downloaded from the CPP Portal.
R-785 | Upload the Financial Bid Declaration in Cover-2 if a separate field is provided, and do not upload alternative price schedules or technical documents in Cover-2. | 238 | 1.(ii) | Submission logistics | Upload the prescribed Financial Bid Declaration in Cover-2 if provided on CPPP, and exclude any technical documents or alternative schedules from Cover-2. | Yes |  |  |  | Where the CPP Portal provides a separate upload field under the Financial Cover, the bidder shall also upload the Financial Bid Declaration prescribed in this Section. No alternative price schedule, technical document, brochure, condition or qualification shall be uploaded in Cover–2.
R-786 | No price or financial information shall be disclosed in Cover-1 (Technical Proposal). | 238 | 1.(iii) | Mandatory | Ensure no price, fee, rate, or financial implication is mentioned in Cover-1. | Yes |  |  |  | No price, rate, fee, percentage, financial implication or other financial information shall be disclosed in Cover–1 containing the Technical Proposal. Disclosure of material price information in Cover–1 shall render the Proposal liable to rejection.
R-787 | Download the BOQ from CPPP, fill bidder details and values in permitted cells, digitally sign, and upload in Cover-2 before the deadline. | 238 | 2.(i) | Submission logistics | Download, fill permitted cells, digitally sign, and upload the official BOQ Excel file into Cover-2 prior to the submission deadline. | Yes |  |  |  | The bidder shall download the BOQ file from the CPP Portal, enter the bidder name and the values in the permitted cells, digitally sign and upload the same BOQ file in Cover–2 before the bid submission deadline.
R-788 | Do not upload scanned PDFs, converted files, manual spreadsheets, or password-protected files in lieu of the prescribed BOQ Excel file. | 238 | 2.(ii) | Submission logistics | Upload only the prescribed BOQ Excel file, avoiding PDFs, converted formats, or password-protected sheets. | Yes |  |  |  | The bidder shall not upload a scanned PDF, converted file, manually prepared spreadsheet, password-protected file or any recreated version in place of the prescribed BOQ Excel file.
R-789 | Complete all mandatory editable fields in the BOQ without leaving any required field blank. | 238 | 2.(iii) | Submission logistics | Fill all mandatory fields, entering permitted notations/values where not applicable, without leaving any required field blank. | Yes |  |  |  | All mandatory editable fields shall be completed. Where a field is not applicable, the bidder shall enter the value or notation permitted by the BOQ instructions; no required field shall be left blank.
R-790 | Verify successful uploading and freeze the bid on the CPP Portal. | 238 | 2.(iv) | Submission logistics | Check for successful upload and freeze the bid on the CPP Portal to avoid it being deemed incomplete or invalid. | Yes |  |  |  | The bidder shall verify successful uploading and shall freeze the Bid on the CPP Portal. An uploaded but unfrozen Bid shall be treated in accordance with the Portal rules as incomplete/invalid.
R-791 | Quote a single firm lump-sum consultancy fee exclusive of GST but inclusive of all other costs, taxes, duties, and expenses. | 238 | 3. | Mandatory | Provide one comprehensive lump-sum fee exclusive of GST and inclusive of all other project costs and overheads. | Yes |  |  |  | The Bidder shall quote one firm and comprehensive Lump-Sum Professional Consultancy Fee, exclusive of GST but inclusive of all other costs, taxes, duties, levies, insurance, licences, overheads, profit and incidental expenses, for complete performance of the assignment in accordance with the RFP.
R-792 | Financial Proposal must be quoted in Indian Rupees only. | 239 | 5.(i) | Mandatory | Quote all fees in INR. | Yes |  |  |  | The Financial Proposal shall be quoted in Indian Rupees only.
R-793 | Basic Lump-Sum Consultancy Fee must remain firm and fixed without escalation throughout the contract. | 239 | 5.(ii) | Mandatory | Maintain firm and fixed pricing without claiming escalation for manpower, travel, inflation, or forex variations. | Yes |  |  |  | The Basic Lump-Sum Consultancy Fee shall remain firm and fixed throughout the Contract, including any period reasonably required for completion of the Consultant’s obligations up to the certification-support stage. No escalation shall be admissible on account of manpower cost, travel cost, inflation, foreign exchange variation, software cost, overheads or any other reason.
R-794 | Financial Proposal must remain valid for the same Bid Validity Period as the Technical Proposal. | 239 | 5.(iii) | Mandatory | Ensure financial bid validity matches the technical bid validity period. | Yes |  |  |  | The Financial Proposal shall remain valid for the same Bid Validity Period as the Technical Proposal.
R-795 | Quote fee exclusive of GST and specify the 6-digit SAC code, GST type, GST rate, and GST amount in the BOQ. | 239 | 6.(i) | Mandatory | Enter the fee excluding GST, and separately state the applicable 6-digit SAC code, GST type, rate, and amount in the BOQ. | Yes |  |  |  | The bidder shall quote the Basic Lump-Sum Consultancy Fee exclusive of GST and shall separately indicate the applicable six-digit SAC Code, GST type, GST rate and GST amount in the BOQ.
R-796 | Determine and quote the exact applicable six-digit SAC Code. | 239 | 6.(ii) | Mandatory | Identify and state the correct six-digit SAC Code in the bid. | Yes |  |  |  | The bidder shall determine and quote the exact six-digit SAC Code applicable and shall be responsible for correctness of the classification and rate.
R-797 | State the GST type as CGST plus SGST or IGST according to place-of-supply rules. | 239 | 6.(iii) | Mandatory | Specify whether CGST+SGST or IGST applies based on place-of-supply provisions. | Yes |  |  |  | The GST type shall be stated as CGST plus SGST or IGST, as applicable under the place-of-supply provisions.
R-798 | Account for all admissible Input Tax Credit when determining the lump-sum consultancy fee. | 239 | 6.(iv) | Mandatory | Factor in Input Tax Credit while calculating the quoted Basic Lump-Sum Consultancy Fee. | Yes |  |  |  | The bidder shall take into account all admissible Input Tax Credit while determining the Basic Lump-Sum Consultancy Fee.
R-799 | Consultancy fee must not be quoted as NIL or zero. | 240 | 7.(iii) | Mandatory | Quote a positive monetary fee; do not enter NIL or zero. | Yes |  |  |  | The Basic Lump-Sum Consultancy Fee shall not be quoted as NIL or zero. A NIL or zero professional fee shall be treated as non-responsive.
R-800 | Do not quote separate rates for individual milestones. | 240 | 7.(iv) | Mandatory | Provide a single lump-sum fee rather than separate individual milestone rates. | Yes |  |  |  | No separate rate shall be quoted for individual milestones. Payments shall be released according to the milestone percentages prescribed by AIIMS Patna in the Payment Schedule.
R-801 | Do not include conditional discounts, rebates, alternative prices, suo-motu discounts, front-loaded prices, or payment-linked qualifications. | 240 | 7.(vi) | Mandatory | Quote unconditional prices without discounts, alternative quotes, or front-loading. | Yes |  |  |  | No conditional discount, rebate, alternative price, suo-motu discount, front- loaded price or payment-linked qualification shall be quoted.
R-802 | Price must not be conditional upon advance payments, revised milestones, minimum construction values, or visit/revision limitations. | 240 | 7.(vii) | Mandatory | Ensure the financial proposal is not contingent upon advance payment or any conditions departing from the RFP. | Yes |  |  |  | The bidder shall not make its price conditional upon advance payment, revised milestone allocation, minimum construction value, and restriction on revisions, limitation of visits or any condition inconsistent with the RFP.
R-803 | Cover-2 must not contain any new technical assumptions, deviations, exclusions, or limitations. | 240 | 7.(ix) | Mandatory | Do not introduce technical assumptions, exclusions, or reservations in Cover-2. | Yes |  |  |  | Cover–2 shall not introduce any new technical assumption, deviation, exclusion or limitation. Any such condition shall not bind AIIMS Patna and may render the Financial Proposal non-responsive.
R-804 | Consider all corrigenda, addenda, and pre-bid clarifications issued on CPPP prior to submitting and freezing the Financial Proposal. | 240 | 7.(x) | Mandatory | Account for all published corrigenda, addenda, and clarifications before finalizing and freezing the bid. | Yes |  |  |  | The bidder shall consider all corrigenda, addenda and pre-bid clarifications issued on the CPP Portal before submitting and freezing the Financial Proposal.
R-805 | In case of resubmission before deadline, ensure both latest Technical and Financial Covers are uploaded and frozen. | 240 | 7.(xi) | Submission logistics | Re-upload and freeze both covers properly if resubmitting the bid prior to the deadline. | Yes |  |  |  | Resubmission of the Bid before the submission deadline shall require the bidder to ensure that the latest Technical and Financial Covers are correctly uploaded and frozen. Only the last valid submission recorded by the Portal shall be considered.
R-806 | All forms must be completed in English, signed and dated by the authorized signatory, and uploaded on CPPP with supporting documents. | 242 | A. General instructions: (i) | Submission logistics | Complete all forms in English, get them signed and dated by the authorized signatory, and upload them with supporting documents in the applicable CPPP cover. | Yes |  |  |  | All forms shall be completed in English, signed and dated by the authorized signatory, and uploaded in the applicable CPPP cover with supporting documents.
R-807 | Annexures 1 to 16 must not contain any financial information, and Annexure 17 must be uploaded only in the Financial Cover with the BOQ. | 242 | A. General instructions: (ii) | Mandatory | Ensure no financial information is included in Annexures 1 to 16, and upload Annexure 17 strictly within the Financial Cover alongside the CPPP BOQ. | Yes |  |  |  | No financial information shall appear in Annexures 1 to 16. Annexure 17 shall be uploaded only in the Financial Cover together with the CPPP BOQ.
R-808 | If a form is not applicable, the bidder must state 'Not Applicable' along with a brief explanation. | 242 | A. General instructions: (iii) | Mandatory | Mark non-applicable forms as 'Not Applicable' with a brief reason rather than leaving them blank. | Yes |  |  |  | Where a form is not applicable, the Bidder shall write "Not Applicable" with a brief reason. Blank or omitted essential forms may render the Bid non-responsive.
R-809 | Supporting documents must be self-attested, legible, and cross-referenced with document name and PDF page number. | 242 | A. General instructions: (iv) | Submission logistics | Self-attest all supporting documents, ensure legibility, and cross-reference them by document name and PDF page number. | Yes |  |  |  | Supporting documents shall be self-attested, legible and cross-referenced by document name and PDF page number.
R-810 | Prescribed fields of repeatable sheets must not be deleted or materially altered. | 242 | A. General instructions: (vii) | Mandatory | Maintain all prescribed fields without deletion or material alteration when copying repeatable sheets. | Yes |  |  |  | A repeatable sheet may be copied as required, but its prescribed fields shall not be deleted or materially altered.
R-811 | Annexure-1 (Bid Covering Letter and Unconditional Acceptance) must be submitted on the bidder's letterhead. | 243 | ANNEXURE-1 | Submission logistics | Print, execute, and submit the Annexure-1 Bid Covering Letter on the Bidder's official letterhead. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead)
R-812 | The Technical Proposal must exclude all price, fee, rate, or financial quotes. | 243 | ANNEXURE-1, Part A- 8 | Mandatory | Ensure no price or financial quotes are included in the Technical Proposal, and submit financial proposals separately in the CPPP Financial Cover. | Yes |  |  |  | The Technical Proposal contains no price, fee, rate or financial quote. The Financial Proposal has been submitted separately in the prescribed CPPP Financial Cover.
R-813 | All services, designs, calculations, specifications, and outputs must comply with the DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024. | 244 | ANNEXURE-1, Part B - (a) | Mandatory | Provide an undertaking and ensure full compliance with DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024 for all deliverables and services. | Yes |  |  |  | We undertake that the Proposal and all services, designs, calculations, specifications, BOQ provisions, tender documents, reviews and certification- support outputs shall comply with the DBT-ICMR National Guidelines for BSL-3 Laboratory, 2024, as amended/updated from time to time, and the order of precedence stated in the RFP.
R-814 | In case of a Joint Venture, Part A and Part C must be submitted by each member, while Part B and Part D must be submitted jointly by the Lead Member. | 245 | ANNEXURE-2, Note | Submission logistics | Submit Part A and Part C separately for each JV member, and have the Lead Member submit Part B and Part D jointly. | Yes |  |  |  | Note: In case of a JV, Part A and Part C shall be submitted separately by each member. Part B and Part D shall be submitted jointly by the Lead Member, identifying the Lead Member, Authorised Representative, and Lead Architect.
R-815 | The Lead Architect's Council of Architecture registration must be valid on the Bid Due Date and maintained throughout the period of professional responsibility. | 246 | ANNEXURE-2, Part D (a) | Eligibility criteria | Confirm and maintain a valid Council of Architecture registration for the Lead Architect on the Bid Due Date and throughout the contract. | Yes |  |  |  | (a) The undersigned Lead Architect confirms that the above registration is valid on the Bid Due Date and shall be maintained as required throughout the period of professional responsibility under the Contract.
R-816 | The Lead Architect cannot be substituted without prior written approval of AIIMS Patna. | 246 | ANNEXURE-2, Part D | Mandatory | Do not substitute the Lead Architect without obtaining prior written approval from AIIMS Patna in accordance with the RFP. | Yes |  |  |  | The Lead Architect shall not be substituted except in accordance with the RFP and with prior written approval of AIIMS Patna.
R-817 | Bidder must cite the exact supporting document name and PDF page number in the Annexure-3 checklist; unindexed documents will not establish compliance. | 247 | ANNEXURE-3 | Submission logistics | Submit Annexure-3 on the Bidder's letterhead citing the exact supporting document and PDF page numbers. | Yes |  |  |  | The Bidder shall cite the exact supporting document and PDF page number. Mere submission of an unindexed document does not establish compliance.
R-818 | Qualifying experience requirement of 2 BSL-3/ABSL-3 or 1 BSL-4/ABSL-4 project in the last 7 financial years. | 247 | ANNEXURE-3, Item 8 | Eligibility criteria | Demonstrate qualifying experience of completing 2 BSL-3/ABSL-3 or 1 BSL-4/ABSL-4 projects in the last 7 financial years. | Yes |  |  |  | Qualifying experience: 2 BSL-3/ABSL-3 or 1 BSL-4/ABSL-4 in last 7 financial years
R-819 | All prescribed Annexures 1 through 16 must be submitted in the Technical Cover. | 247 | ANNEXURE-3, Item 17 | Submission logistics | Submit all prescribed Annexures 1-16 inside the Technical Cover. | Yes |  |  |  | All prescribed Annexures 1-16 submitted in Technical Cover
R-820 | The Bidder must not be under any subsisting debarment, banning, or blacklisting order on the Bid Due Date, and must disclose any such orders from the preceding five years in Annexure-5. | 248 | Part B, Item 2 | Eligibility criteria | Declare absence of subsisting debarment/banning/blacklisting and disclose any relevant orders from the past five years in Annexure-5. | Yes |  |  |  | The Bidder is not subject on the Bid Due Date to a subsisting debarment, banning or blacklisting order applicable to this procurement by a competent Government authority. All relevant orders during the preceding five years are disclosed in Annexure-5.
R-821 | Compliance with reciprocity and Rule 144(xi) land-border procurement restrictions, including submission of Appendix-J and registration if required. | 248 | Part B, Item 6 | Mandatory | Comply with Rule 144(xi) / land-border restrictions and submit Appendix-J alongside mandatory registration where required. | Yes |  |  |  | The Bidder complies with applicable reciprocity and Rule 144(xi) / land-border procurement restrictions and has submitted Appendix-J and the prescribed registration, wherever required.
R-822 | Turnover from Architectural & Engineering Consultancy Services must be certified by a Chartered Accountant, based on audited records and excluding unrelated revenue. | 249 | ANNEXURE-4, Part B | Eligibility criteria | Obtain and submit a CA certificate with UDIN certifying A&E consultancy turnover for FY 2022-23, 2023-24, and 2024-25, excluding construction, supply, and trading revenue. | Yes |  |  |  | The figures above are derived from audited records and exclude construction, supply, trading and unrelated business revenue. This certificate is issued for submission to AIIMS Patna under the subject RFP.
R-823 | For Joint Ventures, the Lead Member must meet at least 51%, the other member at least 30%, and the combined JV at least 100% of the minimum financial eligibility threshold. | 250 | Part C | Eligibility criteria | Ensure and certify that the Lead Member meets at least 51%, the other member meets at least 30%, and the combined JV meets at least 100% of the financial requirement. | Yes |  |  |  | the Lead Member independently meets at least fifty-one percent (51%) of the minimum financial eligibility prescribed for a single applicant, the other member independently meets at least thirty percent (30%), and the combined JV meets not less than one hundred percent (100%) of the prescribed threshold.
R-824 | Bidder must disclose material litigation, arbitration, contract performance issues, and pending matters during the preceding five years on letterhead. | 251 | ANNEXURE-5 | Mandatory | Submit Annexure-5 on the Bidder's Letterhead detailing material and pending matters from the last five years. | Yes |  |  |  | Disclose material matters during the preceding five years and all currently pending matters that may reasonably affect eligibility, integrity, financial capacity, availability of Key Personnel or performance of this Assignment.
R-825 | Disclose all investigation, criminal, and integrity-related proceedings concerning the Bidder, JV member, key management, or proposed Team Leader over the past five years or currently pending. | 251 | ANNEXURE-5, Part D | Mandatory | Disclose any criminal, investigation, or integrity proceedings involving the entity, partners, controlling directors, or Team Leader from the last five years or currently pending. | Yes |  |  |  | Disclose proceedings involving the Bidder, a JV member, proprietor, partner, controlling director or proposed Team Leader during the preceding five years and all matters currently pending, where the subject has a material nexus with professional integrity, public procurement, fraud, corruption, safety, regulatory compliance or performance of consultancy services.
R-826 | Annexure-6 (Firm BSL-3/BSL-4 Experience, Client References, Case Studies and Client Certificate) must be submitted on the bidder's letterhead. | 253 | ANNEXURE-6 | Mandatory | Submit Annexure-6 on the bidder's letterhead. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead)
R-827 | Part C, Part D, and Part E of Annexure-6 must be submitted separately for each listed project, supported by prescribed documentary evidence. | 253 | ANNEXURE-6 | Mandatory | Submit Part C, Part D, and Part E separately for each project claimed for eligibility or technical scoring, along with supporting documents. | Yes |  |  |  | Part C, Part D, and Part E shall be submitted separately for each listed project. All claims shall be supported by the documentary evidence prescribed in the RFP.
R-828 | Bidder must claim minimum eligibility through either two BSL-3/ABSL-3 assignments or one BSL-4/ABSL-4 assignment. | 253 | ANNEXURE-6, Part A | Eligibility criteria | Select and furnish project details under Part A for either two BSL-3/ABSL-3 assignments or one BSL-4/ABSL-4 assignment. | Yes |  |  |  | Eligibility route claimed: [ ] Two BSL-3/ABSL-3 assignments; or [ ] One BSL-4/ABSL-4 assignment
R-829 | For private-client assignments, bidders must submit invoices, payment proof, and applicable TDS/Form 26AS/AIS evidence. | 254 | ANNEXURE-6, Part D | Mandatory | Enclose invoice(s), proof of payment, and applicable TDS/Form 26AS/AIS evidence for private-client projects. | Yes |  |  |  | For private-client assignment: invoice(s), payment proof and applicable TDS/Form 26AS/AIS evidence etc
R-830 | A Client Past Performance Certificate must be submitted for each project relied upon for eligibility or technical scoring, issued on the client institution's letterhead and signed by an authorized officer. | 255 | ANNEXURE-6, Part E | Mandatory | Obtain and submit a completed Part E performance certificate on the client institution's letterhead signed by an authorized client officer for each claimed project. | Yes |  |  |  | (Repeat for each project relied upon for eligibility or technical scoring. To be issued on the Client Institution's letterhead and signed by an authorised officer.)
R-831 | Bidders must produce original or certified copies of submitted documents and facilitate verification within the timeframe stipulated by AIIMS Patna. | 256 | ANNEXURE-6, Part F | Mandatory | Produce original or certified copies and facilitate verification upon request within the time allowed by AIIMS Patna. | Yes |  |  |  | (e) We shall produce originals/certified copies and facilitate verification within the time allowed by AIIMS Patna.
R-832 | Bidder must submit Annexure-7 (Key Personnel Schedule, Organisation Chart and Deployment Commitment) on the Bidder's letterhead. | 257 | ANNEXURE-7 | Submission logistics | Submit the completed Annexure-7 schedule on the Bidder's Letterhead. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead)
R-833 | The Laboratory Equipment Planning and Integration Expert is mandatory in the bidder's proposed team structure. | 257 | ANNEXURE-7 | Mandatory | Include the Laboratory Equipment Planning and Integration Expert in the proposed key personnel team structure. | Yes |  |  |  | The Laboratory Equipment Planning and Integration Expert is mandatory in the proposed team structure.
R-834 | Named Key Personnel must personally perform their assigned roles and remain available for committed inputs, meetings, reviews, and site visits. | 258 | Deployment Undertaking | Mandatory | Ensure all named Key Personnel personally execute their roles and remain available as committed. | Yes |  |  |  | (a) The named Key Personnel shall personally perform the assigned role and shall remain available for the committed input, meetings, reviews and site visits.
R-835 | No Key Personnel substitution is permitted without prior written approval from AIIMS Patna and an equal or better replacement supported by complete evidence. | 258 | Deployment Undertaking | Mandatory | Obtain prior written approval from AIIMS Patna and submit complete supporting evidence of equal or better qualifications before substituting any Key Personnel. | Yes |  |  |  | (b) No substitution shall be made without prior written approval of AIIMS Patna and an equal or better replacement supported by complete evidence.
R-836 | Key Personnel must be on regular payroll/rolls (except for Biosafety Expert and expressly permitted specialist sub-consultants), with employment or association verified through Part B and cross-referenced to Annexures-8 and 9. | 258 | Deployment Undertaking | Eligibility criteria | Establish regular payroll/roll status for proposed key personnel (or permitted association for allowed specialists) and cross-reference supporting certificates and agreements to Annexures-8 and 9. | Yes |  |  |  | (e) The Bidder shall establish the employment or permitted association status of every proposed Key Person through Part B below. Regular payroll/roll status is mandatory except for the Biosafety Expert and other specialist sub-consultants expressly permitted under the RFP. The supporting certificate and agreement/commitment evidence shall be cross-referenced to Annexures-8 and 9, as applicable.
R-837 | Part B Employment / Association Verification Certificate must be certified by a Chartered Accountant or authorised HR signatory of the employing entity, referencing binding agreements for external specialists. | 258 | Part B | Mandatory | Have the Chartered Accountant or authorised HR signatory certify the Part B certificate and reference binding agreements and commitments for external specialists. | Yes |  |  |  | (To be certified by the Chartered Accountant/authorised HR signatory of the employing entity; for a permitted external specialist, the binding agreement and commitment shall be referenced.)
R-838 | The Curriculum Vitae form (Annexure-8) must be submitted separately for each proposed Key Expert and signed by both the Expert and the Bidder. | 260 | ANNEXURE-8 | Submission logistics | Repeat the Annexure-8 form for every proposed Key Expert and ensure each CV is signed by both the expert and the bidder. | Yes |  |  |  | (Repeat this form separately for every proposed Key Expert; to be signed by the Expert and the Bidder)
R-839 | Each Key Expert must sign a declaration certifying CV accuracy, consent to be proposed, availability for committed input, and undertaking to disclose conflicts of interest or availability changes. | 261 | Expert Declaration | Mandatory | Have each proposed expert sign the declaration confirming qualifications, consent, availability, and obligation to disclose availability changes or conflicts. | Yes |  |  |  | I certify that this CV accurately describes my qualifications and experience; that I have consented to be proposed for the stated position; that I am available for the committed input; and that I shall promptly disclose any change affecting my availability or conflict of interest.
R-840 | Biosafety Expert / Sub-Consultant Commitment and Participation Plan must be jointly signed by the bidder and the named biosafety expert with team details. | 262 | ANNEXURE-9 | Mandatory | Jointly sign Annexure-9 with the named Biosafety Expert and provide details of the team. | Yes |  |  |  | (To be jointly signed by the Bidder and the named Biosafety Expert with details of team)
R-841 | Consultant must arrange additional physical visits of the Biosafety Expert as part of the accepted lump-sum fee if material non-conformities remain unresolved or if validation and certification occur on separate dates. | 262 | ANNEXURE-9, Part B | Mandatory | Provide required additional physical visits by the Biosafety Expert at no additional cost if unresolved non-conformities or split validation/certification dates arise. | Yes |  |  |  | If material non- conformities remain unresolved, or if validation and the competent authority's certification inspection occur on separate dates and AIIMS Patna reasonably requires physical participation, the Consultant shall arrange the necessary additional physical visit(s) of the Biosafety Expert as part of the accepted lump-sum fee.
R-842 | The Biosafety Expert must independently review all biosafety-critical drawings, calculations, specifications, BOQ provisions, commissioning plans, validation plans, and certification-support documents. | 262 | ANNEXURE-9, Part C(a) | Mandatory | Ensure the Biosafety Expert independently reviews all specified biosafety-critical project documents and submissions. | Yes |  |  |  | (a) The Expert shall independently review all biosafety-critical drawings, calculations, specifications, BOQ provisions, commissioning plans, validation plans and certification-support documents.
R-843 | A written Review Comment Form must accompany each deliverable, and the bidder must submit an Action Taken Report detailing comments. | 262 | ANNEXURE-9, Part C(b) | Mandatory | Submit a written Review Comment Form with each deliverable and an Action Taken Report identifying incorporated, pending, and technically disagreed comments. | Yes |  |  |  | (b) A written Review Comment Form shall accompany each relevant deliverable. The Bidder shall submit an Action Taken Report identifying incorporated, pending and technically disagreed comments.
R-844 | Minutes of every biosafety-critical workshop, site visit, and review meeting must be prepared within three working days and co-signed by the participating named Expert. | 262 | ANNEXURE-9, Part C(c) | Mandatory | Prepare and submit meeting minutes within three working days, co-signed by the participating named Biosafety Expert. | Yes |  |  |  | (c) Minutes of every biosafety-critical workshop, site visit and review meeting shall be prepared within three working days and co-signed by the named Expert who participated.
R-845 | The Biosafety Expert must meet prescribed turnaround times and cannot be replaced without prior approval and an equal or better substitute. | 263 | ANNEXURE-9, Part C(e) | Mandatory | Comply with review turnaround times and obtain prior approval with an equal or better substitute before replacing the Expert. | Yes |  |  |  | (e) The Expert shall meet the review turnaround time prescribed in the RFP and shall not be replaced without prior approval and an equal or better substitute.
R-846 | No biosafety advice, warning, dissent, or non-compliance observation shall be suppressed, diluted, or withheld from AIIMS Patna. | 263 | ANNEXURE-9, Part C(f) | Mandatory | Disclose all biosafety advice, warnings, dissents, and non-compliance observations transparently to AIIMS Patna. | Yes |  |  |  | (f) No biosafety advice, warning, dissent or non-compliance observation shall be suppressed, diluted or withheld from AIIMS Patna.
R-847 | No material change in the engagement, named Expert, scope, or availability shall be made without prior written approval of AIIMS Patna. | 264 | ANNEXURE-9, Part D(d) | Mandatory | Obtain prior written approval from AIIMS Patna before making any material change to the Biosafety Expert engagement, named personnel, scope, or availability. | Yes |  |  |  | (d) No material change in the engagement, named Expert, scope or availability shall be made without prior written approval of AIIMS Patna.
R-848 | Project Understanding and Preliminary Need Assessment must be submitted on bidder's letterhead, limited to maximum 5 A4 pages (excluding one optional concept diagram), project-specific, and not reproducing the RFP verbatim. | 265 | ANNEXURE-10 | Submission logistics | Prepare and submit Annexure-10 on bidder's letterhead within the 5-page limit with project-specific content. | Yes |  |  |  | Note: Maximum five A4 pages excluding one optional concept diagram. The submission shall be project-specific and shall not reproduce the RFP verbatim.
R-849 | The Bidder must cite its method, principal output, and responsible expert in the Technical Approach, Design Philosophy and Critical Compliance Matrix; generic statements without approach or output may be disregarded. | 266 | ANNEXURE-11 | Evaluation criteria | Submit Annexure-11 on bidder's letterhead detailing proposed approach, principal deliverable/evidence, and experts involved, avoiding generic 'will comply' statements. | Yes |  |  |  | The Bidder shall cite its method, principal output and responsible expert. Generic statements such as "will comply" without an approach or output may be disregarded during technical evaluation.
R-850 | Phase-I completion obligation is Day 60 from T0, and the accepted work program shall form part of the Contract. | 268 | ANNEXURE-12 | Mandatory | Submit the Detailed Work Program and Design Delivery Schedule on the Bidder's Letterhead complying with the Phase-I Day 60 completion obligation. | Yes |  |  |  | The official Phase-I completion obligation is Day 60 from T0. Day 61-Day 75 is not an extension and may be used only for exceptional consolidated comment closure approved in writing by AIIMS Patna. The accepted program shall form part of the Contract.
R-851 | The bidder must explicitly confirm completion of Phase-I by Day 60 with all reviews and expert inputs included. | 268 | ANNEXURE-12 | Mandatory | Include the formal confirmation statement in Annexure-12 that Phase-I shall be completed by Day 60. | Yes |  |  |  | Bidder Confirmation: Phase-I shall be completed by Day 60 with all reviews and expert inputs included.
R-852 | The Project Management, Expert Deployment, Site Visit, Meeting and Record Management Plan must be submitted on bidder letterhead with the technical bid. | 269 | ANNEXURE-13 | Submission logistics | Submit Annexure-13 on the Bidder's Letterhead as part of the technical bid submission. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead and submitted with technical bid)
R-853 | The Joint Site Visit, Site Understanding and Design-Readiness Declaration must be submitted on bidder letterhead and jointly signed by the Authorised Signatory, Lead Architect, and named Biosafety Expert. | 269 | ANNEXURE-13 (Part A) | Mandatory | Execute and submit Part A on the Bidder's Letterhead with joint signatures of the Authorised Signatory, Lead Architect, and named Biosafety Expert. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead and jointly signed by the Authorised Signatory, Lead Architect and named Biosafety Expert)
R-854 | No additional professional-fee claims will be accepted for conditions reasonably visible during site inspection or disclosed in the RFP, and any concealed conditions or discrepancies must be promptly reported. | 269 | ANNEXURE-13 (Part A, Clause d) | Mandatory | Jointly declare that no extra fee claims will be made for visible site conditions and promptly report concealed conditions/discrepancies along with disclosing any bid-stage qualification. | Yes |  |  |  | No additional professional-fee claim shall arise from failure to observe a condition reasonably visible during the Site Visit or disclosed in the RFP. Concealed conditions or material discrepancies subsequently identified shall be promptly reported with their technical, cost, schedule and biosafety implications; any bid-stage qualification shall be disclosed.
R-855 | Annexure-14 must be submitted on the Bidder's Letterhead, restricted to a maximum of six pages excluding supporting certificates, and must detail project-specific controls rather than general policy statements. | 271 | ANNEXURE-14 | Submission logistics | Submit Annexure-14 on bidder's letterhead within the six-page limit (excluding certificates) filled with project-specific controls. | Yes |  |  |  | Note: Maximum six pages excluding supporting certificates. Complete the matrix with project-specific controls, not general company policy statements.
R-856 | Disclose any third-party licence, specialist association, or analytical service relied upon for technical infrastructure, software, and analytical capabilities. | 272 | Part C | Mandatory | Disclose all third-party licences, specialist associations, or analytical services relied upon and ensure resources remain available for the assignment. | Yes |  |  |  | Any third-party licence, specialist association or analytical service relied upon shall be disclosed and shall not dilute the Consultant's responsibility for accuracy, coordination, confidentiality or timely delivery.
R-857 | Submit the Construction, Testing, Commissioning, Validation, Certification and Handover Support Plan (Annexure-15) on the bidder's letterhead. | 273 | ANNEXURE-15 | Mandatory | Complete and submit Annexure-15 on the Bidder's Letterhead detailing the A&E Consultant's technical-support role and deliverables. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead)
R-858 | Submit the Deviations, Assumptions and Optimisation Statement (Annexure-16) on bidder's letterhead, writing 'NIL - No Deviation or Qualification' if no deviations are proposed. | 274 | ANNEXURE-16 | Mandatory | Submit Annexure-16 on letterhead; state 'NIL - No Deviation or Qualification' and sign if no qualification or deviation is proposed. | Yes |  |  |  | Every Bidder shall submit this form. If no matter is proposed, write "NIL - No Deviation or Qualification" and sign.
R-859 | Upload the Financial Proposal Undertaking and CPPP BOQ Confirmation (Annexure-17) strictly in the Financial Cover and state no price in the Technical Cover. | 275 | ANNEXURE-17 | Submission logistics | Upload Annexure-17 only in the Financial Cover, ensuring no pricing details are included in the Technical Cover. | Yes |  |  |  | (To be uploaded only in the Financial Cover; no price shall be stated in the Technical Cover)
R-860 | Enter lump-sum Professional Consultancy Fee in INR solely in the prescribed CPPP BOQ / Financial Proposal format. | 275 | ANNEXURE-17 | Submission logistics | Quote lump-sum fee exclusively in the prescribed CPPP BOQ format on the portal. | Yes |  |  |  | We have entered our lump-sum Professional Consultancy Fee (in INR) only in the prescribed CPPP BOQ / Financial Proposal format. The portal BOQ shall prevail for price entry and financial evaluation.
R-861 | Submit separate standard appendices only where applicable or expressly required by the RFP Data Sheet. | 276 | Separate Standard Appendices | Submission logistics | Submit standard appendices (Appendices A through H) only when applicable or explicitly mandated by the RFP Data Sheet. | Yes |  |  |  | They shall be submitted only where applicable or expressly required by the RFP Data Sheet.
R-862 | Bidders proposing to attend the Pre-Bid Conference must submit an authorisation letter prior to the conference. | 277 | APPENDIX-A | Submission logistics | Submit the pre-bid conference authorisation letter before the conference if attendance is proposed. | Yes |  |  |  | To be submitted before the Pre-Bid Conference, where attendance is proposed
R-863 | The Power of Attorney for Authorised Signatory must be executed on appropriate stamp paper and notarised where applicable. | 278 | APPENDIX-B | Mandatory | Execute the Power of Attorney on appropriate stamp paper and obtain notarisation where applicable. | Yes |  |  |  | (To be executed on appropriate stamp paper / notarised where applicable)
R-864 | Where a proposal is submitted by a Joint Venture, the JV Agreement and Power of Attorney package must be executed on appropriate stamp paper and registered/notarised where required by applicable law. | 279 | APPENDIX-C | Mandatory | Execute the JV Agreement and Power of Attorney package on appropriate stamp paper and register or notarise where required. | Yes |  |  |  | (Applicable only where the Proposal is submitted by a Joint Venture; to be executed on appropriate stamp paper and registered/notarised where required by applicable law.)
R-865 | JV member allocation of participation share, scope, experts, deliverables, and fee distribution must be genuine and proportionate, and token participation is barred. | 279 | Clause 3 | Eligibility criteria | Ensure genuine, proportionate, and consistent allocation across members in Schedule C-1 without token participation. | Yes |  |  |  | The allocation shall be genuine, proportionate and consistent; token participation is prohibited.
R-866 | Each member of the Joint Venture must be jointly and severally liable to AIIMS Patna for the proposal, professional services, defaults, damages, corrections, recoveries, and complete contract performance. | 279 | Clause 4 | Mandatory | Agree to joint and several liability of all JV members to AIIMS Patna irrespective of internal scope allocation. | Yes |  |  |  | Each Member is jointly and severally liable to AIIMS Patna for the Proposal, all obligations, professional services, defaults, damages, corrections, recoveries and complete performance of the Contract, irrespective of internal allocation.
R-867 | Prior written approval from AIIMS Patna is mandatory for any change in JV composition, Lead Member, participation share, assigned scope, key experts, or responsibility allocation. | 279 | Clause 6 | Mandatory | Do not alter JV composition, Lead Member, share, scope, or key experts without prior written approval from AIIMS Patna. | Yes |  |  |  | No change in composition, Lead Member, participation share, assigned scope, key experts or responsibility allocation shall be made without prior written approval of AIIMS Patna.
R-868 | Each JV member must attach a Board Resolution, partners' resolution, or equivalent constitutional authorisation approving participation, the agreement, joint and several liability, allocation, and execution of the Power of Attorney. | 281 | Part C | Mandatory | Attach constitutional authorisation (such as Board or partners' resolution) from each JV member approving JV participation, the agreement, joint and several liability, allocation, and POA execution. | Yes |  |  |  | Each Member shall attach its Board Resolution, partners’ resolution or equivalent constitutional authorisation approving: (i) participation in the JV; (ii) this Agreement; (iii) joint and several liability; (iv) the participation/scope/fee allocation; and (v) execution of the Power of Attorney above.
R-869 | Bid Security Declaration must be submitted on Rs 100/- Non-Judicial Stamp Paper in place of Earnest Money Deposit. | 282 | APPENDIX-D | Mandatory | Submit the Bid Security Declaration duly executed on Rs 100/- Non-Judicial Stamp Paper. | Yes |  |  |  | (To be submitted on Rs 100/- Non-Judicial Stamp Paper)
R-870 | The Bid Security Declaration must remain valid for the Bid validity period and any agreed extension. | 282 | APPENDIX-D | Mandatory | Ensure the Bid Security Declaration remains valid throughout the bid validity period and any agreed extensions. | Yes |  |  |  | This declaration shall remain valid for the Bid validity period and any agreed extension.
R-871 | Bidder must produce original or verifiable source documents of all credentials, financial certificates, experience certificates, registrations, and Key Personnel records when requested by AIIMS Patna. | 283 | APPENDIX-E | Mandatory | Produce originals and verifiable source documents of all submitted credentials, certificates, and personnel records upon request. | Yes |  |  |  | 1. We shall produce originals / verifiable source documents of all material credentials, financial certificates, experience certificates, registrations and Key Personnel records whenever called by AIIMS Patna.
R-872 | Performance Security Bank Guarantee must be executed by any scheduled bank on non-judicial stamp paper under the bank's covering letter mentioning the bank's address. | 284 | APPENDIX-F | Mandatory | Furnish the Performance Security Bank Guarantee from a scheduled bank executed on non-judicial stamp paper with an official bank covering letter stating the bank's address. | Yes |  |  |  | (To be executed by any scheduled bank, on a non-judicial stamp paper under bank's covering letter mentioning address of the bank)
R-873 | Professional Indemnity and Insurance Undertaking must be submitted on the Bidder's Letterhead. | 286 | APPENDIX-G | Mandatory | Execute and submit the undertaking on the bidder's official letterhead. | Yes |  |  |  | (To be submitted on the Bidder's Letterhead)
R-874 | Upon award and prior to commencement of services, the consultant must obtain and maintain at their cost all required insurance including Professional Indemnity Insurance of the prescribed amount and duration. | 286 | APPENDIX-G | Mandatory | Obtain and maintain the required Professional Indemnity Insurance along with other necessary insurances upon award before commencing services. | Yes |  |  |  | (a) We, M/s ______________________________, undertake that, upon award and before commencement of the Services, we shall obtain and maintain at our cost all insurance required under the RFP, including Professional Indemnity Insurance of the prescribed amount and duration, and any applicable employer's liability, workmen compensation, travel, third-party liability or other insurance necessary for performance of the Assignment.
R-875 | The Integrity Pact must be executed on Rs 100.00 Non-judicial Stamp paper and filled by the Bidder. | 287 | APPENDIX-H | Mandatory | Execute and submit the Integrity Pact on Rs 100.00 Non-judicial Stamp paper. | Yes |  |  |  | (On Rs 100.00 Non-judicial Stamp paper)
R-876 | Foreign bidders must disclose names and addresses of Indian agents/representatives, Indian bidders must disclose foreign principals, and all payments to Indian agents must be in Indian Rupees. | 288 | Section - 2, Clause 1.(d) | Mandatory | Disclose details of Indian agents/representatives or foreign principals per guidelines and make payments to Indian agents strictly in INR. | Yes |  |  |  | The Bidder(s)/Contractor(s) of foreign origin shall disclose the name & address of the Agents/representatives in India, if any. Similarly the Bidder(s)/Contractor(s) of Indian Nationality shall furnish the name and address of foreign principals, if any. Further details as mentioned in the “Guidelines on Indian Agents of Foreign Suppliers” shall be disclosed by the Bidder(s)/Contractor(s). Further, as mentioned in the Guidelines all the payment made to the Indian agent/representative have to be in Indian Rupees only.
R-877 | Bidders must disclose all payments made, committed to, or intended to be made to agents, brokers, or intermediaries in connection with the contract award when presenting the bid. | 288 | Section - 2, Clause 1.(e) | Mandatory | Disclose all past, committed, or intended payments to agents or intermediaries upon bid submission. | Yes |  |  |  | The Bidder(s)/Contractor(s) will, when presenting his bid, disclose any and all payments he has made, is committed to or intends to make to agents, brokers or any other intermediaries in connection with the award of the contract.
R-878 | The bidder must declare that no previous transgressions occurred in the last 3 years with any company in any country or any Indian PSU regarding anti-corruption norms. | 288 | Section - 5, Clause 1 | Eligibility criteria | Provide a declaration confirming no previous transgressions in the last 3 years. | Yes |  |  |  | The Bidder declares that no previous transgressions occurred in the last 3 years with any other company in any country conforming to the anti- corruption approach or with any Public Sector Enterprise in India that could justify his exclusion from the tender process.
R-879 | Bidders must sign the Integrity Pact; failure to sign or violation of its provisions will result in disqualification from the tender process. | 289 | Section - 6, Clause 2 | Mandatory | Sign and comply with the provisions of the Integrity Pact to avoid disqualification. | Yes |  |  |  | AIIMS Patna will disqualify from the tender process all bidders who do not sign this Pact or violate its provisions.
R-880 | If the bidder/contractor is a partnership or consortium, the Integrity Pact must be signed by all partners or consortium members. | 290 | Section - 10, Clause 3 | Mandatory | Ensure all partners or consortium members sign the Integrity Pact agreement. | Yes |  |  |  | If the Contractor is a partnership or a consortium, this agreement must be signed by all partners or consortium members.
R-881 | Bidders must submit Annexure H-1 disclosing agents, representatives, brokers, and intermediaries, or submit a signed NIL declaration if there is nothing to disclose. | 291 | ANNEXURE H-1 | Mandatory | Submit completed Annexure H-1 or a signed NIL declaration accompanying Appendix-H. | Yes |  |  |  | (To accompany Appendix-H; submit a signed NIL declaration where there is nothing to disclose.)
R-882 | The bidder and each Joint Venture member must submit the declaration regarding Rule 144(xi), land-border procurement restrictions, and reciprocity in Cover-I, selecting the applicable option and attaching registration where required. | 292 | APPENDIX-I | Eligibility criteria | Complete and submit Appendix-I in Cover-I (separately for the bidder and each JV member), select the applicable option (A, B, or C), and attach competent authority registration or exemption proof if applicable. | Yes |  |  |  | (To be submitted in Cover-I by the Bidder and separately by each JV Member; select the applicable option and attach registration where required.)
R-883 | The bidder must submit the Compliance Methodology cum Statement on its letterhead. | 295 | APPENDIX-K | Mandatory | Submit the completed Compliance Methodology cum Statement on the bidder's letterhead, stating compliance methodology and any deviations against the DBT-ICMR National BSL-3 Guidelines 2024 design criteria. | Yes |  |  |  | (To be submitted by bidder on its Letter head)
R-001 | Wall-floor junctions must be coved continuously to eliminate open joints, and all penetrations through walls, floors, and ceilings must be fully sealed. | 297 | C.2 | Mandatory | Ensure wall-floor junctions are coved continuously and seal all penetrations through walls, floors, and ceilings. | Yes |  |  |  | Wall-floor junctions shall be coved continuously (curved cove finish from floor running up the wall) to eliminate open joints. All penetrations through walls, floors, and ceilings (for service pipes, conduits, etc.) shall be fully sealed.
R-002 | Walls must be constructed with non-porous materials, finished with industrial-grade epoxy/paint or PU/low-lustre acrylic enamel, and be resistant to scratches, stains, moisture, chemicals, and heat. | 297 | C.3 | Mandatory | Construct walls using non-porous materials finished with specified industrial-grade coatings resistant to scratch, stain, moisture, chemical, and heat. | Yes |  |  |  | Walls shall be constructed with non-porous materials and finished with industrial-grade epoxy/paint or PU/low-lustre acrylic enamel. Surfaces shall be scratch-, stain-, moisture-, chemical- and heat-resistant.
R-003 | Ceilings must be monolithic, resistant to liquids and chemicals, with sealed penetrations and continuous seals maintained at wall-ceiling and wall-floor interfaces. | 297 | C.4 | Mandatory | Provide monolithic liquid- and chemical-resistant ceilings, seal all penetrations, and maintain seal continuity at wall-ceiling and wall-floor interfaces. | Yes |  |  |  | Ceilings shall be monolithic, resistant to liquids and chemicals, with all penetrations sealed. Continuity of seal to be maintained between all wall-ceiling and wall-floor interfaces.
R-004 | Interior coatings must be gas- and chemical-resistant, capable of withstanding disinfection/fumigation, and the applicant must specify the proposed coating system. | 297 | C.5 | Mandatory | Specify the proposed coating system capable of withstanding chemical disinfection and fumigation. | No — check |  |  |  | Interior coatings shall be gas- and chemical- resistant, capable of withstanding chemical dinfection and fumigation (e.g., formaldehyde/VHP/peracetic acid). Applicant to specify proposed coating system.
R-005 | Laboratory bench tops must be water-impervious, chemical/heat resistant, monolithic, fitted with marine edges/drip stops, and backsplashes must be tight to wall and sealed. | 297 | C.6 | Mandatory | Provide monolithic bench tops with marine edges/drip stops and tight, sealed backsplashes meeting chemical and heat resistance specifications. | Yes |  |  |  | Laboratory bench tops shall be: impervious to water; resistant to disinfectants, acids, alkalis, organic solvents and moderate heat; monolithic (no open seams); and fitted with marine edges/drip stops for spillage containment. Backsplashes shall be tight to wall and sealed at bench-wall junction.
R-006 | Laboratory furniture must have accessible spaces for cleaning, rounded rims/corners on doors/drawers/handles, self-closing lockable doors, and one-piece drawers with catches. | 297 | C.7 | Mandatory | Provide fit-for-purpose laboratory furniture with specified rounded edges, accessible cleaning clearances, self-closing/lockable doors, and one-piece drawers. | Yes |  |  |  | Laboratory furniture shall be fit for purpose. Open spaces between and under benches, cabinets, and equipment shall be accessible for cleaning. Doors, drawers, handles shall have rounded rims/corners. Cabinet doors shall be self-closing and lockable. Drawers shall be one-piece construction with catches.
R-007 | Reagent shelving must have lip edges, and all open bench seams are prohibited. | 297 | C.8 | Mandatory | Equip reagent shelving with lip edges and ensure no open bench seams exist. | Yes |  |  |  | Reagent shelving shall be equipped with lip edges. All open bench seams are prohibited.
R-008 | Separate, dedicated AHUs must be installed for containment and non-containment zones, supplying 100% fresh non-recirculating air to containment areas. | 297 | D.1.1 | Mandatory | Install separate AHUs supplying 100% single-pass, fresh air for containment areas with no recirculation. | Yes |  |  |  | Separate, dedicated Air Handling Units (AHUs) shall be installed for non-containment and containment zones. Each AHU serving a containment area shall supply 100% fresh (single-pass, non-recirculating) air. No recirculation of air from containment zones is permitted.
R-009 | Airflow direction must flow from less-contaminated to more-contaminated areas, and from entrance towards the rear in containment areas. | 297 | D.1.2 | Mandatory | Design airflow direction from less-contaminated to more-contaminated areas and from entrance towards the rear in containment zones. | Yes |  |  |  | Direction of airflow shall be from less-contaminated area to more-contaminated area. Airflow within the containment area shall be from entrance towards the rear area.
R-010 | Supply and exhaust HVAC systems must be independent with exhaust capacity approximately 15% greater than supply, and a VSD/VFD on exhaust fan is recommended. | 297 | D.1.3 | Mandatory | Design independent supply and exhaust HVAC systems with exhaust capacity approximately 15% higher than supply air capacity. | Yes |  |  |  | Supply and exhaust HVAC systems shall be fully independent. Exhaust capacity shall be approximately 15% (or as applicable) more than supply air capacity. Variable speed drive (VSD/VFD) on exhaust fan is recommended to facilitate room pressure control adjustments.
R-012 | All laboratory rooms must have visual monitoring devices indicating inward airflow and audible/visible alarms for HVAC system failure. | 298 | D.1.4 | Mandatory | Install visual monitoring devices and audible/visible HVAC failure alarms in all laboratory rooms. | Yes |  |  |  | All laboratory rooms shall be provided with visual monitoring devices (magnehelic/photohelic gauge or digital readout) indicating directional inward airflow. Audible and visible alarms for HVAC system failure shall be installed.
R-013 | The BSL-3 core facility must be maintained under continuous negative pressure, with a minimum 15 Pascal differential pressure between adjacent functional spaces. | 298 | D.2.1 | Mandatory | Maintain continuous negative pressure relative to adjacent areas with a minimum 15 Pascal differential pressure between functional spaces. | Yes |  |  |  | The BSL-3 core facility shall be maintained under continuous negative pressure relative to adjacent areas. Minimum differential pressure between any two adjacent functional spaces shall be 15 Pascal.
R-014 | Negative pressure in containment areas must be measured with reference to a common single atmospheric set point. | 298 | D.2.2 | Mandatory | Measure negative pressure referenced to a common single atmospheric set point. | Yes |  |  |  | All negative pressure in the containment area shall be measured with reference to a common single atmospheric set point.
R-015 | The HVAC system must maintain negative pressure across all outside weather conditions and withstand maximum design pressure under fan failure without distortion or damage. | 298 | D.2.3 | Mandatory | Design HVAC to sense and respond to outside weather pressure conditions and withstand maximum design pressure during fan failure without wall distortion. | Yes |  |  |  | The HVAC system shall be capable of sensing and responding to unusual outside pressure conditions (e.g., storms) and maintaining negative pressure in all weather conditions. The system shall withstand maximum design pressure under supply and exhaust fan failure (no wall distortion or damage).
R-016 | All exhaust air from containment areas and containment equipment must be HEPA/ULPA filtered (efficiency >= 99.97%) prior to discharge. | 298 | D.3.2 | Mandatory | Install HEPA/ULPA filters with efficiency >= 99.97% on all containment area and equipment exhaust air. | Yes |  |  |  | All exhaust air from the containment area and containment equipment (BSCs, IVCs) shall be HEPA/ULPA filtered (efficiency >= 99.97%) before discharge to atmosphere. Double HEPA filters in series are recommended in higher-contamination areas.
R-017 | HEPA filter housings must include in-situ leak testing, isolation valves, decontamination injection ports, and differential pressure gauges. | 298 | D.3.3 | Mandatory | Equip HEPA filter housings with in-situ leak testing facilities, upstream and downstream zero-leakage bio-seal dampers, chemical injection ports, and differential pressure gauges. | Yes |  |  |  | HEPA filter housings shall have: (a) in-situ leak testing facility; (b) isolation valves (zero-leakage bio- seal dampers) on both upstream and downstream sides; (c) ports for injecting decontamination chemicals before filter removal/replacement; (d) differential pressure gauges to monitor filter loading. BIBO (Bag-In-Bag-Out) configuration is preferred.
R-018 | Pre-filters must be installed upstream of all supply and exhaust HEPA filters, and used pre-filters must be decontaminated before removal. | 298 | D.3.4 | Mandatory | Install pre-filters upstream of HEPA filters and decontaminate used pre-filters prior to removal. | Yes |  |  |  | Pre-filters shall be installed upstream of all HEPA filters (supply and exhaust) to extend HEPA filter life. Used pre-filters shall be decontaminated before removal from containment area.
R-019 | Supply and exhaust HEPA filter housings must be located as close as possible to the containment space. | 298 | D.3.5 | Mandatory | Position supply and exhaust HEPA filter housings in close proximity to the containment space to minimize ductwork length. | Yes |  |  |  | Supply and exhaust HEPA filter housings shall be located as close as possible to the containment space to minimise the length of containment ductwork.
R-020 | HEPA filters must be designed for appropriate rated capacity with margin for dust loading. | 298 | D.3.6 | Mandatory | Design HEPA filters with appropriate rated capacity to accommodate dust loading margin. | Yes |  |  |  | HEPA filters shall be designed for approrpitate rated capacity to allow sufficient margin for dust loading.
R-021 | Air supply and exhaust ducts within the BSL-3 lab must be airtight, constructed of SS-304, and fumigation-compatible. | 298 | D.4.1 | Mandatory | Construct zero-leakage air supply and exhaust ducts inside the containment lab using SS-304 material compatible with fumigation. | Yes |  |  |  | Air supply and exhaust ducts within the containment BSL-3 lab shall be airtight (zero- leakage), constructed of SS-304 (stainless steel) material to prevent rusting. Duct material shall be fumigation-compatible.
R-022 | Supply and exhaust air dampers must be airtight and tested, and the complete laboratory ductwork must be leak tested by pressure decay test at +1000 Pascal (or soap bubble test) prior to commissioning. | 299 | D.4.2 | Mandatory | Test dampers prior to installation and perform pressure decay test at +1000 Pascal pressure (or soap bubble test) on ductwork before commissioning. | Yes |  |  |  | All supply and exhaust air dampers shall be airtight and tested before installation. The complete laboratory ductwork shall be tested for leakage by pressure decay test at +1000 Pascal pressure (or soap bubble test) prior to commissioning.
R-023 | All air duct openings and service penetrations between non-containment and containment zones must be sealed. | 299 | D.4.3 | Mandatory | Seal all duct openings and service penetrations between containment and non-containment zones. | Yes |  |  |  | All air duct openings and service penetrations running between non-containment and containment areas shall be sealed to prevent air circulation between zones.
R-024 | Exhaust air must discharge from the roof with rainwater ingress protection, preferably vertically upward at > 3000 fpm, with at least 7 m separation between exhaust and supply inlets. | 299 | D.4.4 | Mandatory | Design roof exhaust discharge preventing rainwater ingress, maintaining at least 7 m separation from supply inlets. | Yes |  |  |  | Exhaust air shall be discharged from the roof, preferably vertically upward at a velocity greater than 3000 fpm (900 m/min) to maintain negative pressure under worst weather conditions. The exhaust outlet shall be suitably designed to prevent rainwater ingress. Exhaust stack shall be positioned such that exhaust and supply air inlets are separated by at least 7 m to prevent re- entrainment.
R-025 | Outside air intake must be protected against rain ingress and equipped with a 6mm or 12mm bird screen. | 299 | D.4.5 | Mandatory | Provide outside air intake with rain ingress protection and a 6mm or 12mm bird screen. | Yes |  |  |  | Outside air intake shall be protected against rain ingress with bird screen (6mm or 12mm) and shall not allow rain to wet or clog supply air filters.
R-026 | The supply fan must interlock to start only after the exhaust fan is switched on, and the HVAC control system must be fully electronic to prevent positive pressurisation. | 299 | D.5.1 | Mandatory | Implement electronic HVAC control system with supply-exhaust interlock ensuring supply fan starts only after exhaust fan is on. | Yes |  |  |  | Supply fan shall start only after the exhaust fan is switched on (supply-exhaust interlock). The HVAC control system (DDC/BAS/PLC) shall be fully electronic and prevent positive pressurisation of the laboratory at all times.
R-027 | Zero-leakage isolation valves must be provided in HEPA filter housings to prevent leakage and facilitate gaseous decontamination. | 299 | D.5.2 | Mandatory | Provide zero-leakage isolation valves in HEPA filter housings. | Yes |  |  |  | Isolation valves (zero-leakage) shall be provided in HEPA filter housings to prevent leakage of contaminated air and to facilitate gaseous decontamination of the laboratory in case of AHU breakdown.
R-028 | Standby fans and pumps must be provided in supply and exhaust ventilation systems, with N+1 redundancy for chillers where applicable. | 299 | D.5.3 | Mandatory | Provide standby fans and pumps for supply/exhaust systems, and N+1 redundancy for chillers. | Yes |  |  |  | Standby fans and pumps shall be provided in supply and exhaust ventilation systems. N+1 redundancy for chillers (where applicable) to prevent overheating of interior rooms.
R-029 | Air compressors, if required, must be oil-free, moisture-free, installed outside containment, have sound level < 60 dB, and be mounted on vibration isolators with automatic moisture drain valves. | 299 | E.1 | Mandatory | Install oil-free and moisture-free air compressor outside containment on vibration isolators with auto moisture drain valve and noise level < 60 dB. | Yes |  |  |  | Air compressor (if required for pneumatic controls or compressed air supply within BSL-3) shall be oil- free and moisture-free, installed outside the containment area. Sound level < 60 dB. Shall be mounted on vibration isolators with automatic moisture drain valve.
R-030 | Analysis for centralized or stand-alone steam generators must be conducted based on requirements for autoclave, waste decontamination, and hot water. | 299 | E.2 | Mandatory | Conduct an analysis for centralized steam generator or stand-alone electric steam generators based on facility steam requirements. | Yes |  |  |  | Analysis for centralized steam generator (oil-fired or electric boiler) or stand-alone electric steam generators shall be conducted based on requirement. Steam supply is required for: autoclave operation, liquid waste decontamination, and hot water generation for showers/central heating.
R-031 | The facility must have a DG set capable of 100% load with AMF panel, extended fuel storage, an enclosure meeting CPCB/BPCB norms, and noise level < 60 dB. | 300 | E.3 | Mandatory | Provide a 100% load capacity DG set with AMF panel, CPCB/BPCB compliant enclosure, noise level < 60 dB, and extended fuel storage. | Yes |  |  |  | The BSL-3 facility shall have a Diesel Generator (DG) set capable of 100% load requirement with Automatic Mains Failure (AMF) panel. Fuel storage shall be designed for extended operation during prolonged power outages. DG set shall be housed in an environmentally friendly enclosure meeting CPCB/BPCB norms. Noise level < 60 dB. A standby/second generator is recommended (subject to cost-risk analysis at design stage).
R-032 | Each floor drain must have a minimum 125 mm deep trap connected directly to the ETP, with cleanout plugs in containment, and liquid waste pipes must be acid/chemical resistant, leakproof, and cleanable. | 300 | F.1 | Mandatory | Install floor drains with min 125 mm deep traps connected directly to ETP, cleanout plugs in containment, and acid/chemical-resistant leakproof piping. | Yes |  |  |  | Each floor drain shall have a minimum 125 mm deep trap connected directly to the Effluent Treatment Plant (ETP). Cleanout plugs shall be provided within the containment zone. Liquid waste pipes shall be acid- and chemical-resistant, leakproof, and easily cleanable.
R-033 | Drain traps must withstand maximum negative pressure to prevent reverse airflow and must always remain filled with water/chemical disinfectant. | 300 | F.2 | Mandatory | Design drain traps to withstand maximum negative pressure and maintain them filled with water or chemical disinfectant. | Yes |  |  |  | Drain traps shall withstand maximum negative pressure (as per risk assessment) to prevent reverse airflow from drain lines. Traps shall always remain filled with water/chemical disinfectant for sealing. Sewer lines shall be appropriately protected.
R-034 | A foot/elbow/sensor-operated hand washing station must be provided near the exit of each functional space, with acid- and chemical-resistant sinks. | 300 | F.3 | Mandatory | Provide hands-free hand washing stations with acid/chemical-resistant sinks near the exit of each functional space. | Yes |  |  |  | A foot/elbow/sensor-operated hand washing station shall be provided near the exit of each functional space. Sinks shall be acid- and chemical- resistant, preferably SS-304 or epoxy-coated resin.
R-035 | A sensor-based or foot/elbow-operated eye wash station must be provided in the laboratory, preferably near the exit door. | 300 | F.4 | Mandatory | Install a hands-free eye wash station in the laboratory near the exit door. | Yes |  |  |  | A sensor-based or foot/elbow-operated eye wash station shall be provided in the laboratory, preferably near the exit door.
R-036 | Service pipes must have sloping lines, backflow preventers, and be mounted with a gap from the wall for cleaning access. | 300 | F.5 | Mandatory | Install service pipes with sloping lines, backflow preventers, and spaced away from the wall. | Yes |  |  |  | Service pipes shall be installed with sloping lines and backflow preventers to isolate branch water lines. Piping shall be mounted with a gap from the wall for cleaning access and to avoid contamination.
R-037 | Compressed air lines for instrument control must be oil-free and moisture-free, fitted with inline HEPA filters and backflow preventers. | 300 | F.6 | Mandatory | Fit instrument compressed air lines with inline HEPA filters and backflow preventers delivering oil-free and moisture-free air. | Yes |  |  |  | Compressed air lines for instrument control shall be oil-free and moisture-free, fitted with small inline HEPA filters and backflow preventers.
R-038 | Vacuum outlets, if provided, must be protected by HEPA filters (>= 99.97% efficiency, validated/replaced annually) and liquid disinfectant traps. | 300 | F.7 | Mandatory | Protect vacuum outlets with liquid disinfectant traps and >= 99.97% efficient HEPA filters subject to annual replacement/validation. | Yes |  |  |  | Vacuum outlets (if provided) shall be protected by HEPA filters and liquid disinfectant traps. HEPA filter efficiency >= 99.97%; validated/replaced annually.
R-039 | Liquid waste treatment system (ETP/kill tank) must be provided, with steam-based disinfection for spore-forming bacteria, fungi, and infectious agents. | 300 | F.8 | Mandatory | Provide ETP/kill tank liquid waste treatment system and follow steam-based disinfection protocol for spore-forming bacteria, fungi, and other infectious agents. | Yes |  |  |  | All sewer and vent lines shall be appropriately protected. Liquid waste (biological/effluent) treatment system (ETP/kill tank) shall be provided based on risk assessment. Steam-based disinfection protocol shall be followed for spore- forming bacteria, fungi, and other infectious agents. Chemical disinfection in ETP may be considered for virus-culture-only facilities following proper validation.
R-040 | Effluent from washrooms must be decontaminated prior to municipal sewer disposal, and drain traps must have a minimum 125 mm water seal. | 300 | F.9 | Mandatory | Decontaminate washroom effluent before municipal disposal and install drain traps with minimum 125 mm water seal. | Yes |  |  |  | For facilities with washrooms, effluent from washrooms shall also be decontaminated before disposal to municipal sewer. Drain traps shall have minimum 125 mm water seal.
R-043 | A double-door barrier autoclave with interlocked doors must be provided for decontaminating waste, materials, and lab clothing leaving the facility. | 301 | F.10 | Mandatory | Install an in-situ pass-through double-door barrier autoclave with interlocked doors for waste and clothing decontamination. | Yes |  |  |  | Double-door barrier autoclave (in-situ, pass- through type) with interlocked doors shall be provided for decontamination of all contaminated waste and materials leaving the facility. Waste loaded from inside the facility; removed from outside only after autoclave cycle is complete. Lab clothing shall be decontaminated by autoclaving before washing.
R-044 | A fumigation airlock must be provided for materials that cannot be steam autoclaved. | 301 | F.11 | Mandatory | Provide a fumigation airlock for materials unsuitable for steam autoclaving. | Yes |  |  |  | A fumigation airlock shall be provided for materials that cannot be steam autoclaved.
R-045 | Pass-through cabinets or dunk tanks with door interlocking and override facility must be provided for transferring biological materials. | 301 | F.12 | Mandatory | Install pass-through cabinets or dunk tanks with interlocked doors and override facility for material transfer. | Yes |  |  |  | Pass-through cabinets / dunk tanks shall be provided for transfer of biological materials. Door interlocking with override facility. Dunk tank provision based on risk assessment.
R-046 | Separate power and lighting panels must be provided for containment and non-containment spaces, and main distribution panels must be located outside containment. | 301 | G.1 | Mandatory | Provide separate power and lighting panels, placing main distribution panels outside the containment space. | Yes |  |  |  | Separate power and lighting panels shall be provided for containment and non-containment spaces. All main distribution panels shall be located outside the containment space for ease of maintenance.
R-047 | All conduit openings running across containment boundaries must be fully sealed at accessible locations. | 301 | G.2 | Mandatory | Fully seal all inside and outside conduit openings at accessible inspection points across containment boundaries. | Yes |  |  |  | All conduit openings (inside and outside) running from non-containment to containment areas and across different containment zones shall be fully sealed to prevent air circulation. Sealing shall be done at accessible locations for inspection and maintenance.
R-048 | Lighting must comply with ECBC, providing 300-500 lux in lab areas, 700-800 lux in cleaning cycle areas, and emergency lights must have UPS backup. | 301 | G.3 | Mandatory | Install ECBC-compliant energy-efficient lighting meeting specified lux levels and provide UPS backup for emergency lighting. | Yes |  |  |  | All lights shall be energy-efficient as per the Energy Conservation Building Code (ECBC). Lighting levels: 300-500 lux in laboratory areas; 700-800 lux in cleaning cycle areas. Emergency lighting shall be sufficient to permit safe stopping of work and safe exit. Emergency lights shall have UPS backup.
R-049 | Critical systems must have online UPS with minimum 120 minutes backup, plus a standby UPS of 100% capacity. | 301 | G.4 | Mandatory | Provide online UPS with at least 120 minutes backup for critical systems along with a 100% capacity standby UPS. | Yes |  |  |  | All critical systems (signage, emergency lights, BAS/DDC, communication network, exhaust system for maintaining negative pressure, and other critical equipment) shall be provided with online UPS with minimum 120 minutes backup. A standby UPS of 100% capacity of the designed UPS capacity shall be installed.
R-050 | A standby generator with AMF panel capable of bearing 100% facility load must be available for power failures. | 301 | G.5 | Mandatory | Provide a standby generator equipped with AMF panel sized for 100% facility load. | Yes |  |  |  | A standby generator with AMF panel capable of bearing 100% facility load shall be available for power failure scenarios.
R-051 | Electrical load must be divided equally across phases, with a centralized voltage regulator (±10%) outside the facility, and a separate central servo stabilizer (±2%) for designated equipment. | 301 | G.6 | Mandatory | Balance electrical load equally across phases and install an external central voltage regulator (±10%) and separate central servo stabilizer (±2%). | Yes |  |  |  | Electrical load shall be divided equally across each phase. A centralized voltage regulator (±10% of rated supply) shall be provided, located outside the facility. Equipment requiring servo voltage (±2%) shall be identified at design stage and served by a separate central servo stabilizer outside the facility.
R-052 | A standby cable with 100% load capacity must be maintained, and electrical load calculations must account for future equipment additions. | 301 | G.7 | Mandatory | Provide a 100% load capacity standby cable and factor future equipment additions into load calculations. | Yes |  |  |  | A separate standby cable with 100% load capacity shall be kept as standby and used in case of fault in the main cable to reduce downtime. Electrical load calculations shall account for future equipment additions.
R-053 | Wiring for interlocking of double-door entry, airlocks, pass boxes, and barrier autoclaves must prevent both doors from opening simultaneously under any condition. | 301 | G.8 | Mandatory | Design door interlocking wiring to ensure both doors of entryways, airlocks, pass boxes, and autoclaves cannot open at the same time. | Yes |  |  |  | Wiring for interlocking of double-door entry, airlocks, pass boxes, and double-door autoclaves shall be designed so that both doors cannot be opened simultaneously under any condition.
R-884 | Direct Digital Control (DDC) and Building Automation System (BAS) are mandatory for automated monitoring and control of all critical containment parameters. | 302 | H.4 | Mandatory | Incorporate DDC and BAS in the design for automated monitoring and control of critical parameters and detail the architecture and integration scope. | Yes |  |  |  | Direct Digital Control (DDC) and Building Automation System (BAS) are mandatory for automated monitoring and control of all critical containment parameters (negative pressure, ACPH, HVAC status, access control, alarms). Architecture and integration scope to be detailed.
R-885 | Access control system with biometric/fingerprint scanning must be integrated with the interlocking system, and a 3-tiered security system must be designed. | 302 | H.5 | Mandatory | Design an access control system with biometric/fingerprint scanning integrated with the entry/exit interlocks and provide a 3-tiered security system. | Yes |  |  |  | Access control system with biometric/fingerprint scanning shall be integrated with the entry/exit interlocking system. A 3-tiered security system shall be designed as part of the overall security architecture.
R-886 | Biological Safety Cabinets (BSCs) must be minimum Class II A2, and Class III for highest-risk activities based on risk assessment. | 302 | I.1 | Mandatory | Provide minimum Class II A2 BSCs (or Class III for highest-risk activities) located away from walking areas and crosscurrents, ensuring exhaust air does not interfere with air balance. | Yes |  |  |  | Biological Safety Cabinets (BSCs): Class II A2 (minimum); Class III for highest-risk activities, as per risk assessment. BSCs shall be placed away from walking areas and crosscurrents from doors and ventilation systems. Exhaust air from BSCs (after HEPA filtration) shall be discharged without interference with the cabinet's air balance or the building exhaust system.
R-887 | The design must incorporate provisions to facilitate formal commissioning and validation per Annexure II, III, and IV of DBT-ICMR BSL-3 Guidelines 2024. | 303 | J.1 | Mandatory | Incorporate commissioning and validation provisions into the design for all essential tests specified in the DBT-ICMR BSL-3 Guidelines 2024. | Yes |  |  |  | The design shall incorporate provisions to facilitate formal commissioning and validation as per Annexure II, III, and IV of the DBT-ICMR BSL-3 Guidelines 2024. Essential tests during commissioning include (but are not limited to): directional airflow, negative pressure verification, ACPH measurement, HEPA filter integrity testing (DOP/PAO scan), duct leakage test, autoclave validation, room containment integrity test, electrical system checks, and BAS/DDC functional verification.
R-888 | Design must provide for annual revalidation of critical systems to be executed by ISO/IEC 17025 accredited organizations. | 303 | J.3 | Mandatory | Include design provisions enabling annual revalidation of critical systems by ISO/IEC 17025 accredited bodies. | Yes |  |  |  | Design shall include provisions for annual revalidation of critical systems: directional airflow, air velocity, ACPH, AHU performance, HEPA filter integrity, BSC certification, autoclave efficacy, particle count, and room perimeter integrity. All revalidation to be by ISO/IEC 17025 accredited organizations.
R-889 | Critical biocontainment systems must incorporate sufficient redundancy (N+1 or N+2) so that failure of any single source does not result in shutdown. | 303 | K.1 | Mandatory | Incorporate N+1 or N+2 redundancy for critical electrical, mechanical, and power systems based on criticality and cost-risk analysis. | Yes |  |  |  | Design principle: Failure of any single electrical, mechanical, or power source shall NOT result in shutdown of critical biocontainment systems. Sufficient redundancy (N+1 or N+2 as applicable) shall be incorporated for all critical systems based on criticality and cost-risk analysis.
R-890 | Emergency exit door with override for interlocked doors and break-through panel in anteroom must be provided. | 304 | K.3 | Mandatory | Design emergency exit door with override for all interlocked doors, key in glass-fronted box (tested annually), and break-through panel in anteroom. | Yes |  |  |  | Emergency exit provisions: Emergency exit door with override for all interlocked doors, key in glass-fronted box, tested minimum once per year. The emergency door shall remain closed at all other times. Break-through panel in anteroom for emergency egress.
R-891 | Bidder must submit a Regulatory Compliance Statement confirming the design meets all DBT-ICMR 2024 certification requirements. | 305 | L.9 | Mandatory | Submit a regulatory compliance statement confirming design compliance with the DBT-ICMR National Guidelines for BSL-3 Containment Facility 2024. | Yes |  |  |  | Regulatory Compliance Statement: A statement confirming that the design will meet all requirements for certification under the DBT-ICMR National Guidelines for BSL-3 Containment Facility 2024, and will facilitate application for BSL-3 Certification to the concerned Line Ministry.
R-892 | Bidders must mark Yes/No/NA against each checklist item, mention exact PDF page numbers, and provide reasons where an item is not applicable. | 306 | SECTION - CHECKLIST, Item 3 | Submission logistics | Complete the checklist by marking Yes/No/NA, citing the exact PDF page number for each item, and explaining non-applicable items in the relevant Annexure. | Yes |  |  |  | All requirements shall be complied with in the prescribed format. Against each item, the Bidder shall mark Yes/No/NA and mention the exact PDF page number. Where an item is not applicable, a brief reason shall be stated in the relevant Annexure.
R-893 | Annexures 1 to 16 must be uploaded in Cover-I (Technical Bid), while Annexure-17 and BOQ must be uploaded only in Cover-II (Financial Bid). | 306 | SECTION - CHECKLIST, Item 4 | Submission logistics | Upload Annexures 1 through 16 in Cover-I and Annexure-17 with CPPP BOQ in Cover-II, ensuring no financial details appear in Cover-I. | Yes |  |  |  | Annexures 1 to 16 shall be uploaded in Cover-I (Technical Bid). Annexure-17 and the protected CPPP BOQ shall be uploaded only in Cover-II (Financial Bid). No financial information shall appear in Cover-I.
R-894 | Submission of Annexure-1 (Bid Covering Letter, Unconditional Acceptance, and Part B DBT-ICMR/Statutory Compliance Undertaking). | 306 | Sl. No. 1 | Mandatory | Complete, sign, date, seal, and upload Annexure-1 in Cover-I. | Yes |  |  |  | Annexure-1 - Bid Covering Letter, Unconditional Acceptance and Part B DBT-ICMR/Statutory Compliance Undertaking, duly completed, signed, dated and sealed.
R-895 | Submission of Annexure-2 (Bidder Information, Legal Status, and Lead Architect CoA Registration) with supporting legal and authorization documents. | 306 | Sl. No. 2 | Mandatory | Submit Annexure-2 along with Lead Architect CoA Registration, Professional Responsibility Declaration, registration/incorporation records, and signatory authorization. | Yes |  |  |  | Annexure-2 - Bidder Information, Legal Status and Authorisation, including Part D Lead Architect CoA Registration and Professional Responsibility Declaration, with registration/incorporation documents and signatory authorisation.
R-896 | Submission of Annexure-3 (Eligibility, Qualification and Consolidated Declaration-cum-Document Index). | 306 | Sl. No. 3 | Mandatory | Submit completed Annexure-3 indexing exact document names and PDF page references, covering all applicable eligibility and integrity declarations. | Yes |  |  |  | Annexure-3 - Eligibility, Qualification and Consolidated Declaration-cum-Document Index, duly completed with exact document names and PDF page references, including all applicable eligibility and integrity declarations.
R-897 | Submission of Annexure-4 (Financial Capability and Average Annual Turnover Certificate) with CA certificate(s), UDIN, and audited financials. | 306 | Sl. No. 4 | Eligibility criteria | Upload Annexure-4 with CA certificate(s) containing UDIN, audited financial statements, and JV member-wise financial eligibility (if applicable). | Yes |  |  |  | Annexure-4 - Financial Capability and Average Annual Turnover Certificate, including Part C JV Member-wise financial eligibility where applicable, with CA certificate(s), UDIN and audited supporting pages.
R-898 | Submission of Annexure-5 (Litigation, Arbitration, Investigation, Contract Performance and Current Commitments Disclosure). | 306 | Sl. No. 5 | Mandatory | Submit Annexure-5 with supporting documents for any disclosed litigation/disputes, or a signed NIL declaration if there is nothing to disclose. | Yes |  |  |  | Annexure-5 - Litigation, Arbitration, Investigation, Contract Performance and Current Commitments Disclosure, with supporting records wherever a matter is disclosed; signed NIL declaration where there is nothing to disclose.
R-899 | Submission of Annexure-6 (Firm BSL-3/BSL-4 Experience package) with authenticity undertaking and client certificates. | 306 | Sl. No. 6 | Eligibility criteria | Submit Annexure-6 detailing nominated BSL-3/BSL-4 projects, client certificates, and Part F Experience Document Authenticity and Independent Verification Undertaking. | Yes |  |  |  | Annexure-6 - Firm BSL-3/BSL-4 Experience package, including Part F Experience Document Authenticity and Independent Verification Undertaking, nominated projects, evidence and client certificates.
R-900 | Private-client projects claimed under Annexure-6 must be supported by payment proofs, TDS/26AS/AIS, signatory authority proof, and verifiable contacts. | 306 | Sl. No. 7 | Eligibility criteria | Submit invoices, payment proof, TDS/Form 26AS/AIS evidence, certificate signatory authorization proof, and official client contact details for any private client project claimed. | Yes |  |  |  | For any private-client project claimed under Annexure-6: invoices, payment proof, applicable TDS/Form 26AS/AIS evidence, proof of authority of the certificate signatory and verifiable official client contact details.
R-901 | Submission of Annexure-7 (Key Personnel Schedule, Organisation Chart and Deployment Commitment). | 306 | Sl. No. 8 | Mandatory | Submit Annexure-7 including Part B Employment/Association Verification Certificate and supporting payroll, JV, or external-specialist proof. | Yes |  |  |  | Annexure-7 - Key Personnel Schedule, Organisation Chart and Deployment Commitment, including Part B Employment/Association Verification Certificate and supporting payroll/JV/external-specialist evidence.
R-902 | Submit separate CV of each Key Expert signed by the Expert and the Bidder, along with qualification, registration/certification, and experience evidence. | 307 | Sl. No. 9 | Mandatory | Submit Annexure-8 containing separate CV of each Key Expert, signed by both the Expert and the Bidder, with evidence of qualification, registration/certification, and experience. | Yes |  |  |  | Annexure-8 - Separate CV of each Key Expert, signed by the Expert and the Bidder, with relevant qualification, registration/certification and experience evidence.
R-903 | Submit Biosafety Expert/Sub-Consultant Commitment and Participation Plan with minimum two physical visits, Part D disclosure, binding agreement, and joint signatures. | 307 | Sl. No. 10 | Mandatory | Submit Annexure-9 with commitment and participation plan for Biosafety Expert/Sub-Consultant including required visits, contractual disclosure, binding agreement, and joint signatures. | Yes |  |  |  | Annexure-9 - Biosafety Expert/Sub-Consultant Commitment and Participation Plan, including minimum two physical visits, Part D contractual arrangement disclosure, binding agreement and joint signatures.
R-904 | Submit Project Understanding and Preliminary Need Assessment within the prescribed page limit. | 307 | Sl. No. 11 | Mandatory | Submit Annexure-10 within the specified page limit. | Yes |  |  |  | Annexure-10 - Project Understanding and Preliminary Need Assessment, within the prescribed page limit.
R-905 | Submit Technical Approach, Design Philosophy and Critical Compliance Matrix duly completed for all applicable requirements. | 307 | Sl. No. 12 | Mandatory | Complete and submit Annexure-11 covering all applicable requirements. | Yes |  |  |  | Annexure-11 - Technical Approach, Design Philosophy and Critical Compliance Matrix, duly completed for all applicable requirements.
R-906 | Submit detailed Day 1 to Day 60 Work Program and Design Delivery Schedule. | 307 | Sl. No. 13 | Mandatory | Submit Annexure-12 detailing the work program and design delivery schedule from Day 1 to Day 60. | Yes |  |  |  | Annexure-12 - Detailed Day 1-Day 60 Work Program and Design Delivery Schedule.
R-907 | Submit Project Management, Expert Deployment, Site Visit, Meeting and Record Management Plan including Joint Site Visit declaration signed by Authorised Signatory, Lead Architect, and Biosafety Expert. | 307 | Sl. No. 14 | Mandatory | Submit Annexure-13 including the Joint Site Visit, Site Understanding and Design-Readiness Declaration signed by Authorised Signatory, Lead Architect, and named Biosafety Expert, with records/photographs/observations attached. | Yes |  |  |  | Annexure-13 - Project Management, Expert Deployment, Site Visit, Meeting and Record Management Plan, including the Joint Site Visit, Site Understanding and Design- Readiness Declaration signed by the Authorised Signatory, Lead Architect and named Biosafety Expert, with site-visit records/photographs/observations wherever attached.
R-908 | Submit QA/QC, Risk, BIM/CDE/CFD, Technical Resources, Equipment Integration and Deliverable Control Plan with evidence of resources. | 307 | Sl. No. 15 | Mandatory | Submit Annexure-14 accompanied by evidence of software/resources owned or formally available. | Yes |  |  |  | Annexure-14 - QA/QC, Risk, BIM/CDE/CFD, Technical Resources, Equipment Integration and Deliverable Control Plan, with evidence of software/resources owned or formally available, wherever relied upon.
R-909 | Submit Construction, Testing, Commissioning, Validation, Certification and Handover Support Plan. | 307 | Sl. No. 16 | Mandatory | Submit Annexure-15. | Yes |  |  |  | Annexure-15 - Construction, Testing, Commissioning, Validation, Certification and Handover Support Plan.
R-910 | Submit Deviations, Assumptions and Optimisation Statement or a signed NIL statement if no deviations are proposed. | 307 | Sl. No. 17 | Mandatory | Submit Annexure-16, or submit a signed NIL statement if proposing no deviation or qualification. | Yes |  |  |  | Annexure-16 - Deviations, Assumptions and Optimisation Statement; submit signed NIL statement where no deviation or qualification is proposed.
R-911 | Submit Bid Security Declaration in the prescribed format. | 307 | Sl. No. 20 | Mandatory | Submit Appendix-D in the prescribed format. | Yes |  |  |  | Appendix-D - Bid Security Declaration in the prescribed format.
R-912 | Submit Rule 144(xi) land-border procurement restrictions and reciprocity declaration with supporting documents where applicable. | 308 | Sl. No. 24 | Mandatory | Submit Appendix-I along with competent-authority registration/supporting documents where applicable. | Yes |  |  |  | Appendix-I - Rule 144(xi), land-border procurement restrictions and reciprocity declaration, with competent- authority registration/supporting documents wherever applicable.
R-913 | Submit Compliance methodology cum statement. | 308 | Sl. No. 25 | Mandatory | Submit Appendix-K. | Yes |  |  |  | Appendix-K – Compliance methodology cum statement
R-914 | Submit Financial Proposal Undertaking and CPPP BOQ Confirmation uploaded only in the Financial Cover. | 308 | Section B, Sl. No. 1 | Submission logistics | Duly complete Annexure-17 and upload it strictly in the Financial Cover where the portal provides the field. | Yes |  |  |  | Annexure-17 - Financial Proposal Undertaking and CPPP BOQ Confirmation, duly completed and uploaded only in the Financial Cover, where the portal provides the relevant field.
R-915 | Upload digitally signed protected CPPP BOQ Excel file with firm lump-sum fee without altering structure, rows, columns, formula, or format. | 308 | Section B, Sl. No. 2 | Submission logistics | Digitally sign and upload the protected CPPP BOQ Excel file containing the lump-sum consultancy fee without modifying its structure, rows, columns, formula, or format. | Yes |  |  |  | Protected CPPP BOQ Excel file containing the complete firm lump-sum consultancy fee, digitally signed and uploaded without altering the prescribed structure, rows, columns, formula or format.
R-916 | A maximum of six completed firm-level BSL-3/ABSL-3/BSL-4/ABSL-4 projects taken together may be used for technical scoring across Parameters 1, 2, and 6. | 309 | SCHEDULE TO CLAUSE 19.4, Note | Evaluation criteria | Provide details of a maximum of six completed firm-level projects across Parameters 1, 2, and 6, or adhere to any lower limit specified for an individual parameter. | Yes |  |  |  | Across Parameters 1, 2 and 6, a maximum of six completed firm-level BSL-3/ABSL-3/BSL-4/ABSL-4 projects, taken together, may be used for scoring. Where any individual Parameter specifies a lower number of projects, the lower limit prescribed for that Parameter shall apply.
R-917 | Under Parameter 1, use between one and three eligible completed BSL-3/ABSL-3/BSL-4/ABSL-4 assignments for scoring across the three scoring areas. | 309 | Clause 1.2 | Evaluation criteria | Submit details for 1 to 3 completed assignments, naming one assignment relied upon for each scoring area without combining incomplete evidence across different assignments. | Yes |  |  |  | The Bidder may use one or a maximum of three eligible completed BSL-3/ABSL-3/BSL-4/ABSL-4 assignments under this Parameter. Each of the three scoring areas shall name the one assignment relied upon for that area. Incomplete evidence from different assignments shall not be combined for one scoring area. The project and evidence details shall be stated in the form given under this Parameter.
R-918 | Mandatory submission of evidence for Laboratory planning and movement routes, and HVAC, airflow and room-pressure design. | 309 | Clause 1.3 | Evaluation criteria | Submit sufficient evidence for Sl. No. 1 and Sl. No. 2 under Parameter 1 to avoid being awarded zero marks. | Yes |  |  |  | If sufficient evidence is not submitted for Sl. No. 1 or 2, zero marks shall be awarded for that area. These areas cannot be replaced by another option.
R-919 | Submit specific drawings and records demonstrating laboratory planning and movement routes for a completed past assignment. | 310 | Clause 1.3(i) | Evaluation criteria | Submit: (a) client requirement/design brief, (b) approved layout/flow drawing showing routes, (c) design review/approval record, and (d) final accepted or as-built layout (where available). | Yes |  |  |  | The bidder shall submit: (a) the relevant client requirement or design brief; (b) an approved layout or flow drawing showing the above routes; (c) a design review, comment or approval record; and (d) the final accepted or as-built layout, where available.
R-920 | Submit containment area HVAC parameter table supported by design basis, pressure schedule/schematic, and testing/commissioning records. | 310 | Clause 1.3(ii) | Evaluation criteria | Complete and submit the prescribed table covering Room-pressure relationship, Air changes per hour, and other parameters for the relevant containment area (not an isolated room or best result only), backed by HVAC design basis and validation records. | Yes |  |  |  | The bidder shall submit the following table for the relevant containment area. An isolated room or only the best test result shall not be submitted.
R-921 | Submit evidence for one chosen additional area of past work from Options A, B, C, or D. | 311 | Clause 1.3(iii) | Evaluation criteria | Select and submit supporting evidence for one option among: Option A (coordination), Option B (design checking), Option C (support during construction/validation), or Option D (future modification/improvement). | Yes |  |  |  | The bidder shall choose any one of the following options.
R-922 | The bidder may use one or a maximum of three eligible completed assignments for this criterion, with evidence for each scoring area drawn from a single assignment without combining incomplete evidence across projects. | 312 | (vi)(a)-(b) | Evaluation criteria | Submit evidence for each scoring area from a single assignment, using a maximum of three eligible completed assignments in total for the criterion. | Yes |  |  |  | (a) The bidder may use one or a maximum of three eligible completed assignments for this criterion. (b) Evidence for one scoring area shall come from one assignment only. Incomplete evidence from different assignments shall not be combined to complete one scoring area.
R-923 | Each submitted document must show or permit verification of the project, client, document title, date and revision, bidder's exact role, and relevant PDF page number. | 313 | (vi)(e) | Evaluation criteria | Ensure every submitted document clearly shows project and client, title, date/revision, bidder's exact role, and PDF page number. | Yes |  |  |  | (e) Each document shall clearly show or allow verification of: A. project and client; B. document title; C. date and revision; D. bidder’s exact role; and E. relevant PDF page number.
R-924 | The bidder must provide contact details (name, designation, official email, phone) of the client's authorized contact person for verification. | 313 | 1.5 | Mandatory | Provide the name, designation, official email address, and telephone number of the authorized contact person at the client organization. | Yes |  |  |  | The bidder shall provide the name, designation, official email address and telephone number of the client’s authorized contact person.
R-925 | After the bid-submission deadline, no new assignments or scoring claims can be added, project evidence cannot be substituted, and oral explanation will not earn marks. | 313 | 1.5 | Submission logistics | Submit all assignments and scoring claims prior to the deadline, adhering to post-submission clarification restrictions. | Yes |  |  |  | After the bid-submission deadline: (a) no new assignment shall be introduced; (b) no new scoring claim shall be added; (c) evidence from another project shall not be substituted; and (d) oral explanation shall not independently earn marks.
R-926 | A separate sheet must be submitted for each scoring area using the specified format. | 314 | 1.6 | Mandatory | Complete and submit a separate project and evidence sheet for each scoring area. | Yes |  |  |  | A separate sheet shall be submitted for each scoring area.
R-927 | The bidder must submit actual project records demonstrating how past BSL-3/4 designs were prepared, checked, and approved, rather than describing proposed methods. | 315 | 2.1 | Evaluation criteria | Submit actual past project records showing design preparation, checking, approval, equipment sizing, and risk identification. | Yes |  |  |  | The Bidder shall submit actual records from past projects. A description of the Bidder’s present or proposed method will not be treated as evidence of past work.
R-928 | For each of the three scored parts, the bidder must name one completed project, state the client, its exact role, the evidence document, and exact PDF page numbers, without combining evidence from different projects. | 315 | 2.2 | Evaluation criteria | Specify the relied-upon completed project, client, exact role, evidence document, and Technical Bid PDF page numbers separately for each scored part. | Yes |  |  |  | For each of the three scored parts, the Bidder shall name the one completed BSL-3/ABSL-3/BSL- 4/ABSL-4 project relied upon. Different parts may use different eligible projects. For every part, the Bidder shall state the project, client, its exact role, the evidence document and the exact Technical Bid PDF page numbers in the form given under this Parameter. Evidence from different projects shall not be combined to complete one part.
R-929 | The bidder must submit past project records showing preparation, checking, approval, comments made, and comment closure, with the checker being different from the preparer. | 315 | 2.3 | Evaluation criteria | Submit records identifying the preparer, checker (distinct from preparer), approver, review comments, and closure of comments in the final revision. | Yes |  |  |  | The bidder shall submit records from a past project showing: (a) who prepared the design; (b) who checked the design; (c) who approved the design for issue; (d) what comments were made during checking or client review; and (e) how those comments were corrected and closed in the final revision. The person checking the design should be different from the person who prepared it.
R-930 | The bidder must demonstrate that checking was actually carried out and comments were closed, or establish by acceptance that no comments were received. | 316 | 2.4 | Evaluation criteria | Provide evidence showing actual checking and closure of comments, or client acceptance indicating no comments were received. | Yes |  |  |  | The Bidder must also show that checking was actually carried out and the comments were closed or exhibit by acceptance that no comments were received.
R-931 | The bidder must select any two listed equipment/systems (at least one must be autoclave, ETP/EDS, or containment HVAC/AHU/exhaust) and demonstrate operating inputs, calculations, applicable guidelines, and BOQ/drawing incorporation. | 316 | 2.5 | Evaluation criteria | Select two qualifying equipment/systems and submit documentation showing operating requirements, sizing calculations, applicable standards, and final drawing/BOQ inclusion for both. | Yes |  |  |  | The Bidder shall select any two of the following equipment or systems that were included in its past consultancy scope: (a) Autoclave; (b) ETP or Effluent Decontamination System; (c) Containment HVAC/AHU/exhaust system; At least one selected item shall be an autoclave, ETP/EDS or containment HVAC/AHU/exhaust system. A pass box and dunk tank alone will not be sufficient. For both selected items, the Bidder shall show: (i) the operating requirement or design input; (ii) the calculation or technical basis used to decide capacity, number, size or location; (iii) the applicable guideline, standard, approved user requirement or design requirement that was followed; and (iv) how the decision was included in the final drawing, specification, equipment schedule or BOQ.
R-932 | Bidder must demonstrate the basis of capacity for autoclave, ETP/EDS, or HVAC systems, or basis of selection/location/size for pass boxes or dunk tanks. | 317 | Section 2.6 | Evaluation criteria | Provide calculations and basis for capacity, sizing, numbers, or location in the technical proposal, linking them to project requirements rather than submitting manufacturer catalogues. | Yes |  |  |  | For an autoclave, ETP/EDS or HVAC system, the Bidder shall show the basis of capacity. For a pass box or dunk tank, it may show the basis of number, chamber size, intended load, location, movement route or decontamination requirement.
R-933 | Bidder must specify which applicable guideline or standard was followed and where it was applied in the design. | 317 | Section 2.6 | Evaluation criteria | Explicitly identify the specific standard/guideline requirement utilized and indicate its application within the design documents instead of merely listing guideline names. | Yes |  |  |  | The Bidder shall show which requirement was followed and where it was used in the design.
R-934 | Bidder must demonstrate at least three design problems or failure risks identified during a past project. | 317 | Section 2.7(i) | Evaluation criteria | Submit documentation showing three design problems or failure risks identified in past projects. | Yes |  |  |  | (i) The Bidder shall show at least three design problems or failure risks identified during a past project.
R-935 | Design risks presented must cover containment/HVAC, equipment/BMS/utilities, and one additional acceptance/certification risk. | 317 | Section 2.7(ii) | Evaluation criteria | Ensure the three identified past risks cover: (a) containment/HVAC/pressure cascade/HEPA, (b) equipment/utility/BMS/alarms/interlocks, and (c) one other risk affecting testing, validation, certification, or acceptance. | Yes |  |  |  | (ii) The risks shown shall include: (a) at least one risk relating to containment, HVAC, pressure cascade, room leakage or HEPA arrangement; (b) at least one risk relating to equipment, utility, BMS, alarm, interlock or emergency operation; and (c) one other relevant risk that could have affected testing, validation, certification or final acceptance.
R-936 | Bidder must detail the problem identified, design change made, and closure verification for each past risk. | 317 | Section 2.7(iii) | Evaluation criteria | Submit documented evidence for each risk explaining the identified problem, the corrective design action taken, and how the correction was verified or closed. | Yes |  |  |  | (iii) For each risk, the Bidder shall show: (a) what problem or failure risk was identified; (b) what change or corrective action was made in the design; and (c) how the correction was checked or closed.
R-937 | Bidder must demonstrate three project-specific risks or potential failure points identified and resolved during a past project. | 318 | Section 2.7 Note | Evaluation criteria | Provide evidence of three project-specific risks or potential failure points addressed during design, review, coordination, construction support, testing, or validation of a previous project. | Yes |  |  |  | The Bidder shall demonstrate three project-specific risks or potential failure points that were identified and addressed during the design, design review, coordination, construction support, testing or validation of a past project.
R-938 | Past project citations must be within the Bidder's consultancy scope, clearly identified, non-duplicative, and within allowed limits. | 318 | Section 2.9 | Evaluation criteria | Ensure cited past assignments match documented consultancy scope, clearly state the bidder's role, do not claim duplicate marks across criteria, and do not exceed the permitted assignment count. | Yes |  |  |  | (i) the work shown must have been within the Bidder’s documented consultancy scope; (ii) the project and Bidder’s exact role must be clearly identified; (iii) the same fact or achievement shall not receive marks under more than one technical criterion; and (iv) the maximum number of past assignments permitted elsewhere in the RFP shall continue to apply.
R-939 | Submitted evidence must relate to actual past work existing prior to the proposal submission deadline. | 319 | Section 2.11(i) | Mandatory | Submit only historical documentation created prior to the bid submission deadline to evidence past technical work. | Yes |  |  |  | (i) Evidence shall relate to actual past work and shall have existed before the Proposal submission deadline.
R-940 | Official emails used as evidence must contain sender, recipient, date, project reference, and technical resolution details. | 319 | Section 2.11(iv) | Evaluation criteria | Ensure any submitted email evidence clearly displays sender, recipient, date, project/document reference, and technical comment/closure. | Yes |  |  |  | (iv) An official email may be accepted only when it clearly shows: (a) sender and recipient; (b) date; (c) project or document reference; and (d) the technical comment, decision or closure.
R-941 | Redactions in evidence must leave project identity, dates, revisions, technical issues, design actions, and closures readable. | 319 | Section 2.11(vi) | Mandatory | Redact only confidential commercial details while keeping technical, project, date, and closure records fully legible. | Yes |  |  |  | (vi) Confidential commercial details may be hidden. However, the project/document identity, date or revision, technical issue, design action and closure shall remain readable.
R-942 | Bidder must state the specific guidelines or standards applicable to the past project at its time and location. | 319 | Section 2.11(vii) | Mandatory | Indicate the relevant regulatory or technical standard that governed the historical project at the time of execution. | Yes |  |  |  | (vii) The Bidder shall mention the guideline or standard applicable to the past project at the time and place of that assignment.
R-943 | Bidder must submit a signed CV and details of up to two similar assignments for each proposed Key Expert. | 320 | Section 3.2(i) | Mandatory | Provide a signed CV and details of no more than two similar assignments for each proposed Key Expert. | Yes |  |  |  | (i) The Bidder shall submit: (a) a signed CV of each proposed Key Expert; and (b) details of a maximum of two similar assignments for each expert.
R-944 | Key Expert assignment descriptions must include project details, client, period, designation, personal work performed, and current status. | 320 | Section 3.2(ii) | Mandatory | State project name/type, client/employer, dates, designation, specific technical tasks personally handled, and current status for each key expert assignment. | Yes |  |  |  | (ii) For every assignment, the following shall be stated: (a) name and type of project; (b) client/employer; (c) period and designation of the expert; (d) specific technical work personally performed by the expert; and (e) present status of that work.
R-945 | Key Expert assignments must be presented in the specified format. | 320 | Section 3.3 | Mandatory | Present key expert assignment details using the prescribed Key Expert format. | Yes |  |  |  | The assignments shall be stated in the Key Expert format given under this Parameter.
R-946 | Key Expert assignments are acceptable only if the expert's personal technical work is clearly described and relevant. | 321 | Section 3.6(i) | Evaluation criteria | Clearly state the specific technical work personally executed by the expert and ensure it aligns with the applicable role description. | Yes |  |  |  | (i) An assignment shall be accepted only when the expert’s personally performed work is clearly stated and is relevant to the applicable description’
R-947 | A single person cannot be scored against more than one Key Expert position. | 322 | 3.7 (vi) | Mandatory | Ensure that the same individual is proposed and scored for only one Key Expert position. | Yes |  |  |  | The same person shall not be scored against more than one Key Expert position.
R-948 | No new expert or past assignment will be accepted after the Bid Due Date to enhance the technical score. | 322 | 3.7 (ix) | Submission logistics | Submit all expert profiles and past assignments prior to the Bid Due Date, as no additions or replacements will be allowed thereafter for scoring. | Yes |  |  |  | No new expert or past assignment shall be accepted after the Bid Due Date for improving the Technical Score.
R-949 | Evaluated and accepted key experts must be deployed for the assignment as per contract terms. | 322 | 3.7 (x) | Mandatory | Deploy the specific experts accepted during technical evaluation on the project in compliance with the contract. | Yes |  |  |  | The experts evaluated and accepted under this criterion shall be deployed for the AIIMS Patna assignment in accordance with the Contract.
R-950 | Submission of project details for past BSL-3/BSL-4 work of the proposed Biosafety Expert (maximum two projects). | 323 | 4.2 | Evaluation criteria | Submit details for a maximum of two completed BSL-3/BSL-4 projects for the proposed Biosafety Expert, providing client name, facility type, expert role, work performed, stages/site visits involved, status/result, and supporting document page numbers. | Yes |  |  |  | The Bidder may submit details of a maximum of two completed BSL-3/BSL-4 projects involving the proposed Biosafety Expert. For each project, the Bidder shall provide: (a) project and client name; (b) type of facility; (c) Expert’s role; (d) work performed by the Expert; (e) project stages in which the Expert was involved regularly and site visit; (f) result or present status of the project; and (g) supporting document with Technical Bid page number.
R-951 | Evidence of the Biosafety Expert's role via client/employer certificate or verifiable record. | 323 | 4.2 | Mandatory | Provide a client/employer certificate or other verifiable project documentation supporting the Biosafety Expert's role in the cited projects. | Yes |  |  |  | The Expert’s role shall be supported by a client/employer certificate or another verifiable project record.
R-952 | Identification of supporting project and PDF page references for each evaluated Biosafety scoring Group. | 323 | 4.3 | Evaluation criteria | State whether Project 1, Project 2, or both support each scored Group and provide the exact Technical Bid PDF page numbers and supporting documents. | Yes |  |  |  | For each scored Group, the Bidder shall identify whether Project 1, Project 2 or both projects support the claim and shall state the supporting document and exact Technical Bid PDF page numbers.
R-953 | Demonstration of the Biosafety Expert's review or vetting of design and equipment documents. | 324 | 4.6 | Evaluation criteria | Demonstrate that the Biosafety Expert reviewed or vetted engineering drawings, calculations, or P&IDs rather than requiring personal preparation of such documents. | Yes |  |  |  | The Biosafety Expert is not required to have personally prepared the engineering drawings, calculations or P&IDs. The Bidder shall demonstrate the Expert’s biosafety review or vetting of such documents.
R-954 | Submission of Biosafety Expert project details in the prescribed table format. | 326 | 4.12 | Submission logistics | Complete and submit the Biosafety Expert project details in the structured format under Section 4.12, mapping each scoring group (A through E) to the specific work, results, and PDF page citations. | Yes |  |  |  | 4.12 Biosafety expert project format: Particular Bidder's Response / Reference Name of proposed Biosafety Expert Current Employer / Professional Association Project 1: project, client, facility type, Expert's role and supporting page(s) Project 2: project, client, facility type, Expert's role and supporting page(s) Group Project 1 / Project 2 / Both Expert's Specific Work Result / Status Supporting Document and PDF Page(s) A B C D E
R-955 | Bidder must explain how it proposes to carry out the AIIMS Patna assignment, covering functional planning, retrofitting assessment, compliance, design checking, biosafety expert involvement, interdisciplinary coordination, deliverables, work sequencing, risk management, and accountability. | 327 | 5.1 | Mandatory | Explain the proposed approach and methodology for carrying out the AIIMS Patna assignment across all specified evaluation areas without using generic methodology. | Yes |  |  |  | The Bidder shall explain how it proposes to carry out the AIIMS Patna assignment. The evaluation will cover functional planning, assessment and retrofitting of the existing building, compliance with applicable requirements, design checking, and involvement of the Biosafety Expert, coordination among different disciplines, preparation of deliverables, work sequencing, risk management and accountability. Generic company methodology or repetition of the RFP requirements will not earn marks.
R-956 | Bidder must submit the prescribed AIIMS Patna-Specific Design Delivery Response Form, comprising a written response of up to five A4 pages and one mandatory A3 Functional Zoning and Flow Concept Sketch. | 327 | 5.2(i) | Mandatory | Submit the AIIMS Patna-Specific Design Delivery Response Form with a maximum 5-page A4 written response and one A3 sketch. | Yes |  |  |  | The Bidder shall submit the prescribed AIIMS Patna-Specific Design Delivery Response Form, comprising: (a) A project-specific written response not exceeding five A4 pages; (b) One mandatory A3 Functional Zoning and Flow Concept Sketch.
R-957 | For each Evaluation Group, the bidder must clearly state the factors considered, proposed method, responsible personnel, and resulting output. | 327 | 5.2(iii) | Mandatory | Detail the factors considered, proposed method, responsible key personnel, and resulting outputs for each Evaluation Group in the response. | Yes |  |  |  | For each Evaluation Group, the Bidder shall clearly state: (a) Factors considered — the project conditions, risks and alternatives affecting the decision; (b) Proposed method — how the matter will be assessed, coordinated, checked and closed; (c) Responsible personnel — the proposed Key Personnel responsible for the work; and (d) Resulting output — the drawing, report, matrix, register, review record or other document that will demonstrate completion.
R-958 | Bidders must not cite past projects under this parameter; marks depend only on the AIIMS Patna-specific written response and mandatory A3 sketch submitted with the Technical Bid. | 327 | 5.3 | Mandatory | Do not cite past projects under this parameter; submit only the AIIMS Patna-specific written response and mandatory A3 sketch with the Technical Bid. | Yes |  |  |  | No past project is to be cited under this Parameter. Marks will be based only on the AIIMS Patna-specific written response and the mandatory A3 Functional Zoning and Flow Concept Sketch submitted with the Technical Bid.
R-959 | The mandatory A3 Functional Zoning and Flow Concept Sketch must show all specified minimum planning, flow, access, pressure gradient, and existing-building interface details. | 328 | 5.5(ii) | Mandatory | Include all eight required items (zoning, personnel flow, sample/material flow, equipment movement, waste/decontamination flow, maintenance access, pressure gradients, and existing interfaces) on the A3 concept sketch. | Yes |  |  |  | The mandatory A3 sketch shall show, at a minimum: (a) broad relationship of the BSL-3, BSL-2, support and engineering areas; (b) personnel flow; (c) sample and material flow; (d) equipment movement; (e) waste and decontamination flow; (f) maintenance access; (g) broad pressure-gradient direction; and (h) important existing-building interfaces requiring verification or modification.
R-960 | Bidder must explain how cost, reliability, maintainability, procurement time, and lifecycle implications will be evaluated when comparing technical alternatives. | 329 | 5.6(ii) | Mandatory | Explain the methodology for factoring in cost, reliability, maintainability, lead time, and lifecycle impacts during technical alternative evaluations. | Yes |  |  |  | The Bidder shall explain how cost, reliability, maintainability, procurement time and lifecycle implications will be considered while comparing technically compliant alternatives.
R-961 | Cost reductions that compromise mandatory biosafety, containment, reliability, testing, validation, or certification requirements will not be awarded marks. | 329 | 5.6(iii) | Evaluation criteria | Ensure no proposed cost reductions dilute any mandatory biosafety, containment, testing, or validation requirements. | Yes |  |  |  | Cost reduction that dilutes any mandatory biosafety, containment, reliability, testing, validation or certification requirement shall not earn marks.
R-962 | The same individual cannot serve as maker, checker, and final approver for the same containment-critical deliverable. | 330 | 5.7(ii) | Mandatory | Assign distinct personnel to maker, checker, and approver roles for each containment-critical deliverable. | Yes |  |  |  | The same person shall not act as maker, checker and final approver of the same containment-critical deliverable.
R-963 | No new methodology, expert, commitment, sketch, deliverable, or improvement can be submitted after the Bid Due Date. | 332 | (iv) | Mandatory | Ensure all methodologies, experts, commitments, sketches, deliverables, and proposed improvements are submitted on or before the Bid Due Date. | Yes |  |  |  | No new methodology, expert, commitment, sketch, deliverable or improvement shall be accepted after the Bid Due Date.
R-964 | Bidder must submit evidence of independent third-party validation and/or competent authority regulatory certification/approval for a completed BSL-3/BSL-4 facility included in its proposal. | 333 | 6.1 | Evaluation criteria | Provide documentary evidence that a completed BSL-3/BSL-4 facility in the Technical Proposal was independently validated by a third party or certified/approved by a competent authority. | Yes |  |  |  | The Bidder shall provide evidence that a completed BSL-3/BSL- 4 facility included in its Technical Proposal was independently validated by a competent third-party agency and/or received certification, licence, authorisation, operational approval or equivalent permission from the concerned competent authority.
R-965 | Bidder must submit relevant pages of the final independent validation report/certificate, regulatory approval/license document, and client proof of involvement. | 333 | 6.2(ii) | Mandatory | Submit relevant pages of the validation report/certificate, regulatory document, and client certificate/agreement/work order establishing the bidder's role. | Yes |  |  |  | The Bidder shall submit: (a) relevant pages of the final independent validation report or validation certificate; (b) copy of the certificate, license, authorization, operational approval or equivalent document issued by the concerned authority; and (c) client certificate, agreement, work order or another document establishing the Bidder’s involvement in the project.
R-966 | Submitted validation report pages must clearly identify the facility name, location, BSL level, issuing agency, and final result. | 333 | 6.2 | Submission logistics | Ensure submitted pages of the validation report clearly display the facility name, location, BSL level, issuing agency, and final result. | Yes |  |  |  | The submitted pages shall clearly show the facility name, location, BSL level, issuing agency and final result.
R-967 | Bidder must specify the project(s) used for Independent Validation and Certification claims (maximum two projects) and provide project details and PDF page numbers. | 333 | 6.3 | Evaluation criteria | Name the project(s) relied upon, stating the project, client, exact consultancy role, issuing agency/authority, document, final result, and exact Technical Bid PDF page numbers. | Yes |  |  |  | The Bidder shall name the project relied upon for Independent Validation and the project relied upon for Certification or Authorization. The same project may support both claims, or different projects (maximum two projects) may be used. For each claim, the Bidder shall state the project, client, its exact consultancy role, the issuing agency or authority, the document, the final result and the exact Technical Bid PDF page numbers in the form under this Parameter.
R-968 | Validation and certification documents submitted by the bidder must be verifiable by AIIMS Patna. | 334 | 6.5(vi) | Mandatory | Submit verifiable documents and facilitate verification with the concerned client, validating agency, or competent authority if required. | Yes |  |  |  | The documents shall be verifiable. AIIMS Patna may verify them from the concerned client, validating agency or competent authority.
R-969 | The technical presentation must focus specifically on the proposed AIIMS Patna BSL-3 laboratory, not general company credentials or past projects. | 335 | 7.1 | Mandatory | Prepare and deliver a presentation tailored exclusively to the AIIMS Patna BSL-3 laboratory assignment. | Yes |  |  |  | This presentation shall relate specifically to the proposed AIIMS Patna BSL- 3 laboratory. It shall not be a general company presentation or a presentation only about the Bidder’s past projects.
R-970 | No past project may be cited under Parameter 7; evaluation is based solely on AIIMS Patna-specific slides and the presentation Q&A. | 335 | 7.2 | Evaluation criteria | Exclude past project citations under this parameter and submit AIIMS Patna-specific presentation slides with the Technical Bid. | Yes |  |  |  | No past project is to be cited under this Parameter. Marks will be based only on the AIIMS Patna-specific slides submitted with the Technical Bid and the answers given by the proposed team during the presentation.
R-971 | Presentation is restricted to a maximum of 15 slides including the title slide. | 335 | 7.3(c) | Submission logistics | Limit presentation slides to a maximum of 15 slides, including the title slide. | Yes |  |  |  | The presentation shall contain a maximum of 15 slides, including the title slide.
R-972 | Hidden, backup, or additional presentation slides are strictly prohibited. | 335 | 7.3(d) | Submission logistics | Do not include any hidden, backup, or extra slides in the presentation submission. | Yes |  |  |  | Hidden slides, backup slides or additional slides shall not be permitted.
R-973 | Presentation slides must be submitted with the Technical Proposal, and no new documents or credentials may be introduced during the presentation. | 335 | 7.3(e) | Mandatory | Submit presentation slides along with the Technical Proposal and refrain from presenting new projects, experts, credentials, commitments, or technical documents. | Yes |  |  |  | The presentation slides shall be submitted with the Technical Proposal. No new project, expert, credential, commitment or technical document may be introduced during the presentation.
R-974 | The presentation must cover Part 1: Design preparation and sequence, estimate/BOQ/tender documents, and design checking and compliance. | 335 | 7.4 | Evaluation criteria | Include and explain design preparation/sequence, estimate/BOQ/tender documents, and design checking/compliance in the presentation. | No — check |  |  |  | The Bidder shall explain the following three matters: (i) Design preparation and sequence — 1 Mark (ii) Estimate, BOQ and tender documents — 1 Mark (iii) Design checking and compliance — 1 Mark
R-975 | The presentation must cover Part 2: Support during construction, support during testing/validation/certification, and support for operation and maintenance. | 336 | 7.5 | Evaluation criteria | Include and explain support during construction, support during testing/validation/certification, and support for O&M in the presentation. | Yes |  |  |  | The Bidder shall explain the following three matters: (i) Support during construction — 1 Mark (ii) Support during testing, validation and certification — 1 Mark (iii) Support for operation and maintenance — 1 Mark
R-976 | The proposed Project Lead, Project Director, or Biosafety Expert must personally attend and participate in the presentation and technical questions. | 337 | 7.9(i) | Evaluation criteria | Ensure that the proposed Project Lead, Project Director, or Biosafety Expert personally attends and participates in the presentation and common technical questions. | Yes |  |  |  | The proposed Project Lead/Project Director/the proposed Biosafety Expert shall personally attend (Anyone have to attended personally) and participate in the presentation and common technical questions.
R-977 | Marketing representatives or non-team members are prohibited from answering technical questions on behalf of proposed experts. | 337 | 7.9(iii) | Evaluation criteria | Do not allow marketing representatives or persons not part of the proposed team to answer technical questions. | Yes |  |  |  | A marketing representative or any person who is not part of the proposed team shall not answer technical questions on behalf of the proposed experts.
R-978 | Substitution of the proposed Project Lead, Biosafety Expert, or Project Director for the presentation is prohibited without prior written permission from AIIMS Patna. | 337 | 7.9(iv) | Mandatory | Do not substitute the proposed Project Lead, Biosafety Expert, or Project Director for the presentation unless specifically permitted by AIIMS Patna in writing. | Yes |  |  |  | Substitution of the proposed Project Lead or Biosafety Expert or project director for the presentation shall not be permitted unless specifically allowed by AIIMS Patna for reasons recorded in writing.
R-979 | The proposed team must answer technical questions without outside help, internet searches, or AI tools. | 337 | 7.10(v) | Evaluation criteria | Answer all common questions during the presentation without assistance from any external person, web search, or AI tool. | Yes |  |  |  | During the common questions, the proposed team shall answer without assistance from any outside person, internet search or AI tool.
R-980 | The presentation submitted by the bidder must contain a maximum of 15 slides. | 338 | 7.11 | Submission logistics | Limit the presentation slides to a maximum of 15 slides as required in the reference format. | Yes |  |  |  | Total number of slides, maximum 15
R-981 | A Joint Venture bidder must complete the work allocation table matching the JV Agreement and responsibility matrix. | 339 | 8.9 | Mandatory | Complete the Joint Venture members and work allocation table once, ensuring the work allocated matches the Joint Venture Agreement and responsibility matrix submitted in the Technical Bid. | Yes |  |  |  | The Joint Venture shall complete the following table once. The work stated for each Member shall match the Joint Venture Agreement and responsibility matrix submitted with the Technical Bid.
R-982 | The JV member performing a specific scope must demonstrate eligible experience for that scope, and experience cannot be shared across members. | 339 | 8.10(i) | Eligibility criteria | Ensure that each JV member allocated a technical scope demonstrates its own eligible experience and evidence under the relevant Parameter. | Yes |  |  |  | For each technical scope stated in the Joint Venture Agreement and responsibility matrix, the Member that will perform that scope in the AIIMS Patna assignment shall itself demonstrate the eligible experience and evidence required under the relevant Parameter.
R-983 | A Joint Venture is restricted to citing a maximum of six completed firm-level BSL-3/ABSL-3/BSL-4/ABSL-4 projects in total across Parameters 1, 2, and 6. | 339 | 8.10(iv) | Eligibility criteria | Cite no more than six completed firm-level BSL-3/ABSL-3/BSL-4/ABSL-4 projects across Parameters 1, 2, and 6 combined for all JV members. | Yes |  |  |  | Across Parameters 1, 2 and 6, the Joint Venture may cite a maximum of six completed firm-level BSL-3/ABSL-3/BSL-4/ABSL-4 projects in total. This limit applies to all Joint Venture Members together and not separately to each Member.
R-984 | For firm-level claims, a Joint Venture must specify the member that performed the work and the corresponding project. | 339 | 8.11(ii) | Submission logistics | Name the specific JV member that actually performed the claimed work and identify the project for every firm-level claim. | Yes |  |  |  | For every firm-level claim, the Joint Venture shall name the Member that actually performed the claimed work and the project in which that Member performed it.
R-985 | A Joint Venture must identify the member through which each expert under Parameters 3 and 4 is proposed. | 340 | 8.11(iv) | Submission logistics | State the member through which each named Expert under Parameters 3 and 4 is proposed. | Yes |  |  |  | Under Parameters 3 and 4, marks shall be based on the personal work of the named Expert. The Joint Venture shall also state the Member through which the Expert is proposed.
R-986 | A Joint Venture must submit one integrated AIIMS Patna-specific response aligned with its responsibility matrix under Parameter 5. | 340 | 8.12 | Submission logistics | Submit a single integrated AIIMS Patna-specific response with activity responsibilities consistent with the Joint Venture responsibility matrix. | Yes |  |  |  | The Joint Venture shall submit one integrated AIIMS Patna-specific response. The responsibility stated for each activity shall be consistent with the submitted Joint Venture responsibility matrix. One score shall be awarded for the combined response.
R-987 | Joint Venture bidders must complete the Joint Venture reference format with a separate row for each sub-parameter or scoring claim. | 340 | 8.6 | Submission logistics | Complete the Joint Venture reference format using a separate row for each sub-parameter or scoring claim relied upon. | Yes |  |  |  | This format shall be completed only by a Joint Venture. A separate row shall be used for each sub-parameter or scoring claim relied upon.
R-988 | If re-using evidence submitted under one parameter for another parameter, the bidder must clearly mention the relevant Technical Proposal page number. | 342 | 9.(ii) | Mandatory | Clearly cite the Technical Proposal page number of previously submitted evidence when relying on it under another parameter. | Yes |  |  |  | A document, drawing, report, review record, validation record or any other evidence already submitted under one Parameter may be relied upon under another applicable Parameter by clearly mentioning the relevant Technical Proposal page number.
R-989 | When submitting redacted documents due to confidential or sensitive information, the project identity, document type, revision/date, bidder's role, and relied-upon technical matter must remain clearly identifiable. | 342 | 9.(v) | Mandatory | Ensure that redacted document extracts retain clear identification of project identity, document type, revision/date, role of the bidder, and the specific technical matter. | Yes |  |  |  | Where a document contains confidential, proprietary or security-sensitive information, the Bidder may submit an appropriately redacted extract, provided that the project identity, document type, revision/date, Bidder's role and the technical matter relied upon remain clearly identifiable.
R-990 | Only evidence that existed prior to the Bid Submission Deadline is eligible for consideration. | 342 | 9.(vi) | Eligibility criteria | Ensure all submitted technical evidence existed prior to the Bid Submission Deadline. | Yes |  |  |  | Only evidence that existed prior to the Bid Submission Deadline shall be considered.
R-991 | During clarification, bidders are not permitted to introduce a new project, new technical claim, or substitute evidence from another project. | 342 | 9.(viii) | Mandatory | Do not submit or introduce new projects, new technical claims, or substitute evidence from another project in response to clarification requests. | Yes |  |  |  | Such clarification shall not permit introduction of a new project, new technical claim or substitute evidence from another project.

## Instructions
Column | What it means / how to use it
ID | Requirement code assigned by BidMatrix (R-001, R-002, ...) in document order. Use it to reference rows with your team.
Requirement | What the tender requires, restated concisely. This is what you must satisfy to stay in the race.
Page | Page number in the uploaded tender PDF where the requirement was found. Use it to jump to the source.
Section | Section / clause reference as printed in the document (when visible), e.g. "Section 2.1".
Category | One of: Eligibility criteria (who may bid), Mandatory (must comply or be disqualified), Desirable (scores points), Evaluation criteria (how the bid is scored), Submission logistics (how/when/where to submit).
Required action | The concrete action your team must take to comply (attach a certificate, register, sign, deposit EMD, etc.).
Verified? | Yes = the source quote was programmatically confirmed against the extracted text of the cited page. "No — check" = the quote could NOT be confirmed (row highlighted amber) — always re-check these rows manually against the PDF.
Compliant? | Your team status. Set in the app: yes / no / partial. Empty means not yet assessed.
Owner | Person responsible for closing this requirement (set in the app).
Notes | Free-text notes (set in the app).
Source quote | The verbatim quote from the tender that produced this row — your evidence trail.
Tender file | RFPtenderdocument.pdf
Pages | 343
Requirements | 991
Unverified rows | 9
Exported | 2026-09-07T06:54:54.258Z